## R1-7MLD Puttenahalli STP _ Rela
Task Name | Duration | Start Date | End Date
7 MLD SBR TECHNOLOGY STP AT PUTTENAHALLI LAKE, YELAHANKA - OVERALL PROJECT SCHEDULE | 549d | 2020-05-04 | 2021-11-03
PROJECT INITIATION & PRELIMINARY MOBILISATION | 25d | 2020-05-04 | 2020-05-28
MILESTONE: NOTICE TO COMMENCE WORK, RECEIPT OF WO & OFFICIAL PROJECT START DATE | ~0 | 2020-05-04 | 2020-05-04
PROJECT KICK OFF MEETING | 1d | 2020-05-12 | 2020-05-12
MILESTONE: COMPLETION OF SIGNING OF CONTRACT DOCS | ~0 | 2020-05-18 | 2020-05-18
SUBMISSION OF ORGANISATION CHART | 1d | 2020-05-26 | 2020-05-26
MOBILISATION OF CONTRACTOR'S REPRESENTATIVE | 1d | 2020-05-27 | 2020-05-27
MOBILISATION OF PROJECT MANAGER | 1d | 2020-05-28 | 2020-05-28
HANDING OVER OF SITE BY CLIENT | 1d | 2020-05-20 | 2020-05-20
SOIL & SITE INVESTIGATION/SURVEY | 80d | 2020-05-13 | 2020-07-31
MOBILISATION & DEMOBILISATION OF TOPOGRAPHIC SURVEY TEAM | 69d | 2020-05-13 | 2020-07-20
APPROVAL OF TOPOGRAPHIC SURVEY | 60d | 2020-06-02 | 2020-07-31
MOBILISATION & DEMOBILISATION OF GEO-TECHNICAL SURVEY TEAM | 60d | 2020-05-27 | 2020-07-25
APPROVAL OF GEO-TECHNICAL REPORT | 60d | 2020-06-02 | 2020-07-31
SITE ESTABLISHMENT | 95d | 2020-05-29 | 2020-08-31
ESTABLISHMENT OF SITE OFFICE | 24d | 2020-05-29 | 2020-06-21
EST. OF CONSTRUCTION - POWER & WATER | 60d | 2020-06-15 | 2020-08-13
EST. OF LABORATORY | 60d | 2020-07-03 | 2020-08-31
EST. OF STORAGE YARD | 15d | 2020-08-17 | 2020-08-31
EST. OF OTHER TEMPORARY STRUCTURES (As Req.) | 60d | 2020-07-03 | 2020-08-31
DEMOLITION ACTIVITIES | 68d | 2020-05-25 | 2020-07-31 | construction and execution of work | Existing structure demolition Scheme
STATUTORY CLEARANCE FOR DEMOLITION OF EXISTING STRUCTURES BY EMPLOYER | 40d | 2020-05-25 | 2020-07-03
DISMANTLING OF EQUIPMENT, PIPES, FITTINGS ETC. | 7d | 2020-05-29 | 2020-06-04
DEMOLITION OF APPROVED EXISTING STRUCTURES | 31d | 2020-07-01 | 2020-07-31
APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL) | 80d | 2020-07-27 | 2020-10-14 |  | Existing structure demolition Scheme | Organizational chart
FINALISATION FOR CIVIL WORKS | 30d | 2020-07-27 | 2020-08-25 | construction and execution of work
FINALISATION FOR MECHANICAL WORKS | 30d | 2020-08-11 | 2020-09-09
FINALISATION FOR PIPING WORKS | 30d | 2020-08-21 | 2020-09-19
FINALISATION FOR ELECTRICAL WORKS | 30d | 2020-09-05 | 2020-10-04
FINALISATION FOR INSTRUMENTATION WORKS | 30d | 2020-09-15 | 2020-10-14
MOBILISATION OF SITE TEAMS | 259d | 2020-11-11 | 2021-07-27
MOBILISATION FOR CIVIL WORKS | 6d | 2020-11-11 | 2020-11-16
MOBILISATION FOR MECHANICAL WORKS | 20d | 2021-03-28 | 2021-04-16
MOBILISATION FOR PIPING WORKS WORKS | 7d | 2021-04-10 | 2021-04-16
MOBILISATION FOR ELECTRICAL WORKS | 7d | 2021-07-14 | 2021-07-20
MOBILISATION FOR INSTRUMENTATION WORKS | 7d | 2021-07-21 | 2021-07-27
BASIC ENGINEERING PACKAGE | 386d | 2020-05-19 | 2021-06-08 | construction and execution of work | Process design calculations |  | Document
PROCESS DESIGN DOCUMENT (BEP TECHNICAL PROPOSAL) | 386d | 2020-05-19 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
HYDRAULIC FLOW DIAGRAM | 386d | 2020-05-19 | 2021-06-08 | construction and execution of work | Hydrolic flow diagram |  | document
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
SITE LAYOUT | 386d | 2020-05-19 | 2021-06-08 | Civil GA Drawings and Structural Design & Drawings
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
P&I DIAGRAM | 317d | 2020-07-27 | 2021-06-08 | Process and Instrumentation Diagram (P&ID) |  |  | document
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-07-27 | 2020-08-04
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-08-05 | 2020-08-11
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-08-12 | 2020-08-18
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-08-19 | 2020-08-25
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
PIPING & VALVES SCHEDULE | 287d | 2020-08-26 | 2021-06-08 | ???? |  |  | document
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-08-26 | 2020-09-04
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-09-05 | 2020-09-11
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-12 | 2020-09-18
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-09-19 | 2020-09-25
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
ELECTRICAL LOAD LIST | 266d | 2020-09-16 | 2021-06-08 | 15) Electrical General Arrangement Drawings | GA drawings and details |  | document
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-09-16 | 2020-09-25
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-09-26 | 2020-10-02
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-03 | 2020-10-09
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-10-10 | 2020-10-16
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
PLANT OPERATION & CONTROL PHILOSOPHY | 266d | 2020-09-16 | 2021-06-08 | construction and execution of work | Design basis report |  | document
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-09-16 | 2020-09-25
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-26 | 2020-10-09
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-10-17 | 2020-10-23
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
VENDOR CREDENTIALS | 180d | 2020-05-29 | 2020-11-24 | General Documents | Credentials and details |  | document
SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF CEMENT/ STEEL/ AGGREGATES/ OTHER CIVIL ITEMS ETC. AS APPLICABLE | 90d | 2020-05-29 | 2020-08-26
SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF MECHANICAL/ ELECTRICAL/ INSTRUMENTATION ITEMS ETC. AS APPLICABLE | 180d | 2020-05-29 | 2020-11-24
DETAILED ENGINEERING, PROCUREMENT, CONSTRUCTION & ERECTION - UNIT WISE | 374d | 2020-07-27 | 2021-08-04
CIVIL DESIGN BASIS REPORT | 317d | 2020-07-27 | 2021-06-08 | construction and execution of work | Design basis report |  | document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-07-27 | 2020-08-09
ENGINEER'S COMMENTS ON 1st SUBMISSION | 10d | 2020-08-10 | 2020-08-19
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-08-20 | 2020-08-26
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-08-27 | 2020-09-02
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
MECHANICAL COARSE SCREEN & BELT CONVEYOR | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
SUBMERSIBLE PUMPS & ACCESSORIES | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA drawings and details |  | documants
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings |  | documents
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR TSPS & ALLIED UNITS | 258d | 2020-11-11 | 2021-07-26 | Construction and execution of works | Contructions program
COMPLETION OF EXCAVATION | 15d | 2020-11-11 | 2020-11-25
COMPLETION OF PCC | 12d | 2020-11-26 | 2020-12-07
COMPLETION OF RAFT | 30d | 2020-12-08 | 2021-01-06
COMPLETION OF 50% SIDE WALL | 75d | 2020-12-23 | 2021-03-07
COMPLETION 100% SIDE WALL | 65d | 2021-02-21 | 2021-04-26
COMPLETION OF PLINTH LEVEL SLAB | 25d | 2021-04-17 | 2021-05-11
COMPLETION OF COLUMN/BEAM UPTO TOP SLAB | 15d | 2021-05-07 | 2021-05-21
COMPLETION OF TOP SLAB | 28d | 2021-05-12 | 2021-06-08
COMPLETION OF BLOCK MASONRY | 20d | 2021-06-09 | 2021-06-28
COMPLETION OF HYDRO TEST | 28d | 2021-06-29 | 2021-07-26
COMPLETION OF WATER PROOFING | 20d | 2021-06-22 | 2021-07-11
COMPLETION OF FINISHING WORKS | 25d | 2021-07-02 | 2021-07-26
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
MECHANICAL FINE SCREEN & BELT CONVEYOR | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 | Construction and execution of works | Contructions program
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 | Construction and execution of works | Contructions program
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27 | Construction and execution of works | Contructions program
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13 | Construction and execution of works | Contructions program
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20 | Construction and execution of works | Contructions program
MECHANICAL GRIT REMOVAL DETRITOR MECHANISM | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 | Construction and execution of works | Contructions program
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA drawings and details |  | documants
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings |  | documents
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER | 124d | 2021-04-01 | 2021-08-02 | Construction and execution of works | Contructions program
COMPLETION OF EXCAVATION | 7d | 2021-04-01 | 2021-04-07 | Construction and execution of works | Contructions program
COMPLETION OF PCC | 12d | 2021-04-08 | 2021-04-19 | Construction and execution of works | Contructions program
COMPLETION OF RAFT/COLUMNS | 25d | 2021-04-20 | 2021-05-14 | Construction and execution of works | Contructions program
COMPLETION OF 50% SIDE WALL & BASE SLABS | 60d | 2021-05-05 | 2021-07-03 | Construction and execution of works | Contructions program
COMPLETION 100% SIDE WALL | 45d | 2021-06-19 | 2021-08-02 | Construction and execution of works | Contructions program
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Construction and execution of works | Contructions program
COMPLETION OF FINISHING WORKS | 30d | 2021-06-28 | 2021-07-27 | Construction and execution of works | Contructions program
ERECTION | 110d | 2021-04-17 | 2021-08-04 | Construction and execution of works | Contructions program
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Construction and execution of works | Contructions program
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Construction and execution of works | Contructions program
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04 | Construction and execution of works | Contructions program
SEQUENTIAL BATCH REACTORS | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
DECANTERS | 233d | 2020-07-27 | 2021-03-16
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 10d | 2020-09-14 | 2020-09-23
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-24 | 2020-10-07
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-08 | 2020-10-12 | Construction and execution of works | Contructions program
MANUFACTURING | 120d | 2020-10-13 | 2021-02-09 | Construction and execution of works | Contructions program
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-10 | 2021-02-23 | Construction and execution of works | Contructions program
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-24 | 2021-03-09 | Construction and execution of works | Contructions program
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-10 | 2021-03-16 | Construction and execution of works | Contructions program
DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
PUMPING MACHINERY | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR SEQUENTIAL BATCH REACTORS | 237d | 2020-12-08 | 2021-08-01
COMPLETION OF EXCAVATION | 10d | 2020-12-08 | 2020-12-17
COMPLETION OF PCC | 12d | 2020-12-18 | 2020-12-29
COMPLETION OF RAFT | 30d | 2020-12-30 | 2021-01-28
COMPLETION OF 50% SIDE WALL | 80d | 2021-01-09 | 2021-03-29
COMPLETION 100% SIDE WALL | 110d | 2021-03-10 | 2021-06-27
COMPLETION OF HYDRO TEST | 30d | 2021-06-28 | 2021-07-27
COMPLETION OF FINISHING WORKS | 35d | 2021-06-28 | 2021-08-01
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DEEP BED MEDIA FILTERS | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
AIR SCOUR BLOWERS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
UNDERDRAIN COMPONENTS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR DEEP BED MEDIA FILTERS | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-01-29 | 2021-02-04
COMPLETION OF PCC | 10d | 2021-02-05 | 2021-02-14
COMPLETION OF RAFT | 30d | 2021-02-15 | 2021-03-16
COMPLETION OF 50% SIDE WALL | 30d | 2021-03-02 | 2021-03-31
COMPLETION 100% SIDE WALL | 45d | 2021-03-17 | 2021-04-30
COMPLETION OF TROUGHS & ALLIED CHANNELS | 28d | 2021-03-24 | 2021-04-20
COMPLETION OF TOP SLAB | 28d | 2021-04-21 | 2021-05-18
COMPLETION OF HYDRO TEST | 28d | 2021-05-19 | 2021-06-15
COMPLETION OF BLOCK MASONRY FOR MACHINE ROOM | 25d | 2021-05-19 | 2021-06-12
COMPLETION OF WATER PROOFING | 21d | 2021-06-13 | 2021-07-03
COMPLETION OF FINISHING WORKS | 30d | 2021-07-04 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
CHLORINE CONTACT TANK | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PLANT SERVICE WATER PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR CHLORINE CONTACT TANK | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
INTERMEDIATE SUMP & PLANT DRAIN DRAIN SUMP | 374d | 2020-07-27 | 2021-08-04 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
FILTER FEED PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
PLANT DRAIN PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR INTERMEDIATE SUMP & PDS | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
THICKENER FEED SUMP (SURPLUS SLUDGE SUMP) | 374d | 2020-07-27 | 2021-08-04 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
THICKENER FEED PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
AIR BLOWERS/MIXERS FOR SLUDGE AGITATION | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR THICKENER FEED SUMP | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
SLUDGE THICKENER | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
THICKENER MECHANISM/MACHINERY | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
POLY-ELECTROLYTE DOSING UNITS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR SLUDGE THICKENER | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
CENTRIFUGE FEED PUMPS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR THICK SLUDGE SUMP | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
CENTRIFUGE BUILDING & CENTRATE SUMP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
SLUDGE DEWATERING CENTRIFUGE MACHINERY | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
CENTRATE TRANSFER PUMPS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR CENTRIFUGE BUILDING & CENTRATE SUMP | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 30d | 2021-02-18 | 2021-03-19
COMPLETION OF 50% SIDE WALL | 48d | 2021-03-05 | 2021-04-21
COMPLETION OF 100% SIDE WALL | 45d | 2021-04-07 | 2021-05-21
COMPLETION OF RCC WORK UPTO PLINTH LEVEL FOR CENTRIFUGE BUILDING | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
COMPLETION OF HYDRO TEST OF CENTRATE SUMP | 28d | 2021-05-22 | 2021-06-18
COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DRIED SLUDGE STORAGE SHED | 301d | 2020-09-30 | 2021-07-27
CIVIL DESIGN DRAWINGS | 252d | 2020-09-30 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL WORKS FOR DRIED SLUDGE STORAGE SHED | 170d | 2021-02-08 | 2021-07-27
COMPLETION OF EXCAVATION | 7d | 2021-02-08 | 2021-02-14
COMPLETION OF PCC | 12d | 2021-02-15 | 2021-02-26
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 28d | 2021-05-05 | 2021-06-01
COMPLETION OF WORK UPTO ROOF SHED | 28d | 2021-05-05 | 2021-06-01
COMPLETION OF TOP ROOF | 28d | 2021-06-02 | 2021-06-29
COMPLETION OF FINISHING WORKS | 28d | 2021-06-30 | 2021-07-27
CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR CHLORINATION ROOM & CHEMICAL ROOM | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 12d | 2021-01-29 | 2021-02-09
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
AIR BLOWER ROOM (PROCESS) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
PROCESS AIR BLOWERS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MOTORS FOR AIR BLOWERS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR AIR BLOWER ROOM | 154d | 2021-03-02 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-03-02 | 2021-03-08
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 21d | 2021-03-09 | 2021-03-29
COMPLETION OF GRADE SLAB/PCC | 28d | 2021-03-30 | 2021-04-26
COMPLETION OF RCC UPTO TOP SLAB | 56d | 2021-03-30 | 2021-05-24
COMPLETION OF TOP SLAB | 28d | 2021-05-25 | 2021-06-21
COMPLETION OF BLOCK MASONRY | 21d | 2021-06-22 | 2021-07-12
COMPLETION OF FINISHING WORKS | 21d | 2021-07-13 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 244d | 2020-07-27 | 2021-03-27
LAB EQUIPMENT | 244d | 2020-07-27 | 2021-03-27 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 21d | 2020-07-27 | 2020-08-16
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-17 | 2020-08-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-24 | 2020-09-20
RESUBMISSION | 14d | 2020-09-21 | 2020-10-04
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-10-05 | 2020-10-18
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-19 | 2020-10-23
MANUFACTURING | 120d | 2020-10-24 | 2021-02-20
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-21 | 2021-03-06
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-03-07 | 2021-03-20
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-21 | 2021-03-27
UPS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
CIVIL DESIGN DRAWINGS | 279d | 2020-09-03 | 2021-06-08 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 21d | 2020-09-03 | 2020-09-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-24 | 2020-10-07
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-08 | 2020-10-14
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-15 | 2020-10-21
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL WORKS FOR ADMIN BUILDING, PLC ROOM, LAB & WORKSHOP | 228d | 2020-12-18 | 2021-08-02
COMPLETION OF EXCAVATION | 6d | 2020-12-18 | 2020-12-23
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2020-12-24 | 2021-01-20
COMPLETION OF GRADE SLAB/PCC | 15d | 2021-01-21 | 2021-02-04
COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-01-21 | 2021-02-19
COMPLETION OF GF SLAB | 30d | 2021-02-20 | 2021-03-21
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-03-22 | 2021-04-11
COMPLETION OF TOP SLAB | 28d | 2021-04-12 | 2021-05-09
COMPLETION OF BLOCK MASONRY | 25d | 2021-05-10 | 2021-06-03
COMPLETION OF WATERPROOFING | 28d | 2021-06-04 | 2021-07-01
COMPLETION OF FINISHING WORKS | 60d | 2021-06-04 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04 |  |  |  |  | ca drawings strucural designs and drawings
HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM | 333d | 2020-09-06 | 2021-08-04 |  |  |  |  | ga drawings and details
ELECTRICAL DESIGN DRAWINGS | 85d | 2020-09-06 | 2020-11-29 |  |  |  |  | technical data sheets
PREPARATION & SUBMISSION TO CLIENT | 24d | 2020-10-17 | 2020-11-09
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-10 | 2020-11-23
RE-SUBMISSION FOR CODE-B APPROVAL | 1d | 2020-11-24 | 2020-11-24
ENGINEER'S REVIEW AND CODE-B APPROVAL | 5d | 2020-11-25 | 2020-11-29
RE-SUBMISSION FOR CODE-A APPROVAL | 2d | 2020-09-06 | 2020-09-07
ENGINEER'S REVIEW AND CODE-A APPROVAL | 3d | 2020-09-08 | 2020-09-10
CIVIL DESIGN DRAWINGS | 221d | 2020-11-30 | 2021-07-08 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-30 | 2020-12-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-14 | 2020-12-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-28 | 2021-01-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-01-04 | 2021-01-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
CIVIL WORKS FOR HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM | 195d | 2021-01-11 | 2021-07-24
COMPLETION OF EXCAVATION | 7d | 2021-01-11 | 2021-01-17
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-18 | 2021-02-14
COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-15 | 2021-03-07
COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-02-15 | 2021-03-16
COMPLETION OF GF SLAB | 28d | 2021-03-17 | 2021-04-13
COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-04-14 | 2021-05-11
COMPLETION OF TOP SLAB | 21d | 2021-05-12 | 2021-06-01
COMPLETION OF BLOCK MASONRY | 25d | 2021-06-02 | 2021-06-26
COMPLETION OF WATERPROOFING | 21d | 2021-06-27 | 2021-07-17
COMPLETION OF FINISHING WORKS | 28d | 2021-06-27 | 2021-07-24
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DG ROOM | 333d | 2020-09-06 | 2021-08-04
ELECTRICAL DESIGN DRAWINGS | 85d | 2020-09-06 | 2020-11-29
PREPARATION & SUBMISSION TO CLIENT | 24d | 2020-10-17 | 2020-11-09
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-10 | 2020-11-23
RE-SUBMISSION FOR CODE-B APPROVAL | 1d | 2020-11-24 | 2020-11-24
ENGINEER'S REVIEW AND CODE-B APPROVAL | 5d | 2020-11-25 | 2020-11-29
RE-SUBMISSION FOR CODE-A APPROVAL | 2d | 2020-09-06 | 2020-09-07
ENGINEER'S REVIEW AND CODE-A APPROVAL | 3d | 2020-09-08 | 2020-09-10
CIVIL DESIGN DRAWINGS | 221d | 2020-11-30 | 2021-07-08 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-30 | 2020-12-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-14 | 2020-12-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-28 | 2021-01-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-01-04 | 2021-01-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
CIVIL WORKS FOR DG ROOM | 138d | 2021-01-11 | 2021-05-28
COMPLETION OF EXCAVATION | 12d | 2021-01-11 | 2021-01-22
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-23 | 2021-02-19
COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-20 | 2021-03-12
COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-02-20 | 2021-03-19
COMPLETION OF TOP SLAB | 21d | 2021-03-20 | 2021-04-09
COMPLETION OF BLOCK MASONRY | 21d | 2021-04-10 | 2021-04-30
COMPLETION OF WATERPROOFING | 21d | 2021-05-01 | 2021-05-21
COMPLETION OF FINISHING WORKS | 28d | 2021-05-01 | 2021-05-28
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
GUARD ROOM | 334d | 2020-09-03 | 2021-08-02 | ca drawings strucural designs and drawings | GA Drawings
CIVIL DESIGN DRAWINGS | 279d | 2020-09-03 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 21d | 2020-09-03 | 2020-09-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-24 | 2020-10-07
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-08 | 2020-10-14
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-15 | 2020-10-21
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL WORKS FOR GUARD ROOM | 88d | 2021-05-07 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-05-07 | 2021-05-13
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 14d | 2021-05-14 | 2021-05-27
COMPLETION OF GRADE SLAB/PCC | 14d | 2021-05-28 | 2021-06-10
COMPLETION OF RCC UPTO TOP SLAB | 15d | 2021-05-28 | 2021-06-11
COMPLETION OF TOP SLAB | 21d | 2021-06-12 | 2021-07-02
COMPLETION OF BLOCK MASONRY | 10d | 2021-07-03 | 2021-07-12
COMPLETION OF WATERPROOFING | 14d | 2021-07-13 | 2021-07-26
COMPLETION OF FINISHING WORKS | 7d | 2021-07-27 | 2021-08-02
ROAD, DRAINS, & LANDSCAPING WORKS | 206d | 2021-01-11 | 2021-08-04
CIVIL DESIGN DRAWINGS | 194d | 2021-01-11 | 2021-07-23
PREPARATION & SUBMISSION TO CLIENT | 14d | 2021-01-11 | 2021-01-24
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2021-01-25 | 2021-02-07
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2021-02-08 | 2021-02-14
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-02-15 | 2021-02-21
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-21 | 2021-07-05
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-07-06 | 2021-07-23
CIVIL WORKS - ROADS - 100% COMPLETION | 45d | 2021-06-21 | 2021-08-04
CIVIL WORKS - DRAINS - 100% COMPLETION | 60d | 2021-06-06 | 2021-08-04
COMPOUND WALL(AS SUITABLE/APPLICABLE) | 60d | 2021-06-06 | 2021-08-04
PLANTATION WORKS - LANDSCAPING - 100% COMPLETION INCL. SOIL FILL UP AND DRESSING | 90d | 2021-05-07 | 2021-08-04
OTHER PLANT MECHANICAL, PIPING AND E&I WORKS (VALVES, PIPES, FITTINGS & OTHER COMMON E&I ITEMS) | 313d | 2020-09-26 | 2021-08-04
PROCUREMENT | 267d | 2020-09-26 | 2021-06-19
GATE VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
KNIFE GATE VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
NON RETURN VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
BALL VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
BUTTERFLY VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
DI PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
SS PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
MS PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
EOT/HOT HOIST ARRANGEMENTS | 237d | 2020-10-26 | 2021-06-19 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-10-26 | 2020-11-08
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-11-09 | 2020-11-15
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-16 | 2020-12-13
RESUBMISSION | 14d | 2020-12-14 | 2020-12-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-28 | 2021-01-10
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-11 | 2021-01-15
MANUFACTURING | 120d | 2021-01-16 | 2021-05-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-16 | 2021-05-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-30 | 2021-06-12
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-13 | 2021-06-19
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT & FITTINGS | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQUIPMENT & FIXTURES | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
ELECTRICAL WORKS | 292d | 2020-10-17 | 2021-08-04
ENGINEERING & DOCUMENTATION - ELECTRICAL | 265d | 2020-10-17 | 2021-07-08
TRANSFORMER SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
DG SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
LT CAPACITOR SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
SINGLE LINE DIAGRAM | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
ELECTRICAL HT SUBSTATION LAYOUT | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
EARTHING GRID DESIGN & LAYOUT | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
LIGHTING DESIGN & LAYOUT | 216d | 2020-12-05 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-19 | 2021-01-01
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
POWER & CONTROL CABLE SCHEDULE | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
CABLE ROUTING DRAWING | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
PROCUREMENT - ELECTRICAL | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
TRANSFORMER | 237d | 2020-10-17 | 2021-06-10
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
HT PANELS | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
LT PANELS | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
DISTRIBUTION BOXES | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
HT & LT CABLES & TRAYS (AS APPLICABLE) | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
ERECTION | 60d | 2021-06-06 | 2021-08-04
ERECTION OF ELECTRICAL EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST (DRY/WET FOR ELECTRICAL EQUIPMENT AS APPLICABLE) | 15d | 2021-07-21 | 2021-08-04
INSTRUMENTATION CONTROL & AUTOMATION WORKS | 285d | 2020-10-24 | 2021-08-04 | Instrumentation, control and automation documents | GA drawings and details |  | document
ENGINEERING & DOCUMENTATION - ICA | 258d | 2020-10-24 | 2021-07-08
FUNCTIONAL DESIGN SPECIFICATION | 228d | 2020-10-24 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-24 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-07 | 2020-11-20
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-28 | 2020-12-04
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
INSTRUMENT SCHEDULE | 216d | 2020-12-05 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-19 | 2021-01-01
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
INSTRUMENT DATASHEETS | 216d | 2020-12-05 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-19 | 2021-01-01
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
I/O SCHEDULE | 211d | 2020-12-10 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-10 | 2020-12-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-24 | 2021-01-06
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-07 | 2021-01-13
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-14 | 2021-01-20
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
INSTRUMENT LOCATION LAYOUT WITH CABLE ROUTING | 209d | 2020-12-12 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-26 | 2021-01-08
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-16 | 2021-01-22
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
PROCUREMENT - ICA | 262d | 2020-10-24 | 2021-07-12 | Instrumentation, control and automation documents | Data sheets |  | document
INSTRUMENTATION (AS PER APPROVED LIST) | 237d | 2020-10-24 | 2021-06-17
VENDOR FINALISATION & ORDER | 14d | 2020-10-24 | 2020-11-06
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-11-07 | 2020-11-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-14 | 2020-12-11
RESUBMISSION | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-26 | 2021-01-08
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-09 | 2021-01-13
MANUFACTURING | 120d | 2021-01-14 | 2021-05-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-14 | 2021-05-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-28 | 2021-06-10
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-11 | 2021-06-17
INSTRUMENTATION CABLES - POWER & CONTROL CABLES | 237d | 2020-10-24 | 2021-06-17 | Instrumentation, control and automation documents | Data sheets |  | document
VENDOR FINALISATION & ORDER | 14d | 2020-10-24 | 2020-11-06
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-11-07 | 2020-11-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-14 | 2020-12-11
RESUBMISSION | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-26 | 2021-01-08
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-09 | 2021-01-13
MANUFACTURING | 120d | 2021-01-14 | 2021-05-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-14 | 2021-05-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-28 | 2021-06-10
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-11 | 2021-06-17
INSTRUMENTATION CABLES TRAY & SUPPORTS | 177d | 2021-01-09 | 2021-07-04 | Instrumentation, control and automation documents | Data sheets |  | document
VENDOR FINALISATION & ORDER | 14d | 2021-01-09 | 2021-01-22
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2021-01-23 | 2021-01-29
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2021-01-30 | 2021-02-26
RESUBMISSION | 14d | 2021-02-27 | 2021-03-12
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2021-03-13 | 2021-03-26
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-03-27 | 2021-03-31
MANUFACTURING | 60d | 2021-04-01 | 2021-05-30
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-31 | 2021-06-13
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-06-14 | 2021-06-27
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-28 | 2021-07-04
PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) | 185d | 2021-01-09 | 2021-07-12 | Instrumentation, control and automation documents | Data sheets |  | document
VENDOR FINALISATION & ORDER | 14d | 2021-01-09 | 2021-01-22
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2021-01-23 | 2021-01-29
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2021-01-30 | 2021-02-26
RESUBMISSION | 7d | 2021-02-27 | 2021-03-05
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2021-03-06 | 2021-03-19
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-03-20 | 2021-03-24
MANUFACTURING | 75d | 2021-03-25 | 2021-06-07
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-06-08 | 2021-06-21
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-06-22 | 2021-07-05
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-07-06 | 2021-07-12
ERECTION | 60d | 2021-06-06 | 2021-08-04
ERECTION OF ICA EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST (DRY/WET FOR ICA EQUIPMENT AS APPLICABLE) | 15d | 2021-07-21 | 2021-08-04
COMMISSIONING | 91d | 2021-08-05 | 2021-11-03
PREPARATION & SUBMISSION OF O&M MANUALS | 50d | 2021-09-14 | 2021-11-02
PREPARATION & SUBMISSION OF AS BUILT DRAWINGS | 50d | 2021-09-14 | 2021-11-02
STABILITY TEST RUN ON COMPLETION OF WORKS | 30d | 2021-08-05 | 2021-09-03
PERFORMANCE RUN & COMMISSIONING | 60d | 2021-09-04 | 2021-11-02
TRAINING OF BWSSB STAFF | 10d | 2021-10-24 | 2021-11-02
HANDING OVER OF PLANT TO CLIENT | 1d | 2021-11-03 | 2021-11-03
ISSUE OF TAKING OVER CERTIFICATE BY CLIENT | ~0 | 2021-11-03 | 2021-11-03
MILESTONE: START DATE | ~0 | 2020-05-04 | 2020-05-04
OVERALL PROJECT TIMELINE | 549d | 2020-05-04 | 2021-11-03
MILESTONE: END DATE | ~0 | 2021-11-03 | 2021-11-03

## Sheet1
Task Name | Duration | Start Date | End Date
7 MLD SBR TECHNOLOGY STP AT PUTTENAHALLI LAKE, YELAHANKA - OVERALL PROJECT SCHEDULE | 549d | 2020-05-04 | 2021-11-03 | 11) Construction / Execution of Work | Existing structures demolition Scheme
PROJECT INITIATION & PRELIMINARY MOBILISATION | 25d | 2020-05-04 | 2020-05-28 | 11) Construction / Execution of Work | Construction Programme
MILESTONE: NOTICE TO COMMENCE WORK, RECEIPT OF WO & OFFICIAL PROJECT START DATE | ~0 | 2020-05-04 | 2020-05-04 | 1) Feasibility Report
PROJECT KICK OFF MEETING | 1d | 2020-05-12 | 2020-05-12 | 5) Detailed Design Report (DDR) | Draft DDR {PDF,Doc,Excel} | A) Report
MILESTONE: COMPLETION OF SIGNING OF CONTRACT DOCS | ~0 | 2020-05-18 | 2020-05-18
SUBMISSION OF ORGANISATION CHART | 1d | 2020-05-26 | 2020-05-26
MOBILISATION OF CONTRACTOR'S REPRESENTATIVE | 1d | 2020-05-27 | 2020-05-27
MOBILISATION OF PROJECT MANAGER | 1d | 2020-05-28 | 2020-05-28
HANDING OVER OF SITE BY CLIENT | 1d | 2020-05-20 | 2020-05-20
SOIL & SITE INVESTIGATION/SURVEY | 80d | 2020-05-13 | 2020-07-31
MOBILISATION & DEMOBILISATION OF TOPOGRAPHIC SURVEY TEAM | 69d | 2020-05-13 | 2020-07-20
APPROVAL OF TOPOGRAPHIC SURVEY | 60d | 2020-06-02 | 2020-07-31
MOBILISATION & DEMOBILISATION OF GEO-TECHNICAL SURVEY TEAM | 60d | 2020-05-27 | 2020-07-25
APPROVAL OF GEO-TECHNICAL REPORT | 60d | 2020-06-02 | 2020-07-31
SITE ESTABLISHMENT | 95d | 2020-05-29 | 2020-08-31
ESTABLISHMENT OF SITE OFFICE | 24d | 2020-05-29 | 2020-06-21
EST. OF CONSTRUCTION - POWER & WATER | 60d | 2020-06-15 | 2020-08-13
EST. OF LABORATORY | 60d | 2020-07-03 | 2020-08-31
EST. OF STORAGE YARD | 15d | 2020-08-17 | 2020-08-31
EST. OF OTHER TEMPORARY STRUCTURES (As Req.) | 60d | 2020-07-03 | 2020-08-31
DEMOLITION ACTIVITIES | 68d | 2020-05-25 | 2020-07-31 | Construction / Execution of Work | Existing structures demolition Scheme
STATUTORY CLEARANCE FOR DEMOLITION OF EXISTING STRUCTURES BY EMPLOYER | 40d | 2020-05-25 | 2020-07-03 |  | DEMOLITION ACTIVITIES
DISMANTLING OF EQUIPMENT, PIPES, FITTINGS ETC. | 7d | 2020-05-29 | 2020-06-04
DEMOLITION OF APPROVED EXISTING STRUCTURES | 31d | 2020-07-01 | 2020-07-31
APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL) | 80d | 2020-07-27 | 2020-10-14 |  | Existing structures demolition Scheme | Organizational chart
FINALISATION FOR CIVIL WORKS | 30d | 2020-07-27 | 2020-08-25 | construction and execution of work
FINALISATION FOR MECHANICAL WORKS | 30d | 2020-08-11 | 2020-09-09
FINALISATION FOR PIPING WORKS | 30d | 2020-08-21 | 2020-09-19
FINALISATION FOR ELECTRICAL WORKS | 30d | 2020-09-05 | 2020-10-04
FINALISATION FOR INSTRUMENTATION WORKS | 30d | 2020-09-15 | 2020-10-14
MOBILISATION OF SITE TEAMS | 259d | 2020-11-11 | 2021-07-27
MOBILISATION FOR CIVIL WORKS | 6d | 2020-11-11 | 2020-11-16
MOBILISATION FOR MECHANICAL WORKS | 20d | 2021-03-28 | 2021-04-16
MOBILISATION FOR PIPING WORKS WORKS | 7d | 2021-04-10 | 2021-04-16
MOBILISATION FOR ELECTRICAL WORKS | 7d | 2021-07-14 | 2021-07-20
MOBILISATION FOR INSTRUMENTATION WORKS | 7d | 2021-07-21 | 2021-07-27
BASIC ENGINEERING PACKAGE | 386d | 2020-05-19 | 2021-06-08 | construction and execution of work | Process design calculations |  | Document
PROCESS DESIGN DOCUMENT (BEP TECHNICAL PROPOSAL) | 386d | 2020-05-19 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
HYDRAULIC FLOW DIAGRAM | 386d | 2020-05-19 | 2021-06-08 | construction and execution of work | Hydrolic flow diagram |  | document
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
SITE LAYOUT | 386d | 2020-05-19 | 2021-06-08 | Civil GA Drawings and Structural Design & Drawings
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
P&I DIAGRAM | 317d | 2020-07-27 | 2021-06-08 | Process and Instrumentation Diagram (P&ID) |  |  | document
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-07-27 | 2020-08-04
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-08-05 | 2020-08-11
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-08-12 | 2020-08-18
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-08-19 | 2020-08-25
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
PIPING & VALVES SCHEDULE | 287d | 2020-08-26 | 2021-06-08 | ???? |  |  | document
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-08-26 | 2020-09-04
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-09-05 | 2020-09-11
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-12 | 2020-09-18
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-09-19 | 2020-09-25
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
ELECTRICAL LOAD LIST | 266d | 2020-09-16 | 2021-06-08 | 15) Electrical General Arrangement Drawings | GA drawings and details |  | document
PLANT OPERATION & CONTROL PHILOSOPHY | 266d | 2020-09-16 | 2021-06-08 | construction and execution of work | Design basis report |  | document
VENDOR CREDENTIALS | 180d | 2020-05-29 | 2020-11-24 | General Documents | Credentials and details |  | document
SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF CEMENT/ STEEL/ AGGREGATES/ OTHER CIVIL ITEMS ETC. AS APPLICABLE | 90d | 2020-05-29 | 2020-08-26
SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF MECHANICAL/ ELECTRICAL/ INSTRUMENTATION ITEMS ETC. AS APPLICABLE | 180d | 2020-05-29 | 2020-11-24
DETAILED ENGINEERING, PROCUREMENT, CONSTRUCTION & ERECTION - UNIT WISE | 374d | 2020-07-27 | 2021-08-04
CIVIL DESIGN BASIS REPORT | 317d | 2020-07-27 | 2021-06-08 | construction and execution of work | Design basis report |  | document
TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
MECHANICAL COARSE SCREEN & BELT CONVEYOR | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
SUBMERSIBLE PUMPS & ACCESSORIES | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA drawings and details |  | documants
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings |  | documents
CIVIL WORKS FOR TSPS & ALLIED UNITS | 258d | 2020-11-11 | 2021-07-26 | Construction and execution of works | Contructions program
COMPLETION OF EXCAVATION | 15d | 2020-11-11 | 2020-11-25
COMPLETION OF PCC | 12d | 2020-11-26 | 2020-12-07
COMPLETION OF RAFT | 30d | 2020-12-08 | 2021-01-06
COMPLETION OF 50% SIDE WALL | 75d | 2020-12-23 | 2021-03-07
COMPLETION 100% SIDE WALL | 65d | 2021-02-21 | 2021-04-26
COMPLETION OF PLINTH LEVEL SLAB | 25d | 2021-04-17 | 2021-05-11
COMPLETION OF COLUMN/BEAM UPTO TOP SLAB | 15d | 2021-05-07 | 2021-05-21
COMPLETION OF TOP SLAB | 28d | 2021-05-12 | 2021-06-08
COMPLETION OF BLOCK MASONRY | 20d | 2021-06-09 | 2021-06-28
COMPLETION OF HYDRO TEST | 28d | 2021-06-29 | 2021-07-26
COMPLETION OF WATER PROOFING | 20d | 2021-06-22 | 2021-07-11
COMPLETION OF FINISHING WORKS | 25d | 2021-07-02 | 2021-07-26
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
MECHANICAL FINE SCREEN & BELT CONVEYOR | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 | Construction and execution of works | Contructions program
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 | Construction and execution of works | Contructions program
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27 | Construction and execution of works | Contructions program
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13 | Construction and execution of works | Contructions program
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20 | Construction and execution of works | Contructions program
MECHANICAL GRIT REMOVAL DETRITOR MECHANISM | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 | Construction and execution of works | Contructions program
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA drawings and details |  | documants
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings |  | documents
CIVIL WORKS FOR STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER | 124d | 2021-04-01 | 2021-08-02 | Construction and execution of works | Contructions program
COMPLETION OF EXCAVATION | 7d | 2021-04-01 | 2021-04-07 | Construction and execution of works | Contructions program
COMPLETION OF PCC | 12d | 2021-04-08 | 2021-04-19 | Construction and execution of works | Contructions program
COMPLETION OF RAFT/COLUMNS | 25d | 2021-04-20 | 2021-05-14 | Construction and execution of works | Contructions program
COMPLETION OF 50% SIDE WALL & BASE SLABS | 60d | 2021-05-05 | 2021-07-03 | Construction and execution of works | Contructions program
COMPLETION 100% SIDE WALL | 45d | 2021-06-19 | 2021-08-02 | Construction and execution of works | Contructions program
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Construction and execution of works | Contructions program
COMPLETION OF FINISHING WORKS | 30d | 2021-06-28 | 2021-07-27 | Construction and execution of works | Contructions program
ERECTION | 110d | 2021-04-17 | 2021-08-04 | Construction and execution of works | Contructions program
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Construction and execution of works | Contructions program
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Construction and execution of works | Contructions program
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04 | Construction and execution of works | Contructions program
SEQUENTIAL BATCH REACTORS | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
DECANTERS | 233d | 2020-07-27 | 2021-03-16
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | Mechanical technical data sheets and drawings | Data sheets |  | documants
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-08 | 2020-10-12 | Construction and execution of works | Contructions program
MANUFACTURING | 120d | 2020-10-13 | 2021-02-09 | Construction and execution of works | Contructions program
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-10 | 2021-02-23 | Construction and execution of works | Contructions program
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-24 | 2021-03-09 | Construction and execution of works | Contructions program
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-10 | 2021-03-16 | Construction and execution of works | Contructions program
DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
PUMPING MACHINERY | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
CIVIL WORKS FOR SEQUENTIAL BATCH REACTORS | 237d | 2020-12-08 | 2021-08-01
COMPLETION OF EXCAVATION | 10d | 2020-12-08 | 2020-12-17
COMPLETION OF PCC | 12d | 2020-12-18 | 2020-12-29
COMPLETION OF RAFT | 30d | 2020-12-30 | 2021-01-28
COMPLETION OF 50% SIDE WALL | 80d | 2021-01-09 | 2021-03-29
COMPLETION 100% SIDE WALL | 110d | 2021-03-10 | 2021-06-27
COMPLETION OF HYDRO TEST | 30d | 2021-06-28 | 2021-07-27
COMPLETION OF FINISHING WORKS | 35d | 2021-06-28 | 2021-08-01
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DEEP BED MEDIA FILTERS | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
AIR SCOUR BLOWERS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
UNDERDRAIN COMPONENTS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | Data sheets
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR DEEP BED MEDIA FILTERS | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-01-29 | 2021-02-04
COMPLETION OF PCC | 10d | 2021-02-05 | 2021-02-14
COMPLETION OF RAFT | 30d | 2021-02-15 | 2021-03-16
COMPLETION OF 50% SIDE WALL | 30d | 2021-03-02 | 2021-03-31
COMPLETION 100% SIDE WALL | 45d | 2021-03-17 | 2021-04-30
COMPLETION OF TROUGHS & ALLIED CHANNELS | 28d | 2021-03-24 | 2021-04-20
COMPLETION OF TOP SLAB | 28d | 2021-04-21 | 2021-05-18
COMPLETION OF HYDRO TEST | 28d | 2021-05-19 | 2021-06-15
COMPLETION OF BLOCK MASONRY FOR MACHINE ROOM | 25d | 2021-05-19 | 2021-06-12
COMPLETION OF WATER PROOFING | 21d | 2021-06-13 | 2021-07-03
COMPLETION OF FINISHING WORKS | 30d | 2021-07-04 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
CHLORINE CONTACT TANK | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PLANT SERVICE WATER PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | Data sheets
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR CHLORINE CONTACT TANK | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
INTERMEDIATE SUMP & PLANT DRAIN DRAIN SUMP | 374d | 2020-07-27 | 2021-08-04 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
FILTER FEED PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
PLANT DRAIN PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA Drawings
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR INTERMEDIATE SUMP & PDS | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
THICKENER FEED SUMP (SURPLUS SLUDGE SUMP) | 374d | 2020-07-27 | 2021-08-04 | Mechanical technical data sheets and drawings | Data sheets |  | documants
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
THICKENER FEED PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
AIR BLOWERS/MIXERS FOR SLUDGE AGITATION | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA Drawings and design
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR THICKENER FEED SUMP | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
SLUDGE THICKENER | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
THICKENER MECHANISM/MACHINERY | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
POLY-ELECTROLYTE DOSING UNITS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA Drawings
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR SLUDGE THICKENER | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
CENTRIFUGE FEED PUMPS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA Drawings
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR THICK SLUDGE SUMP | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
CENTRIFUGE BUILDING & CENTRATE SUMP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
SLUDGE DEWATERING CENTRIFUGE MACHINERY | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
CENTRATE TRANSFER PUMPS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA Drawings
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR CENTRIFUGE BUILDING & CENTRATE SUMP | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 30d | 2021-02-18 | 2021-03-19
COMPLETION OF 50% SIDE WALL | 48d | 2021-03-05 | 2021-04-21
COMPLETION OF 100% SIDE WALL | 45d | 2021-04-07 | 2021-05-21
COMPLETION OF RCC WORK UPTO PLINTH LEVEL FOR CENTRIFUGE BUILDING | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
COMPLETION OF HYDRO TEST OF CENTRATE SUMP | 28d | 2021-05-22 | 2021-06-18
COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DRIED SLUDGE STORAGE SHED | 301d | 2020-09-30 | 2021-07-27
CIVIL DESIGN DRAWINGS | 252d | 2020-09-30 | 2021-06-08 | civil drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR DRIED SLUDGE STORAGE SHED | 170d | 2021-02-08 | 2021-07-27
COMPLETION OF EXCAVATION | 7d | 2021-02-08 | 2021-02-14
COMPLETION OF PCC | 12d | 2021-02-15 | 2021-02-26
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 28d | 2021-05-05 | 2021-06-01
COMPLETION OF WORK UPTO ROOF SHED | 28d | 2021-05-05 | 2021-06-01
COMPLETION OF TOP ROOF | 28d | 2021-06-02 | 2021-06-29
COMPLETION OF FINISHING WORKS | 28d | 2021-06-30 | 2021-07-27
CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | GA Drawings
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | civik drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR CHLORINATION ROOM & CHEMICAL ROOM | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 12d | 2021-01-29 | 2021-02-09
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
AIR BLOWER ROOM (PROCESS) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
PROCESS AIR BLOWERS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MOTORS FOR AIR BLOWERS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | Mechanical technical data sheets and drawings | Data sheets
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 | civil drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR AIR BLOWER ROOM | 154d | 2021-03-02 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-03-02 | 2021-03-08
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 21d | 2021-03-09 | 2021-03-29
COMPLETION OF GRADE SLAB/PCC | 28d | 2021-03-30 | 2021-04-26
COMPLETION OF RCC UPTO TOP SLAB | 56d | 2021-03-30 | 2021-05-24
COMPLETION OF TOP SLAB | 28d | 2021-05-25 | 2021-06-21
COMPLETION OF BLOCK MASONRY | 21d | 2021-06-22 | 2021-07-12
COMPLETION OF FINISHING WORKS | 21d | 2021-07-13 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 244d | 2020-07-27 | 2021-03-27
LAB EQUIPMENT | 244d | 2020-07-27 | 2021-03-27 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 21d | 2020-07-27 | 2020-08-16
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-19 | 2020-10-23
MANUFACTURING | 120d | 2020-10-24 | 2021-02-20
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-21 | 2021-03-06
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-03-07 | 2021-03-20
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-21 | 2021-03-27
UPS | 237d | 2020-07-27 | 2021-03-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
CIVIL DESIGN DRAWINGS | 279d | 2020-09-03 | 2021-06-08 | civil drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR ADMIN BUILDING, PLC ROOM, LAB & WORKSHOP | 228d | 2020-12-18 | 2021-08-02
COMPLETION OF EXCAVATION | 6d | 2020-12-18 | 2020-12-23
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2020-12-24 | 2021-01-20
COMPLETION OF GRADE SLAB/PCC | 15d | 2021-01-21 | 2021-02-04
COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-01-21 | 2021-02-19
COMPLETION OF GF SLAB | 30d | 2021-02-20 | 2021-03-21
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-03-22 | 2021-04-11
COMPLETION OF TOP SLAB | 28d | 2021-04-12 | 2021-05-09
COMPLETION OF BLOCK MASONRY | 25d | 2021-05-10 | 2021-06-03
COMPLETION OF WATERPROOFING | 28d | 2021-06-04 | 2021-07-01
COMPLETION OF FINISHING WORKS | 60d | 2021-06-04 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04 |  |  |  |  | ca drawings strucural designs and drawings
HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM | 333d | 2020-09-06 | 2021-08-04 | Electrical design and drawings | GA drawings |  |  | ga drawings and details
ELECTRICAL DESIGN DRAWINGS | 85d | 2020-09-06 | 2020-11-29 |  |  |  |  | technical data sheets
CIVIL DESIGN DRAWINGS | 221d | 2020-11-30 | 2021-07-08 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM | 195d | 2021-01-11 | 2021-07-24
COMPLETION OF EXCAVATION | 7d | 2021-01-11 | 2021-01-17
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-18 | 2021-02-14
COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-15 | 2021-03-07
COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-02-15 | 2021-03-16
COMPLETION OF GF SLAB | 28d | 2021-03-17 | 2021-04-13
COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-04-14 | 2021-05-11
COMPLETION OF TOP SLAB | 21d | 2021-05-12 | 2021-06-01
COMPLETION OF BLOCK MASONRY | 25d | 2021-06-02 | 2021-06-26
COMPLETION OF WATERPROOFING | 21d | 2021-06-27 | 2021-07-17
COMPLETION OF FINISHING WORKS | 28d | 2021-06-27 | 2021-07-24
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DG ROOM | 333d | 2020-09-06 | 2021-08-04
ELECTRICAL DESIGN DRAWINGS | 85d | 2020-09-06 | 2020-11-29
PREPARATION & SUBMISSION TO CLIENT | 24d | 2020-10-17 | 2020-11-09
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-10 | 2020-11-23
RE-SUBMISSION FOR CODE-B APPROVAL | 1d | 2020-11-24 | 2020-11-24
ENGINEER'S REVIEW AND CODE-B APPROVAL | 5d | 2020-11-25 | 2020-11-29
RE-SUBMISSION FOR CODE-A APPROVAL | 2d | 2020-09-06 | 2020-09-07
ENGINEER'S REVIEW AND CODE-A APPROVAL | 3d | 2020-09-08 | 2020-09-10
CIVIL DESIGN DRAWINGS | 221d | 2020-11-30 | 2021-07-08 | ca drawings strucural designs and drawings | GA Drawings
CIVIL WORKS FOR DG ROOM | 138d | 2021-01-11 | 2021-05-28
COMPLETION OF EXCAVATION | 12d | 2021-01-11 | 2021-01-22
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-23 | 2021-02-19
COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-20 | 2021-03-12
COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-02-20 | 2021-03-19
COMPLETION OF TOP SLAB | 21d | 2021-03-20 | 2021-04-09
COMPLETION OF BLOCK MASONRY | 21d | 2021-04-10 | 2021-04-30
COMPLETION OF WATERPROOFING | 21d | 2021-05-01 | 2021-05-21
COMPLETION OF FINISHING WORKS | 28d | 2021-05-01 | 2021-05-28
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
GUARD ROOM | 334d | 2020-09-03 | 2021-08-02 | civil drawings strucural designs and drawings | GA Drawings
CIVIL DESIGN DRAWINGS | 279d | 2020-09-03 | 2021-06-08
CIVIL WORKS FOR GUARD ROOM | 88d | 2021-05-07 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-05-07 | 2021-05-13
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 14d | 2021-05-14 | 2021-05-27
COMPLETION OF GRADE SLAB/PCC | 14d | 2021-05-28 | 2021-06-10
COMPLETION OF RCC UPTO TOP SLAB | 15d | 2021-05-28 | 2021-06-11
COMPLETION OF TOP SLAB | 21d | 2021-06-12 | 2021-07-02
COMPLETION OF BLOCK MASONRY | 10d | 2021-07-03 | 2021-07-12
COMPLETION OF WATERPROOFING | 14d | 2021-07-13 | 2021-07-26
COMPLETION OF FINISHING WORKS | 7d | 2021-07-27 | 2021-08-02
ROAD, DRAINS, & LANDSCAPING WORKS | 206d | 2021-01-11 | 2021-08-04
CIVIL DESIGN DRAWINGS | 194d | 2021-01-11 | 2021-07-23 | civil drawings strucural designs and drawings | GA Drawings
CIVIL WORKS - ROADS - 100% COMPLETION | 45d | 2021-06-21 | 2021-08-04
CIVIL WORKS - DRAINS - 100% COMPLETION | 60d | 2021-06-06 | 2021-08-04
COMPOUND WALL(AS SUITABLE/APPLICABLE) | 60d | 2021-06-06 | 2021-08-04
PLANTATION WORKS - LANDSCAPING - 100% COMPLETION INCL. SOIL FILL UP AND DRESSING | 90d | 2021-05-07 | 2021-08-04
OTHER PLANT MECHANICAL, PIPING AND E&I WORKS (VALVES, PIPES, FITTINGS & OTHER COMMON E&I ITEMS) | 313d | 2020-09-26 | 2021-08-04
PROCUREMENT | 267d | 2020-09-26 | 2021-06-19
GATE VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
KNIFE GATE VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
NON RETURN VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
BALL VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
BUTTERFLY VALVES | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
DI PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
SS PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
MS PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
EOT/HOT HOIST ARRANGEMENTS | 237d | 2020-10-26 | 2021-06-19 | Mechanical technical data sheets and drawings | Data sheets |  | documants
VENDOR FINALISATION & ORDER | 14d | 2020-10-26 | 2020-11-08
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-11 | 2021-01-15
MANUFACTURING | 120d | 2021-01-16 | 2021-05-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-16 | 2021-05-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-30 | 2021-06-12
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-13 | 2021-06-19
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT & FITTINGS | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQUIPMENT & FIXTURES | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
ELECTRICAL WORKS | 292d | 2020-10-17 | 2021-08-04
ENGINEERING & DOCUMENTATION - ELECTRICAL | 265d | 2020-10-17 | 2021-07-08
TRANSFORMER SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
DG SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
LT CAPACITOR SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
SINGLE LINE DIAGRAM | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
ELECTRICAL HT SUBSTATION LAYOUT | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
EARTHING GRID DESIGN & LAYOUT | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
LIGHTING DESIGN & LAYOUT | 216d | 2020-12-05 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
POWER & CONTROL CABLE SCHEDULE | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
CABLE ROUTING DRAWING | 223d | 2020-11-28 | 2021-07-08 | Electrical general arrangements and drawings | GA drawings and details |  | Document
PROCUREMENT - ELECTRICAL | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
TRANSFORMER | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
HT PANELS | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
LT PANELS | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
DISTRIBUTION BOXES | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
HT & LT CABLES & TRAYS (AS APPLICABLE) | 237d | 2020-10-17 | 2021-06-10 | Electrical general arrangements and drawings | Data sheets |  | Document
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30 | Electrical general arrangements and drawings | GA Drawings and details |  | Document
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
ERECTION | 60d | 2021-06-06 | 2021-08-04
ERECTION OF ELECTRICAL EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST (DRY/WET FOR ELECTRICAL EQUIPMENT AS APPLICABLE) | 15d | 2021-07-21 | 2021-08-04
INSTRUMENTATION CONTROL & AUTOMATION WORKS | 285d | 2020-10-24 | 2021-08-04 | Instrumentation, control and automation documents | GA drawings and details |  | document
ENGINEERING & DOCUMENTATION - ICA | 258d | 2020-10-24 | 2021-07-08
FUNCTIONAL DESIGN SPECIFICATION | 228d | 2020-10-24 | 2021-06-08
INSTRUMENT SCHEDULE | 216d | 2020-12-05 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
INSTRUMENT DATASHEETS | 216d | 2020-12-05 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
I/O SCHEDULE | 211d | 2020-12-10 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
INSTRUMENT LOCATION LAYOUT WITH CABLE ROUTING | 209d | 2020-12-12 | 2021-07-08 | Instrumentation, control and automation documents | GA drawings and details |  | document
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-26 | 2021-01-08
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-16 | 2021-01-22
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
PROCUREMENT - ICA | 262d | 2020-10-24 | 2021-07-12 | Instrumentation, control and automation documents | Data sheets |  | document
INSTRUMENTATION (AS PER APPROVED LIST) | 237d | 2020-10-24 | 2021-06-17
VENDOR FINALISATION & ORDER | 14d | 2020-10-24 | 2020-11-06
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-09 | 2021-01-13
MANUFACTURING | 120d | 2021-01-14 | 2021-05-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-14 | 2021-05-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-28 | 2021-06-10
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-11 | 2021-06-17
INSTRUMENTATION CABLES - POWER & CONTROL CABLES | 237d | 2020-10-24 | 2021-06-17 | Instrumentation, control and automation documents | Data sheets |  | document
VENDOR FINALISATION & ORDER | 14d | 2020-10-24 | 2020-11-06
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-09 | 2021-01-13
MANUFACTURING | 120d | 2021-01-14 | 2021-05-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-14 | 2021-05-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-28 | 2021-06-10
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-11 | 2021-06-17
INSTRUMENTATION CABLES TRAY & SUPPORTS | 177d | 2021-01-09 | 2021-07-04 | Instrumentation, control and automation documents | Data sheets |  | document
VENDOR FINALISATION & ORDER | 14d | 2021-01-09 | 2021-01-22
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-03-27 | 2021-03-31
MANUFACTURING | 60d | 2021-04-01 | 2021-05-30
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-31 | 2021-06-13
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-06-14 | 2021-06-27
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-28 | 2021-07-04
PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) | 185d | 2021-01-09 | 2021-07-12 | Instrumentation, control and automation documents | Data sheets |  | document
VENDOR FINALISATION & ORDER | 14d | 2021-01-09 | 2021-01-22
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-03-20 | 2021-03-24
MANUFACTURING | 75d | 2021-03-25 | 2021-06-07
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-06-08 | 2021-06-21
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-06-22 | 2021-07-05
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-07-06 | 2021-07-12
ERECTION | 60d | 2021-06-06 | 2021-08-04
ERECTION OF ICA EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST (DRY/WET FOR ICA EQUIPMENT AS APPLICABLE) | 15d | 2021-07-21 | 2021-08-04
COMMISSIONING | 91d | 2021-08-05 | 2021-11-03
PREPARATION & SUBMISSION OF O&M MANUALS | 50d | 2021-09-14 | 2021-11-02
PREPARATION & SUBMISSION OF AS BUILT DRAWINGS | 50d | 2021-09-14 | 2021-11-02
STABILITY TEST RUN ON COMPLETION OF WORKS | 30d | 2021-08-05 | 2021-09-03
PERFORMANCE RUN & COMMISSIONING | 60d | 2021-09-04 | 2021-11-02
TRAINING OF BWSSB STAFF | 10d | 2021-10-24 | 2021-11-02
HANDING OVER OF PLANT TO CLIENT | 1d | 2021-11-03 | 2021-11-03
ISSUE OF TAKING OVER CERTIFICATE BY CLIENT | ~0 | 2021-11-03 | 2021-11-03
MILESTONE: START DATE | ~0 | 2020-05-04 | 2020-05-04
OVERALL PROJECT TIMELINE | 549d | 2020-05-04 | 2021-11-03
MILESTONE: END DATE | ~0 | 2021-11-03 | 2021-11-03