## R1-7MLD Puttenahalli STP _ Rela
Task Name | Duration | Start Date | End Date
7 MLD SBR TECHNOLOGY STP AT PUTTENAHALLI LAKE, YELAHANKA - OVERALL PROJECT SCHEDULE | 549d | 2020-05-04 | 2021-11-03 | 1) Feasibility Report |  |  |  |  | Pre construction Phase
PROJECT INITIATION & PRELIMINARY MOBILISATION | 25d | 2020-05-04 | 2020-05-28 |  | Correspondence
MILESTONE: NOTICE TO COMMENCE WORK, RECEIPT OF WO & OFFICIAL PROJECT START DATE | ~0 | 2020-05-04 | 2020-05-04 |  | Inward
PROJECT KICK OFF MEETING | 1d | 2020-05-12 | 2020-05-12 |  | Outward
MILESTONE: COMPLETION OF SIGNING OF CONTRACT DOCS | ~0 | 2020-05-18 | 2020-05-18 | 2) Detailed Project Report (DPR) |  |  |  |  | Pre construction Phase
SUBMISSION OF ORGANISATION CHART | 1d | 2020-05-26 | 2020-05-26 |  | Correspondence
MOBILISATION OF CONTRACTOR'S REPRESENTATIVE | 1d | 2020-05-27 | 2020-05-27 |  | Inward
MOBILISATION OF PROJECT MANAGER | 1d | 2020-05-28 | 2020-05-28 |  | Outward
HANDING OVER OF SITE BY CLIENT | 1d | 2020-05-20 | 2020-05-20 | 3) Consultancy Agreement |  |  |  |  | Pre construction Phase
SOIL & SITE INVESTIGATION/SURVEY | 80d | 2020-05-13 | 2020-07-31 |  | Correspondence
MOBILISATION & DEMOBILISATION OF TOPOGRAPHIC SURVEY TEAM | 69d | 2020-05-13 | 2020-07-20 |  | Inward
APPROVAL OF TOPOGRAPHIC SURVEY | 60d | 2020-06-02 | 2020-07-31 |  | Outward
MOBILISATION & DEMOBILISATION OF GEO-TECHNICAL SURVEY TEAM | 60d | 2020-05-27 | 2020-07-25 | 4) Inception Report |  |  |  |  | Pre construction Phase
APPROVAL OF GEO-TECHNICAL REPORT | 60d | 2020-06-02 | 2020-07-31 |  | Correspondence
SITE ESTABLISHMENT | 95d | 2020-05-29 | 2020-08-31 |  | Inward
ESTABLISHMENT OF SITE OFFICE | 24d | 2020-05-29 | 2020-06-21 |  | Outward
EST. OF CONSTRUCTION - POWER & WATER | 60d | 2020-06-15 | 2020-08-13 | 5) Detailed Design Report (DDR) |  |  |  |  | Pre construction Phase
EST. OF LABORATORY | 60d | 2020-07-03 | 2020-08-31 |  | Draft DDR {PDF,Doc,Excel}
EST. OF STORAGE YARD | 15d | 2020-08-17 | 2020-08-31 |  | A) Report
EST. OF OTHER TEMPORARY STRUCTURES (As Req.) | 60d | 2020-07-03 | 2020-08-31 |  | B) Design
DEMOLITION ACTIVITIES | 68d | 2020-05-25 | 2020-07-31 |  | C) Drawings
STATUTORY CLEARANCE FOR DEMOLITION OF EXISTING STRUCTURES BY EMPLOYER | 40d | 2020-05-25 | 2020-07-03 |  | D) Models
DISMANTLING OF EQUIPMENT, PIPES, FITTINGS ETC. | 7d | 2020-05-29 | 2020-06-04 |  | E) Estimates
DEMOLITION OF APPROVED EXISTING STRUCTURES | 31d | 2020-07-01 | 2020-07-31 |  | F) Scanned Approvals
APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL) | 80d | 2020-07-27 | 2020-10-14 |  | G) Supporting Files
FINALISATION FOR CIVIL WORKS | 30d | 2020-07-27 | 2020-08-25 |  | Final (DDR) {PDF,Doc,Excel}
FINALISATION FOR MECHANICAL WORKS | 30d | 2020-08-11 | 2020-09-09 |  | A) Report
FINALISATION FOR PIPING WORKS | 30d | 2020-08-21 | 2020-09-19 |  | B) Design
FINALISATION FOR ELECTRICAL WORKS | 30d | 2020-09-05 | 2020-10-04 |  | C) Drawings
FINALISATION FOR INSTRUMENTATION WORKS | 30d | 2020-09-15 | 2020-10-14 |  | D) Models
MOBILISATION OF SITE TEAMS | 259d | 2020-11-11 | 2021-07-27 |  | E) Estimates
MOBILISATION FOR CIVIL WORKS | 6d | 2020-11-11 | 2020-11-16 |  | F) Scanned Approvals
MOBILISATION FOR MECHANICAL WORKS | 20d | 2021-03-28 | 2021-04-16 |  | G) Supporting Files
MOBILISATION FOR PIPING WORKS WORKS | 7d | 2021-04-10 | 2021-04-16 |  | Correspondence
MOBILISATION FOR ELECTRICAL WORKS | 7d | 2021-07-14 | 2021-07-20 |  | Inward
MOBILISATION FOR INSTRUMENTATION WORKS | 7d | 2021-07-21 | 2021-07-27 |  | Outward
BASIC ENGINEERING PACKAGE | 386d | 2020-05-19 | 2021-06-08 | 6) Construction Cost Estimate (CCE) |  |  |  |  | Pre construction Phase
PROCESS DESIGN DOCUMENT (BEP TECHNICAL PROPOSAL) | 386d | 2020-05-19 | 2021-06-08 |  | A) Final (CCE) {PDF,Doc,Excel)
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27 |  | B) Support Files
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21 |  | Correspondence
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16 |  | Inward
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26 |  | Outward
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 | 7) Bid Documents Preparation |  |  |  |  | Pre construction Phase
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Draft Bid Documents
HYDRAULIC FLOW DIAGRAM | 386d | 2020-05-19 | 2021-06-08 |  | Volume 1: Bidding
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27 |  | Part 1
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21 |  | Part 2
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16 |  | Volume 2:Technical
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26 |  | Technical List Parts Specifications
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Technical Schedule
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Geo Technical Reviews
SITE LAYOUT | 386d | 2020-05-19 | 2021-06-08 |  | Volume 3:Price Bidding
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-05-19 | 2020-05-27 |  | Documents Related to Pricing
ENGINEER'S COMMENTS ON 1st SUBMISSION | 25d | 2020-05-28 | 2020-06-21 |  | Volume 4:Drawings
RESUBMISSION FOR CODE-B APPROVAL | 25d | 2020-06-22 | 2020-07-16 |  | Documents Related to Drawings
ENGINEER'S REVIEW & CODE-B APPROVAL | 10d | 2020-07-17 | 2020-07-26 |  | Final Bid Documents
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Final Tender Files {PDF,Doc,Excel}
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Correspondence
P&I DIAGRAM | 317d | 2020-07-27 | 2021-06-08 |  | Inward
PREPARATION & SUBMISSION TO CLIENT | 9d | 2020-07-27 | 2020-08-04 |  | Outward
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-08-05 | 2020-08-11 | 8) Tender Documents |  |  |  |  | Pre construction Phase
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-08-12 | 2020-08-18 | Bidders' Queries & Response
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-08-19 | 2020-08-25 |  | Final Bidders' Queries & Response {PDF,Doc,Excel}
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Support Files
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 | Conformed Documents
PIPING & VALVES SCHEDULE | 287d | 2020-08-26 | 2021-06-08 |  | Conformed Document Files
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-08-26 | 2020-09-04 |  | Completed Technical Schedule
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-09-05 | 2020-09-11 |  | Support Files
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-12 | 2020-09-18 | Addenda
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-09-19 | 2020-09-25 |  | Addendum 1
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Addendum 2
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Addendum 3
ELECTRICAL LOAD LIST | 266d | 2020-09-16 | 2021-06-08 |  | Final Addenda Files {PDF,Doc,Excel}
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-09-16 | 2020-09-25 |  | Support Files
ENGINEER'S COMMENTS ON 1st SUBMISSION | 7d | 2020-09-26 | 2020-10-02 |  | Correspondence
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-03 | 2020-10-09 |  | Inward
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-10-10 | 2020-10-16 |  | Outward
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 | 9) Tender Evaluation |  |  |  |  | Pre construction Phase
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 | Qualification Criteria Evaluation
PLANT OPERATION & CONTROL PHILOSOPHY | 266d | 2020-09-16 | 2021-06-08 |  | Final Evaluation Files {PDF,Doc,Excel}
PREPARATION & SUBMISSION TO CLIENT | 10d | 2020-09-16 | 2020-09-25 |  | Support Files
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-26 | 2020-10-09 | Technical Bid Evaluation
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-10 | 2020-10-16 |  | Final Technical files {PDF,Doc,Excel}
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-10-17 | 2020-10-23 |  | Support Files
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 | Price Bid Evaluation
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Final Pricing Files {PDF,Doc,Excel}
VENDOR CREDENTIALS | 180d | 2020-05-29 | 2020-11-24 |  | Support Files
SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF CEMENT/ STEEL/ AGGREGATES/ OTHER CIVIL ITEMS ETC. AS APPLICABLE | 90d | 2020-05-29 | 2020-08-26 | Letter of Acceptance (LOA)
SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF MECHANICAL/ ELECTRICAL/ INSTRUMENTATION ITEMS ETC. AS APPLICABLE | 180d | 2020-05-29 | 2020-11-24 |  | Draft LOA {Doc,Excel}
DETAILED ENGINEERING, PROCUREMENT, CONSTRUCTION & ERECTION - UNIT WISE | 374d | 2020-07-27 | 2021-08-04 |  | Support Files
CIVIL DESIGN BASIS REPORT | 317d | 2020-07-27 | 2021-06-08 |  | Final LOA {PDF,Doc,Excel}
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-07-27 | 2020-08-09 |  | Support Files
ENGINEER'S COMMENTS ON 1st SUBMISSION | 10d | 2020-08-10 | 2020-08-19 | Signing of Contract Agreement
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-08-20 | 2020-08-26 |  | Draft Contract Agreement {Doc,Excel}
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-08-27 | 2020-09-02 |  | Support Files
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Final Contract Agreement {PDF,Doc,Excel}
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Support Files
TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.) | 374d | 2020-07-27 | 2021-08-04 | Contract Document
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20 |  | Concluded/Final Contract Document {PDF}
MECHANICAL COARSE SCREEN & BELT CONVEYOR | 237d | 2020-07-27 | 2021-03-20 |  | Correspondence
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09 |  | Inward
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 |  | Outward
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13 | 10) Letter of Commencement (LOC) |  |  |  |  | Construction Phase
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27 |  | Draft LOC {Doc,Excel}
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11 |  | Support Files
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 |  | Final LOC {PDF,Doc,Excel}
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 |  | Support Files
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27 |  | Correspondence
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13 |  | Inward
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20 |  | Outward
SUBMERSIBLE PUMPS & ACCESSORIES | 237d | 2020-07-27 | 2021-03-20 | 11) Construction / Execution of Work
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09 |  | Handing Over of Site to the Contractor |  |  |  | Kick off meeting and site handing over to start work go hand in hand. Please retain handing over of site it self
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 |  | Permission to start work |  |  |  | Letter of Commencement (LOC)
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13 |  | Organisation Chart |  |  |  | Organization chart
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27 |  | Deployment Schedule |  |  |  | Mobilization of Project manager, Contractor's representative, mobilization of site team
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11 |  | Topographical Survey |  |  |  | Establishment of site office, temporary water and power supply, laboratory shall be included as separate activity as 'Temporary site establishment'
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 |  | Geo-Technical Investigation
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 |  | Existing structures Demolition Scheme |  |  |  | Demolition activities
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27 |  | Process Design Calculation |  |  |  | Basic Engineering package
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13 |  | Process Flow Diagram
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20 |  | Hydraulic Flow Calculation |  |  |  | Hydraulic flow diagram
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 |  | Hydraulic Flow Diagram
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01 |  | Mass Flow Diagram |  |  |  | Basic Engineering package(BEP) (mass balance is part of BEP)
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15 |  | Construction Programme |  |  |  | Please retain | Please include 'Layout plan'
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22 |  | Billing Breakup & Cash Flow Chart |  |  |  | Please retain
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29 |  | Design Basis Report |  |  |  | Civil Design basis report
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Construction Methodology |  |  |  | Please retain
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Health and Safety Manual |  |  |  | Please retain
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 |  | Environmental Management Plan |  |  |  | Please retain
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13 |  | Quality Assurance Plan |  |  |  | Please retain
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27 |  | Correspondence
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03 |  | Inward
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10 |  | Outward
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23 | 12) Process & Instruments Diagram (P&ID)
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11 |  | Correspondence
CIVIL WORKS FOR TSPS & ALLIED UNITS | 258d | 2020-11-11 | 2021-07-26 |  | Inward
COMPLETION OF EXCAVATION | 15d | 2020-11-11 | 2020-11-25 |  | Outward
COMPLETION OF PCC | 12d | 2020-11-26 | 2020-12-07 | 13) Civil GA Drawings and Structural Design & Drawings
COMPLETION OF RAFT | 30d | 2020-12-08 | 2021-01-06 |  | Correspondence |  |  |  | Appointment of contracting teams (internal/external), Mobilization of site teams need not be considered as an activity. It will be covered under deployment schedule
COMPLETION OF 50% SIDE WALL | 75d | 2020-12-23 | 2021-03-07 |  | Inward |  |  |  | vendor credentials row 89 comes under this categaory
COMPLETION 100% SIDE WALL | 65d | 2021-02-21 | 2021-04-26 |  | Outward
COMPLETION OF PLINTH LEVEL SLAB | 25d | 2021-04-17 | 2021-05-11 | 14) Mechanical: Technical Data Sheets / Drawings |  |  |  |  | Piping & valve schedule comes under this category
COMPLETION OF COLUMN/BEAM UPTO TOP SLAB | 15d | 2021-05-07 | 2021-05-21 |  | Correspondence |  |  |  | vendor credentials row 90 comes under this categaory
COMPLETION OF TOP SLAB | 28d | 2021-05-12 | 2021-06-08 |  | Inward |  |  |  | Equipments highlighted comes under this category
COMPLETION OF BLOCK MASONRY | 20d | 2021-06-09 | 2021-06-28 |  | Outward
COMPLETION OF HYDRO TEST | 28d | 2021-06-29 | 2021-07-26 | 15) Electrical General Arrangement Drawings |  |  |  |  | Electrical load comes under this category
COMPLETION OF WATER PROOFING | 20d | 2021-06-22 | 2021-07-11 |  | Transformer | Start | End
COMPLETION OF FINISHING WORKS | 25d | 2021-07-02 | 2021-07-26
ERECTION | 110d | 2021-04-17 | 2021-08-04 |  | Correspondence |  |  |  | vendor credentials row 90 comes under this categaory
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 |  | Inward |  |  |  | Equipments highlighted color comes under this category
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 |  | Outward
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04 | 16) Instrumentation,Control & Automation Documents |  |  |  |  | Plant operation and control philosophy comes under this category
STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20 |  | Correspondence |  |  |  | vendor credentials row 90 comes under this categaory
MECHANICAL FINE SCREEN & BELT CONVEYOR | 237d | 2020-07-27 | 2021-03-20 |  | Inward |  |  |  | Equipments/instruments highlighted comes under this category
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09 |  | Outward
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 | 17) Factory Acceptance Test(FAT) Document |  |  |  |  | Dispatch clearance document of all instruments/equipment (dates from inspection to Dispatch & receipt of material) will come under this category
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13 |  | Correspondence
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27 |  | Inward
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11 |  | Outward |  |  | 17a | Supply of plants and equipments at site
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 | 18) Site Acceptance Test(SAT) Document |  |  |  |  | Site acceptance test for mechanical, electrical & Instruments comes under this category
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 |  | Correspondence
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27 |  | Inward
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13 |  | Outward
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20 | 19) Pre-Commissioning Document |  |  |  |  | Commissioning and pre-commissioning document shall be combined
MECHANICAL GRIT REMOVAL DETRITOR MECHANISM | 237d | 2020-07-27 | 2021-03-20 |  | Correspondence
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09 |  | Inward
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16 |  | Outward
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13 | 20) Commissioning Philosophy Document
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27 |  | Correspondence
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11 |  | Inward
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16 |  | Outward
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13 | 21) As-Built Drawings
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27 |  | Correspondence
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13 |  | Inward
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20 |  | Outward
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08 | 22) Training Requirement
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01 |  | Correspondence
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15 |  | Inward
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22 |  | Outward
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29 | 23) O & M Manuals
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21 |  | Correspondence
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08 |  | Inward
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11 |  | Outward
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13 | 24) Handing Over Documentations
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27 |  | Correspondence
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03 |  | Inward
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10 |  | Outward
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23 | 25) Monthly Reports
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11 | 26) Management Reports
CIVIL WORKS FOR STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER | 124d | 2021-04-01 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-04-01 | 2021-04-07
COMPLETION OF PCC | 12d | 2021-04-08 | 2021-04-19
COMPLETION OF RAFT/COLUMNS | 25d | 2021-04-20 | 2021-05-14
COMPLETION OF 50% SIDE WALL & BASE SLABS | 60d | 2021-05-05 | 2021-07-03
COMPLETION 100% SIDE WALL | 45d | 2021-06-19 | 2021-08-02
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 30d | 2021-06-28 | 2021-07-27
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
SEQUENTIAL BATCH REACTORS | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
DECANTERS | 233d | 2020-07-27 | 2021-03-16
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 10d | 2020-09-14 | 2020-09-23
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-24 | 2020-10-07
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-08 | 2020-10-12
MANUFACTURING | 120d | 2020-10-13 | 2021-02-09
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-10 | 2021-02-23
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-24 | 2021-03-09
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-10 | 2021-03-16
DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
PUMPING MACHINERY | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR SEQUENTIAL BATCH REACTORS | 237d | 2020-12-08 | 2021-08-01
COMPLETION OF EXCAVATION | 10d | 2020-12-08 | 2020-12-17
COMPLETION OF PCC | 12d | 2020-12-18 | 2020-12-29
COMPLETION OF RAFT | 30d | 2020-12-30 | 2021-01-28
COMPLETION OF 50% SIDE WALL | 80d | 2021-01-09 | 2021-03-29
COMPLETION 100% SIDE WALL | 110d | 2021-03-10 | 2021-06-27
COMPLETION OF HYDRO TEST | 30d | 2021-06-28 | 2021-07-27
COMPLETION OF FINISHING WORKS | 35d | 2021-06-28 | 2021-08-01
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DEEP BED MEDIA FILTERS | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
AIR SCOUR BLOWERS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
UNDERDRAIN COMPONENTS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR DEEP BED MEDIA FILTERS | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-01-29 | 2021-02-04
COMPLETION OF PCC | 10d | 2021-02-05 | 2021-02-14
COMPLETION OF RAFT | 30d | 2021-02-15 | 2021-03-16
COMPLETION OF 50% SIDE WALL | 30d | 2021-03-02 | 2021-03-31
COMPLETION 100% SIDE WALL | 45d | 2021-03-17 | 2021-04-30
COMPLETION OF TROUGHS & ALLIED CHANNELS | 28d | 2021-03-24 | 2021-04-20
COMPLETION OF TOP SLAB | 28d | 2021-04-21 | 2021-05-18
COMPLETION OF HYDRO TEST | 28d | 2021-05-19 | 2021-06-15
COMPLETION OF BLOCK MASONRY FOR MACHINE ROOM | 25d | 2021-05-19 | 2021-06-12
COMPLETION OF WATER PROOFING | 21d | 2021-06-13 | 2021-07-03
COMPLETION OF FINISHING WORKS | 30d | 2021-07-04 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
CHLORINE CONTACT TANK | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
PLANT SERVICE WATER PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR CHLORINE CONTACT TANK | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
INTERMEDIATE SUMP & PLANT DRAIN DRAIN SUMP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
FILTER FEED PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
PLANT DRAIN PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR INTERMEDIATE SUMP & PDS | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
THICKENER FEED SUMP (SURPLUS SLUDGE SUMP) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
THICKENER FEED PUMPS INCL. MOTORS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
AIR BLOWERS/MIXERS FOR SLUDGE AGITATION | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR THICKENER FEED SUMP | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
SLUDGE THICKENER | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
THICKENER MECHANISM/MACHINERY | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
POLY-ELECTROLYTE DOSING UNITS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR SLUDGE THICKENER | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
CENTRIFUGE FEED PUMPS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR THICK SLUDGE SUMP | 178d | 2021-01-29 | 2021-07-25
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
CENTRIFUGE BUILDING & CENTRATE SUMP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
SLUDGE DEWATERING CENTRIFUGE MACHINERY | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
CENTRATE TRANSFER PUMPS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR CENTRIFUGE BUILDING & CENTRATE SUMP | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
COMPLETION OF RAFT | 30d | 2021-02-18 | 2021-03-19
COMPLETION OF 50% SIDE WALL | 48d | 2021-03-05 | 2021-04-21
COMPLETION OF 100% SIDE WALL | 45d | 2021-04-07 | 2021-05-21
COMPLETION OF RCC WORK UPTO PLINTH LEVEL FOR CENTRIFUGE BUILDING | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
COMPLETION OF HYDRO TEST OF CENTRATE SUMP | 28d | 2021-05-22 | 2021-06-18
COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DRIED SLUDGE STORAGE SHED | 301d | 2020-09-30 | 2021-07-27
CIVIL DESIGN DRAWINGS | 252d | 2020-09-30 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL WORKS FOR DRIED SLUDGE STORAGE SHED | 170d | 2021-02-08 | 2021-07-27
COMPLETION OF EXCAVATION | 7d | 2021-02-08 | 2021-02-14
COMPLETION OF PCC | 12d | 2021-02-15 | 2021-02-26
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 28d | 2021-05-05 | 2021-06-01
COMPLETION OF WORK UPTO ROOF SHED | 28d | 2021-05-05 | 2021-06-01
COMPLETION OF TOP ROOF | 28d | 2021-06-02 | 2021-06-29
COMPLETION OF FINISHING WORKS | 28d | 2021-06-30 | 2021-07-27
CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR CHLORINATION ROOM & CHEMICAL ROOM | 186d | 2021-01-29 | 2021-08-02
COMPLETION OF EXCAVATION | 12d | 2021-01-29 | 2021-02-09
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
AIR BLOWER ROOM (PROCESS) | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 237d | 2020-07-27 | 2021-03-20
PROCESS AIR BLOWERS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MOTORS FOR AIR BLOWERS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
MECHANICAL G.A. DRAWINGS | 287d | 2020-08-26 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 7d | 2020-08-26 | 2020-09-01
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-02 | 2020-09-15
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-09-16 | 2020-09-22
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-23 | 2020-09-29
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL DESIGN DRAWINGS | 285d | 2020-09-30 | 2021-07-11
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-09-30 | 2020-10-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-14 | 2020-10-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-28 | 2020-11-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-04 | 2020-11-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-09 | 2021-06-23
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-24 | 2021-07-11
CIVIL WORKS FOR AIR BLOWER ROOM | 154d | 2021-03-02 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-03-02 | 2021-03-08
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 21d | 2021-03-09 | 2021-03-29
COMPLETION OF GRADE SLAB/PCC | 28d | 2021-03-30 | 2021-04-26
COMPLETION OF RCC UPTO TOP SLAB | 56d | 2021-03-30 | 2021-05-24
COMPLETION OF TOP SLAB | 28d | 2021-05-25 | 2021-06-21
COMPLETION OF BLOCK MASONRY | 21d | 2021-06-22 | 2021-07-12
COMPLETION OF FINISHING WORKS | 21d | 2021-07-13 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP | 374d | 2020-07-27 | 2021-08-04
PROCUREMENT | 244d | 2020-07-27 | 2021-03-27
LAB EQUIPMENT | 244d | 2020-07-27 | 2021-03-27
VENDOR FINALISATION & ORDER | 21d | 2020-07-27 | 2020-08-16
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-17 | 2020-08-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-24 | 2020-09-20
RESUBMISSION | 14d | 2020-09-21 | 2020-10-04
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-10-05 | 2020-10-18
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-19 | 2020-10-23
MANUFACTURING | 120d | 2020-10-24 | 2021-02-20
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-21 | 2021-03-06
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-03-07 | 2021-03-20
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-21 | 2021-03-27
UPS | 237d | 2020-07-27 | 2021-03-20
VENDOR FINALISATION & ORDER | 14d | 2020-07-27 | 2020-08-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-08-10 | 2020-08-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-08-17 | 2020-09-13
RESUBMISSION | 14d | 2020-09-14 | 2020-09-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-09-28 | 2020-10-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-10-12 | 2020-10-16
MANUFACTURING | 120d | 2020-10-17 | 2021-02-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-02-14 | 2021-02-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-02-28 | 2021-03-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-03-14 | 2021-03-20
CIVIL DESIGN DRAWINGS | 279d | 2020-09-03 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 21d | 2020-09-03 | 2020-09-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-24 | 2020-10-07
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-08 | 2020-10-14
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-15 | 2020-10-21
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL WORKS FOR ADMIN BUILDING, PLC ROOM, LAB & WORKSHOP | 228d | 2020-12-18 | 2021-08-02
COMPLETION OF EXCAVATION | 6d | 2020-12-18 | 2020-12-23
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2020-12-24 | 2021-01-20
COMPLETION OF GRADE SLAB/PCC | 15d | 2021-01-21 | 2021-02-04
COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-01-21 | 2021-02-19
COMPLETION OF GF SLAB | 30d | 2021-02-20 | 2021-03-21
COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-03-22 | 2021-04-11
COMPLETION OF TOP SLAB | 28d | 2021-04-12 | 2021-05-09
COMPLETION OF BLOCK MASONRY | 25d | 2021-05-10 | 2021-06-03
COMPLETION OF WATERPROOFING | 28d | 2021-06-04 | 2021-07-01
COMPLETION OF FINISHING WORKS | 60d | 2021-06-04 | 2021-08-02
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM | 333d | 2020-09-06 | 2021-08-04
ELECTRICAL DESIGN DRAWINGS | 85d | 2020-09-06 | 2020-11-29
PREPARATION & SUBMISSION TO CLIENT | 24d | 2020-10-17 | 2020-11-09
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-10 | 2020-11-23
RE-SUBMISSION FOR CODE-B APPROVAL | 1d | 2020-11-24 | 2020-11-24
ENGINEER'S REVIEW AND CODE-B APPROVAL | 5d | 2020-11-25 | 2020-11-29
RE-SUBMISSION FOR CODE-A APPROVAL | 2d | 2020-09-06 | 2020-09-07
ENGINEER'S REVIEW AND CODE-A APPROVAL | 3d | 2020-09-08 | 2020-09-10
CIVIL DESIGN DRAWINGS | 221d | 2020-11-30 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-30 | 2020-12-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-14 | 2020-12-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-28 | 2021-01-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-01-04 | 2021-01-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
CIVIL WORKS FOR HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM | 195d | 2021-01-11 | 2021-07-24
COMPLETION OF EXCAVATION | 7d | 2021-01-11 | 2021-01-17
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-18 | 2021-02-14
COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-15 | 2021-03-07
COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-02-15 | 2021-03-16
COMPLETION OF GF SLAB | 28d | 2021-03-17 | 2021-04-13
COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-04-14 | 2021-05-11
COMPLETION OF TOP SLAB | 21d | 2021-05-12 | 2021-06-01
COMPLETION OF BLOCK MASONRY | 25d | 2021-06-02 | 2021-06-26
COMPLETION OF WATERPROOFING | 21d | 2021-06-27 | 2021-07-17
COMPLETION OF FINISHING WORKS | 28d | 2021-06-27 | 2021-07-24
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
DG ROOM | 333d | 2020-09-06 | 2021-08-04
ELECTRICAL DESIGN DRAWINGS | 85d | 2020-09-06 | 2020-11-29
PREPARATION & SUBMISSION TO CLIENT | 24d | 2020-10-17 | 2020-11-09
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-10 | 2020-11-23
RE-SUBMISSION FOR CODE-B APPROVAL | 1d | 2020-11-24 | 2020-11-24
ENGINEER'S REVIEW AND CODE-B APPROVAL | 5d | 2020-11-25 | 2020-11-29
RE-SUBMISSION FOR CODE-A APPROVAL | 2d | 2020-09-06 | 2020-09-07
ENGINEER'S REVIEW AND CODE-A APPROVAL | 3d | 2020-09-08 | 2020-09-10
CIVIL DESIGN DRAWINGS | 221d | 2020-11-30 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-30 | 2020-12-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-14 | 2020-12-27
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-28 | 2021-01-03
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-01-04 | 2021-01-10
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
CIVIL WORKS FOR DG ROOM | 138d | 2021-01-11 | 2021-05-28
COMPLETION OF EXCAVATION | 12d | 2021-01-11 | 2021-01-22
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-23 | 2021-02-19
COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-20 | 2021-03-12
COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-02-20 | 2021-03-19
COMPLETION OF TOP SLAB | 21d | 2021-03-20 | 2021-04-09
COMPLETION OF BLOCK MASONRY | 21d | 2021-04-10 | 2021-04-30
COMPLETION OF WATERPROOFING | 21d | 2021-05-01 | 2021-05-21
COMPLETION OF FINISHING WORKS | 28d | 2021-05-01 | 2021-05-28
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
GUARD ROOM | 334d | 2020-09-03 | 2021-08-02
CIVIL DESIGN DRAWINGS | 279d | 2020-09-03 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 21d | 2020-09-03 | 2020-09-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-09-24 | 2020-10-07
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2020-10-08 | 2020-10-14
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-15 | 2020-10-21
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
CIVIL WORKS FOR GUARD ROOM | 88d | 2021-05-07 | 2021-08-02
COMPLETION OF EXCAVATION | 7d | 2021-05-07 | 2021-05-13
COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 14d | 2021-05-14 | 2021-05-27
COMPLETION OF GRADE SLAB/PCC | 14d | 2021-05-28 | 2021-06-10
COMPLETION OF RCC UPTO TOP SLAB | 15d | 2021-05-28 | 2021-06-11
COMPLETION OF TOP SLAB | 21d | 2021-06-12 | 2021-07-02
COMPLETION OF BLOCK MASONRY | 10d | 2021-07-03 | 2021-07-12
COMPLETION OF WATERPROOFING | 14d | 2021-07-13 | 2021-07-26
COMPLETION OF FINISHING WORKS | 7d | 2021-07-27 | 2021-08-02
ROAD, DRAINS, & LANDSCAPING WORKS | 206d | 2021-01-11 | 2021-08-04
CIVIL DESIGN DRAWINGS | 194d | 2021-01-11 | 2021-07-23
PREPARATION & SUBMISSION TO CLIENT | 14d | 2021-01-11 | 2021-01-24
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2021-01-25 | 2021-02-07
RE-SUBMISSION FOR CODE-B APPROVAL | 7d | 2021-02-08 | 2021-02-14
ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-02-15 | 2021-02-21
RE-SUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-21 | 2021-07-05
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-07-06 | 2021-07-23
CIVIL WORKS - ROADS - 100% COMPLETION | 45d | 2021-06-21 | 2021-08-04
CIVIL WORKS - DRAINS - 100% COMPLETION | 60d | 2021-06-06 | 2021-08-04
COMPOUND WALL(AS SUITABLE/APPLICABLE) | 60d | 2021-06-06 | 2021-08-04
PLANTATION WORKS - LANDSCAPING - 100% COMPLETION INCL. SOIL FILL UP AND DRESSING | 90d | 2021-05-07 | 2021-08-04
OTHER PLANT MECHANICAL, PIPING AND E&I WORKS (VALVES, PIPES, FITTINGS & OTHER COMMON E&I ITEMS) | 313d | 2020-09-26 | 2021-08-04
PROCUREMENT | 267d | 2020-09-26 | 2021-06-19
GATE VALVES | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
KNIFE GATE VALVES | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
NON RETURN VALVES | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
BALL VALVES | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
BUTTERFLY VALVES | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
DI PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
SS PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
MS PIPES & FITTINGS | 237d | 2020-09-26 | 2021-05-20
VENDOR FINALISATION & ORDER | 14d | 2020-09-26 | 2020-10-09
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-10 | 2020-10-16
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-10-17 | 2020-11-13
RESUBMISSION | 14d | 2020-11-14 | 2020-11-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-11-28 | 2020-12-11
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2020-12-12 | 2020-12-16
MANUFACTURING | 120d | 2020-12-17 | 2021-04-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-04-16 | 2021-04-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-04-30 | 2021-05-13
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-05-14 | 2021-05-20
EOT/HOT HOIST ARRANGEMENTS | 237d | 2020-10-26 | 2021-06-19
VENDOR FINALISATION & ORDER | 14d | 2020-10-26 | 2020-11-08
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-11-09 | 2020-11-15
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-16 | 2020-12-13
RESUBMISSION | 14d | 2020-12-14 | 2020-12-27
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-28 | 2021-01-10
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-11 | 2021-01-15
MANUFACTURING | 120d | 2021-01-16 | 2021-05-15
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-16 | 2021-05-29
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-30 | 2021-06-12
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-13 | 2021-06-19
ERECTION | 110d | 2021-04-17 | 2021-08-04
ERECTION OF MECHANICAL & PIPING EQUIPMENT & FITTINGS | 60d | 2021-04-17 | 2021-06-15
ERECTION OF ELECTRICAL & INSTRUMENTATION EQUIPMENT & FIXTURES | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
ELECTRICAL WORKS | 292d | 2020-10-17 | 2021-08-04
ENGINEERING & DOCUMENTATION - ELECTRICAL | 265d | 2020-10-17 | 2021-07-08
TRANSFORMER SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
DG SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
LT CAPACITOR SIZING CALCULATION | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
SINGLE LINE DIAGRAM | 265d | 2020-10-17 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-17 | 2020-10-30
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-10-31 | 2020-11-13
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-14 | 2020-11-20
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
ELECTRICAL HT SUBSTATION LAYOUT | 223d | 2020-11-28 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
EARTHING GRID DESIGN & LAYOUT | 223d | 2020-11-28 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
LIGHTING DESIGN & LAYOUT | 216d | 2020-12-05 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-19 | 2021-01-01
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
POWER & CONTROL CABLE SCHEDULE | 223d | 2020-11-28 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
CABLE ROUTING DRAWING | 223d | 2020-11-28 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-11-28 | 2020-12-11
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-12 | 2020-12-25
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-12-26 | 2021-01-01
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
PROCUREMENT - ELECTRICAL | 237d | 2020-10-17 | 2021-06-10
TRANSFORMER | 237d | 2020-10-17 | 2021-06-10
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
HT PANELS | 237d | 2020-10-17 | 2021-06-10
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
LT PANELS | 237d | 2020-10-17 | 2021-06-10
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
DISTRIBUTION BOXES | 237d | 2020-10-17 | 2021-06-10
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
HT & LT CABLES & TRAYS (AS APPLICABLE) | 237d | 2020-10-17 | 2021-06-10
VENDOR FINALISATION & ORDER | 14d | 2020-10-17 | 2020-10-30
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-10-31 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-07 | 2020-12-04
RESUBMISSION | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-19 | 2021-01-01
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-02 | 2021-01-06
MANUFACTURING | 120d | 2021-01-07 | 2021-05-06
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-07 | 2021-05-20
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-21 | 2021-06-03
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-04 | 2021-06-10
ERECTION | 60d | 2021-06-06 | 2021-08-04
ERECTION OF ELECTRICAL EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST (DRY/WET FOR ELECTRICAL EQUIPMENT AS APPLICABLE) | 15d | 2021-07-21 | 2021-08-04
INSTRUMENTATION CONTROL & AUTOMATION WORKS | 285d | 2020-10-24 | 2021-08-04
ENGINEERING & DOCUMENTATION - ICA | 258d | 2020-10-24 | 2021-07-08
FUNCTIONAL DESIGN SPECIFICATION | 228d | 2020-10-24 | 2021-06-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-10-24 | 2020-11-06
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-11-07 | 2020-11-20
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2020-11-21 | 2020-11-27
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2020-11-28 | 2020-12-04
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-05-07 | 2021-05-21
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-22 | 2021-06-08
INSTRUMENT SCHEDULE | 216d | 2020-12-05 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-19 | 2021-01-01
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
INSTRUMENT DATASHEETS | 216d | 2020-12-05 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-05 | 2020-12-18
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-19 | 2021-01-01
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-02 | 2021-01-08
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
I/O SCHEDULE | 211d | 2020-12-10 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-10 | 2020-12-23
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-24 | 2021-01-06
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-07 | 2021-01-13
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-14 | 2021-01-20
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
INSTRUMENT LOCATION LAYOUT WITH CABLE ROUTING | 209d | 2020-12-12 | 2021-07-08
PREPARATION & SUBMISSION TO CLIENT | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S COMMENTS ON 1st SUBMISSION | 14d | 2020-12-26 | 2021-01-08
RESUBMISSION FOR CODE-B APPROVAL | 7d | 2021-01-09 | 2021-01-15
ENGINEER'S REVIEW & CODE-B APPROVAL | 7d | 2021-01-16 | 2021-01-22
RESUBMISSION FOR CODE-A APPROVAL | 15d | 2021-06-06 | 2021-06-20
ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-08
PROCUREMENT - ICA | 262d | 2020-10-24 | 2021-07-12
INSTRUMENTATION (AS PER APPROVED LIST) | 237d | 2020-10-24 | 2021-06-17
VENDOR FINALISATION & ORDER | 14d | 2020-10-24 | 2020-11-06
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-11-07 | 2020-11-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-14 | 2020-12-11
RESUBMISSION | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-26 | 2021-01-08
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-09 | 2021-01-13
MANUFACTURING | 120d | 2021-01-14 | 2021-05-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-14 | 2021-05-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-28 | 2021-06-10
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-11 | 2021-06-17
INSTRUMENTATION CABLES - POWER & CONTROL CABLES | 237d | 2020-10-24 | 2021-06-17
VENDOR FINALISATION & ORDER | 14d | 2020-10-24 | 2020-11-06
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2020-11-07 | 2020-11-13
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2020-11-14 | 2020-12-11
RESUBMISSION | 14d | 2020-12-12 | 2020-12-25
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2020-12-26 | 2021-01-08
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-01-09 | 2021-01-13
MANUFACTURING | 120d | 2021-01-14 | 2021-05-13
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-14 | 2021-05-27
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-05-28 | 2021-06-10
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-11 | 2021-06-17
INSTRUMENTATION CABLES TRAY & SUPPORTS | 177d | 2021-01-09 | 2021-07-04
VENDOR FINALISATION & ORDER | 14d | 2021-01-09 | 2021-01-22
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2021-01-23 | 2021-01-29
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2021-01-30 | 2021-02-26
RESUBMISSION | 14d | 2021-02-27 | 2021-03-12
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2021-03-13 | 2021-03-26
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-03-27 | 2021-03-31
MANUFACTURING | 60d | 2021-04-01 | 2021-05-30
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-05-31 | 2021-06-13
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-06-14 | 2021-06-27
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-06-28 | 2021-07-04
PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) | 185d | 2021-01-09 | 2021-07-12
VENDOR FINALISATION & ORDER | 14d | 2021-01-09 | 2021-01-22
SUBMISSION OF DATASHEETS/DRAWINGS | 7d | 2021-01-23 | 2021-01-29
ENGINEER'S COMMENTS ON 1st SUBMISSION | 28d | 2021-01-30 | 2021-02-26
RESUBMISSION | 7d | 2021-02-27 | 2021-03-05
ENGINEER'S REVIEW & CODE-A APPROVAL | 14d | 2021-03-06 | 2021-03-19
ISSUE OF MANUFACTURING CLEARANCE | 5d | 2021-03-20 | 2021-03-24
MANUFACTURING | 75d | 2021-03-25 | 2021-06-07
INSPECTION/REVIEW OF TEST CERTIFICATES As Appl. | 14d | 2021-06-08 | 2021-06-21
PAINTING & PACKAGING OF EQUIPMENT | 14d | 2021-06-22 | 2021-07-05
DISPATCH & RECEIPT OF MATERIAL @ SITE | 7d | 2021-07-06 | 2021-07-12
ERECTION | 60d | 2021-06-06 | 2021-08-04
ERECTION OF ICA EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
SITE ACCEPTANCE TEST (DRY/WET FOR ICA EQUIPMENT AS APPLICABLE) | 15d | 2021-07-21 | 2021-08-04
COMMISSIONING | 91d | 2021-08-05 | 2021-11-03
PREPARATION & SUBMISSION OF O&M MANUALS | 50d | 2021-09-14 | 2021-11-02
PREPARATION & SUBMISSION OF AS BUILT DRAWINGS | 50d | 2021-09-14 | 2021-11-02
STABILITY TEST RUN ON COMPLETION OF WORKS | 30d | 2021-08-05 | 2021-09-03
PERFORMANCE RUN & COMMISSIONING | 60d | 2021-09-04 | 2021-11-02
TRAINING OF BWSSB STAFF | 10d | 2021-10-24 | 2021-11-02
HANDING OVER OF PLANT TO CLIENT | 1d | 2021-11-03 | 2021-11-03
ISSUE OF TAKING OVER CERTIFICATE BY CLIENT | ~0 | 2021-11-03 | 2021-11-03
MILESTONE: START DATE | ~0 | 2020-05-04 | 2020-05-04
OVERALL PROJECT TIMELINE | 549d | 2020-05-04 | 2021-11-03
MILESTONE: END DATE | ~0 | 2021-11-03 | 2021-11-03

## sheet 2
SL NO | TASK NAME | DURATION | START DATE | END DATE
I | Engineering (Design, Drawings & Documentation)
11) | Construction / Execution of Work
1 | Handing Over of Site to the Contractor | 1d | 2021-05-20 | 2021-05-20
2 | Permission to start work |  | 2020-05-04 | 2020-05-04
3 | Organisation Chart |  | 2020-05-26 | 2020-05-26
4 | Deployment Schedule |  | 2020-05-27 | 2020-05-27
5 | Topographical Survey
| Mobilization & Demobilization |  | 2020-05-13 | 2020-07-20
| Approval of document |  | 2020-06-02 | 2020-07-31
6 | Geo-Technical Investigation
| Mobilization & Demobilization |  | 2020-05-27 | 2020-07-25
| Approval of document |  | 2020-06-02 | 2020-07-31
7 | Existing structures Demolition and Dismantling Scheme |  | 2020-05-25 | 2020-07-31
8 | Process Design Calculation/Process Flow Diagram/Mass Flow Diagram (BEP)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 10d | 2020-05-19 | 2020-07-26
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
9 | Hydraulic Flow Calculation/Hydraulic Flow Diagram
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 10d | 2020-05-19 | 2020-07-26
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
10 | Construction Programme
11 | Billing Breakup & Cash Flow Chart
12 | Civil Design Basis Report
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-07-27 | 2020-09-02
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
13 | Construction Methodology
14 | Health and Safety Manual
15 | Environmental Management Plan
16 | Quality Assurance Plan
17 | Site/Plant Layout
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 10d | 2020-05-19 | 2020-07-26
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
12) | Process & Instruments Diagram (P&ID)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-07-27 | 2020-08-25
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
13) | Civil GA Drawings and Structural Design and Drawings
1) | TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
2) | STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
3) | SEQUENTIAL BATCH REACTORS
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
4) | DEEP BED MEDIA FILTERS
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
5) | CHLORINE CONTACT TANK
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
6) | INTERMEDIATE SUMP & PLANT DRAIN SUMP
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
7) | THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
8) | SLUDGE THICKENER
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
9) | THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
10) | CENTRIFUGE BUILDING & CENTRATE SUMP
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
11) | DRIED SLUDGE STORAGE SHED
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
12) | CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
13) | AIR BLOWER ROOM (PROCESS)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11
14) | ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-03 | 2020-10-21
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
15) | HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-11-30 | 2021-01-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
16) | DG ROOM
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-11-30 | 2021-01-10
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
17) | GUARD ROOM
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-03 | 2020-10-21
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
18) | ROAD, DRAINS, & LANDSCAPING WORKS
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-01-11 | 2021-02-21
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-23
19) | VENDOR CREDENTIALS
| SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF CEMENT/ STEEL/ AGGREGATES/ OTHER CIVIL ITEMS ETC. AS APPLICABLE | 90d | 2020-05-29 | 2020-08-26
14) | Mechanical Technical Data Sheets/Drawings
14A) | Mechanical GA drawings
1) | TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
2) | STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
3) | SEQUENTIAL BATCH REACTORS
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
4) | DEEP BED MEDIA FILTERS
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
5) | CHLORINE CONTACT TANK
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
6) | INTERMEDIATE SUMP & PLANT DRAIN SUMP
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
7) | THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
8) | SLUDGE THICKENER
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
9) | THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
10) | CENTRIFUGE BUILDING & CENTRATE SUMP
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
11) | DRIED SLUDGE STORAGE SHED
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
12) | CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
13) | AIR BLOWER ROOM (PROCESS)
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
14B) | Mechanical Datasheet
1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
2 | SUBMERSIBLE PUMPS & ACCESSORIES
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
3 | MECHANICAL FINE SCREEN & BELT CONVEYOR
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
4 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
5 | DECANTERS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-07
6 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
7 | PUMPING MACHINERY
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
8 | AIR SCOUR BLOWERS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
9 | UNDERDRAIN COMPONENTS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
10 | PLANT SERVICE WATER PUMPS INCL. MOTORS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
11 | FILTER FEED PUMPS INCL. MOTORS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
12 | PLANT DRAIN PUMPS INCL. MOTORS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
13 | THICKENER FEED PUMPS INCL. MOTORS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
14 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
15 | THICKENER MECHANISM/MACHINERY
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
16 | POLY-ELECTROLYTE DOSING UNITS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
17 | CENTRIFUGE FEED PUMPS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
18 | SLUDGE DEWATERING CENTRIFUGE MACHINERY
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
19 | CENTRATE TRANSFER PUMPS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
20 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC.
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
21 | PROCESS AIR BLOWERS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
22 | MOTORS FOR AIR BLOWERS
| Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11
23 | GATE VALVES
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
24 | KNIFE GATE VALVES
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
25 | NON RETURN VALVES
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
26 | BALL VALVES
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
27 | BUTTERFLY VALVES
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
28 | DI PIPES & FITTINGS
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
29 | SS PIPES & FITTINGS
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
30 | MS PIPES & FITTINGS
| Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11
31 | EOT/HOT HOIST ARRANGEMENTS
| Submission to client and approval in Code 'A' |  | 2020-11-09 | 2021-01-10
15) | Electrical General Arrangement Drawings/ Datasheet
15A) | Electrical GA drawings
1 | TRANSFORMER SIZING CALCULATION
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
2 | DG SIZING CALCULATION
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
3 | LT CAPACITOR SIZING CALCULATION
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
4 | SINGLE LINE DIAGRAM
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
5 | ELECTRICAL HT SUBSTATION LAYOUT
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
6 | EARTHING GRID DESIGN & LAYOUT
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
7 | LIGHTING DESIGN & LAYOUT
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-05 | 2021-01-15
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
8 | POWER & CONTROL CABLE SCHEDULE
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
9 | CABLE ROUTING DRAWING
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
10 | HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2020-09-06 | 2020-09-10
11 | DG ROOM
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-29
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2020-09-06 | 2020-09-10
15B | Electrical Datasheet
1 | TRANSFORMER |  | 2020-10-31 | 2021-01-01
Submission to client and approval in Code 'A'
2 | HT PANELS |  | 2020-10-31 | 2021-01-01
Submission to client and approval in Code 'A'
3 | LT PANELS |  | 2020-10-31 | 2021-01-01
Submission to client and approval in Code 'A'
4 | DISTRIBUTION BOXES |  | 2020-10-31 | 2021-01-01
Submission to client and approval in Code 'A'
5 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2020-10-31 | 2021-01-01
Submission to client and approval in Code 'A'
16) | Instrumentation,Control & Automation Documents
16A | Intruments documents
1 | FUNCTIONAL DESIGN SPECIFICATION
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-24 | 2020-12-04
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08
2 | INSTRUMENT SCHEDULE
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-05 | 2021-01-15
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
3 | INSTRUMENT DATASHEETS
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-05 | 2021-01-15
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
4 | I/O SCHEDULE
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-10 | 2021-01-20
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
5 | INSTRUMENT LOCATION LAYOUT WITH CABLE ROUTING
| ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-12 | 2021-01-22
| ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
16B | Technical Datasheet
1 | INSTRUMENTATION (AS PER APPROVED LIST)
| Submission to client and approval in Code 'A' |  | 2020-11-07 | 2021-01-08
2 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES
| Submission to client and approval in Code 'A' |  | 2020-11-07 | 2021-01-08
3 | INSTRUMENTATION CABLES TRAY & SUPPORTS
| Submission to client and approval in Code 'A' |  | 2021-01-23 | 2021-03-26
4 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE)
| Submission to client and approval in Code 'A' |  | 2021-01-23 | 2021-03-19
II | Place orders for plant and equipments
1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR |  | 2020-07-27 | 2020-08-09
2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  | 2020-07-27 | 2020-08-09
3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2020-07-27 | 2020-08-09
4 | DECANTERS |  | 2020-07-27 | 2020-08-09
5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  | 2020-07-27 | 2020-09-08
6 | PUMPING MACHINERY |  | 2020-07-27 | 2020-09-08
7 | AIR SCOUR BLOWERS |  | 2020-07-27 | 2020-09-08
8 | UNDERDRAIN COMPONENTS |  | 2020-07-27 | 2020-09-08
9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08
10 | FILTER FEED PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08
11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08
12 | THICKENER FEED PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08
13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2020-07-27 | 2020-09-08
14 | THICKENER MECHANISM/MACHINERY |  | 2020-07-27 | 2020-09-08
15 | POLY-ELECTROLYTE DOSING UNITS |  | 2020-07-27 | 2020-09-08
16 | CENTRIFUGE FEED PUMPS |  | 2020-07-27 | 2020-09-08
17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  | 2020-07-27 | 2020-09-08
18 | CENTRATE TRANSFER PUMPS |  | 2020-07-27 | 2020-09-08
19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2020-07-27 | 2020-09-08
20 | PROCESS AIR BLOWERS |  | 2020-07-27 | 2020-09-08
21 | MOTORS FOR AIR BLOWERS |  | 2020-07-27 | 2020-09-08
22 | GATE VALVES |  | 2020-09-26 | 2020-10-09
23 | KNIFE GATE VALVES |  | 2020-09-26 | 2020-10-09
24 | NON RETURN VALVES |  | 2020-09-26 | 2020-10-09
25 | BALL VALVES |  | 2020-09-26 | 2020-10-09
26 | BUTTERFLY VALVES |  | 2020-09-26 | 2020-10-09
27 | DI PIPES & FITTINGS |  | 2020-09-26 | 2020-10-09
28 | SS PIPES & FITTINGS |  | 2020-09-26 | 2020-10-09
29 | MS PIPES & FITTINGS |  | 2020-09-26 | 2020-10-09
30 | EOT/HOT HOIST ARRANGEMENTS |  | 2020-10-26 | 2020-11-08
31 | TRANSFORMER |  | 2020-10-17 | 2020-10-30
32 | HT PANELS |  | 2020-10-17 | 2020-10-30
33 | LT PANELS |  | 2020-10-17 | 2020-10-30
34 | DISTRIBUTION BOXES |  | 2020-10-17 | 2020-10-30
35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2020-10-17 | 2020-10-30
36 | INSTRUMENTATION (AS PER APPROVED LIST) |  | 2020-10-24 | 2020-11-06
37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  | 2020-10-24 | 2020-11-06
38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  | 2021-01-09 | 2021-01-22
39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-01-09 | 2021-01-22
40 | UPS |  | 2020-07-27 | 2020-08-09
41 | LAB EQUIPMENT |  | 2020-07-27 | 2020-08-16
III | Construction of Civil Structures
1 | TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
| COMPLETION OF EXCAVATION | 15d | 2020-11-11 | 2020-11-25
| COMPLETION OF PCC | 12d | 2020-11-26 | 2020-12-07
| COMPLETION OF RAFT | 30d | 2020-12-08 | 2021-01-06
| COMPLETION OF 50% SIDE WALL | 75d | 2020-12-23 | 2021-03-07
| COMPLETION 100% SIDE WALL | 65d | 2021-02-21 | 2021-04-26
| COMPLETION OF PLINTH LEVEL SLAB | 25d | 2021-04-17 | 2021-05-11
| COMPLETION OF COLUMN/BEAM UPTO TOP SLAB | 15d | 2021-05-07 | 2021-05-21
| COMPLETION OF TOP SLAB | 28d | 2021-05-12 | 2021-06-08
| COMPLETION OF BLOCK MASONRY | 20d | 2021-06-09 | 2021-06-28
| COMPLETION OF HYDRO TEST | 28d | 2021-06-29 | 2021-07-26
| COMPLETION OF WATER PROOFING | 20d | 2021-06-22 | 2021-07-11
| COMPLETION OF FINISHING WORKS | 25d | 2021-07-02 | 2021-07-26
2 | STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
| COMPLETION OF EXCAVATION | 7d | 2021-04-01 | 2021-04-07
| COMPLETION OF PCC | 12d | 2021-04-08 | 2021-04-19
| COMPLETION OF RAFT/COLUMNS | 25d | 2021-04-20 | 2021-05-14
| COMPLETION OF 50% SIDE WALL & BASE SLABS | 60d | 2021-05-05 | 2021-07-03
| COMPLETION 100% SIDE WALL | 45d | 2021-06-19 | 2021-08-02
| COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
| COMPLETION OF FINISHING WORKS | 30d | 2021-06-28 | 2021-07-27
3 | 3)SEQUENTIAL BATCH REACTORS
| COMPLETION OF EXCAVATION | 10d | 2020-12-08 | 2020-12-17
| COMPLETION OF PCC | 12d | 2020-12-18 | 2020-12-29
| COMPLETION OF RAFT | 30d | 2020-12-30 | 2021-01-28
| COMPLETION OF 50% SIDE WALL | 80d | 2021-01-09 | 2021-03-29
| COMPLETION 100% SIDE WALL | 110d | 2021-03-10 | 2021-06-27
| COMPLETION OF HYDRO TEST | 30d | 2021-06-28 | 2021-07-27
| COMPLETION OF FINISHING WORKS | 35d | 2021-06-28 | 2021-08-01
4 | 4)DEEP BED MEDIA FILTERS
| COMPLETION OF EXCAVATION | 7d | 2021-01-29 | 2021-02-04
| COMPLETION OF PCC | 10d | 2021-02-05 | 2021-02-14
| COMPLETION OF RAFT | 30d | 2021-02-15 | 2021-03-16
| COMPLETION OF 50% SIDE WALL | 30d | 2021-03-02 | 2021-03-31
| COMPLETION 100% SIDE WALL | 45d | 2021-03-17 | 2021-04-30
| COMPLETION OF TROUGHS & ALLIED CHANNELS | 28d | 2021-03-24 | 2021-04-20
| COMPLETION OF TOP SLAB | 28d | 2021-04-21 | 2021-05-18
| COMPLETION OF HYDRO TEST | 28d | 2021-05-19 | 2021-06-15
| COMPLETION OF BLOCK MASONRY FOR MACHINE ROOM | 25d | 2021-05-19 | 2021-06-12
| COMPLETION OF WATER PROOFING | 21d | 2021-06-13 | 2021-07-03
| COMPLETION OF FINISHING WORKS | 30d | 2021-07-04 | 2021-08-02
5 | 5)CHLORINE CONTACT TANK
| COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
| COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
| COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
| COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
| COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
| COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
6 | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
| COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
| COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
| COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
| COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
| COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
| COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
7 | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
| COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
| COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
| COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
| COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
| COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
| COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
8 | 8)SLUDGE THICKENER
| COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
| COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
| COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
| COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
| COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
| COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
9 | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
| COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
| COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
| COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03
| COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23
| COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27
| COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25
10 | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
| COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07
| COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17
| COMPLETION OF RAFT | 30d | 2021-02-18 | 2021-03-19
| COMPLETION OF 50% SIDE WALL | 48d | 2021-03-05 | 2021-04-21
| COMPLETION OF 100% SIDE WALL | 45d | 2021-04-07 | 2021-05-21
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL FOR CENTRIFUGE BUILDING | 28d | 2021-04-07 | 2021-05-04
| COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
| COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
| COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
| COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
| COMPLETION OF HYDRO TEST OF CENTRATE SUMP | 28d | 2021-05-22 | 2021-06-18
| COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
11 | 11)DRIED SLUDGE STORAGE SHED
| COMPLETION OF EXCAVATION | 7d | 2021-02-08 | 2021-02-14
| COMPLETION OF PCC | 12d | 2021-02-15 | 2021-02-26
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
| COMPLETION OF GRADE SLAB/PCC | 28d | 2021-05-05 | 2021-06-01
| COMPLETION OF WORK UPTO ROOF SHED | 28d | 2021-05-05 | 2021-06-01
| COMPLETION OF TOP ROOF | 28d | 2021-06-02 | 2021-06-29
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-30 | 2021-07-27
12 | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
| COMPLETION OF EXCAVATION | 12d | 2021-01-29 | 2021-02-09
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04
| COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14
| COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25
| COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24
| COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08
| COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02
13 | 13)AIR BLOWER ROOM (PROCESS)
| COMPLETION OF EXCAVATION | 7d | 2021-03-02 | 2021-03-08
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 21d | 2021-03-09 | 2021-03-29
| COMPLETION OF GRADE SLAB/PCC | 28d | 2021-03-30 | 2021-04-26
| COMPLETION OF RCC UPTO TOP SLAB | 56d | 2021-03-30 | 2021-05-24
| COMPLETION OF TOP SLAB | 28d | 2021-05-25 | 2021-06-21
| COMPLETION OF BLOCK MASONRY | 21d | 2021-06-22 | 2021-07-12
| COMPLETION OF FINISHING WORKS | 21d | 2021-07-13 | 2021-08-02
14 | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
| COMPLETION OF EXCAVATION | 6d | 2020-12-18 | 2020-12-23
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2020-12-24 | 2021-01-20
| COMPLETION OF GRADE SLAB/PCC | 15d | 2021-01-21 | 2021-02-04
| COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-01-21 | 2021-02-19
| COMPLETION OF GF SLAB | 30d | 2021-02-20 | 2021-03-21
| COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-03-22 | 2021-04-11
| COMPLETION OF TOP SLAB | 28d | 2021-04-12 | 2021-05-09
| COMPLETION OF BLOCK MASONRY | 25d | 2021-05-10 | 2021-06-03
| COMPLETION OF WATERPROOFING | 28d | 2021-06-04 | 2021-07-01
| COMPLETION OF FINISHING WORKS | 60d | 2021-06-04 | 2021-08-02
15 | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
| COMPLETION OF EXCAVATION | 7d | 2021-01-11 | 2021-01-17
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-18 | 2021-02-14
| COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-15 | 2021-03-07
| COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-02-15 | 2021-03-16
| COMPLETION OF GF SLAB | 28d | 2021-03-17 | 2021-04-13
| COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-04-14 | 2021-05-11
| COMPLETION OF TOP SLAB | 21d | 2021-05-12 | 2021-06-01
| COMPLETION OF BLOCK MASONRY | 25d | 2021-06-02 | 2021-06-26
| COMPLETION OF WATERPROOFING | 21d | 2021-06-27 | 2021-07-17
| COMPLETION OF FINISHING WORKS | 28d | 2021-06-27 | 2021-07-24
16 | 16)DG ROOM
| COMPLETION OF EXCAVATION | 12d | 2021-01-11 | 2021-01-22
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-23 | 2021-02-19
| COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-20 | 2021-03-12
| COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-02-20 | 2021-03-19
| COMPLETION OF TOP SLAB | 21d | 2021-03-20 | 2021-04-09
| COMPLETION OF BLOCK MASONRY | 21d | 2021-04-10 | 2021-04-30
| COMPLETION OF WATERPROOFING | 21d | 2021-05-01 | 2021-05-21
| COMPLETION OF FINISHING WORKS | 28d | 2021-05-01 | 2021-05-28
17 | 17)GUARD ROOM
| COMPLETION OF EXCAVATION | 7d | 2021-05-07 | 2021-05-13
| COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 14d | 2021-05-14 | 2021-05-27
| COMPLETION OF GRADE SLAB/PCC | 14d | 2021-05-28 | 2021-06-10
| COMPLETION OF RCC UPTO TOP SLAB | 15d | 2021-05-28 | 2021-06-11
| COMPLETION OF TOP SLAB | 21d | 2021-06-12 | 2021-07-02
| COMPLETION OF BLOCK MASONRY | 10d | 2021-07-03 | 2021-07-12
| COMPLETION OF WATERPROOFING | 14d | 2021-07-13 | 2021-07-26
| COMPLETION OF FINISHING WORKS | 7d | 2021-07-27 | 2021-08-02 |  | `
18 | 18)ROAD, DRAINS, & LANDSCAPING WORKS
| CIVIL WORKS - ROADS - 100% COMPLETION | 45d | 2021-06-21 | 2021-08-04
| CIVIL WORKS - DRAINS - 100% COMPLETION | 60d | 2021-06-06 | 2021-08-04
| COMPOUND WALL(AS SUITABLE/APPLICABLE) | 60d | 2021-06-06 | 2021-08-04
| PLANTATION WORKS - LANDSCAPING - 100% COMPLETION INCL. SOIL FILL UP AND DRESSING | 90d | 2021-05-07 | 2021-08-04
IV | Supply & Delivery to site Plant & Machineries
1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR | 7d | 2021-03-14 | 2021-03-20
2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  | 2021-03-14 | 2021-03-20
3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2021-03-14 | 2021-03-20
4 | DECANTERS |  | 2021-03-10 | 2021-03-16
5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  | 2021-03-14 | 2021-03-20
6 | PUMPING MACHINERY |  | 2021-03-14 | 2021-03-20
7 | AIR SCOUR BLOWERS |  | 2021-03-14 | 2021-03-20
8 | UNDERDRAIN COMPONENTS |  | 2021-03-14 | 2021-03-20
9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20
10 | FILTER FEED PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20
11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20
12 | THICKENER FEED PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20
13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2021-03-14 | 2021-03-20
14 | THICKENER MECHANISM/MACHINERY |  | 2021-03-14 | 2021-03-20
15 | POLY-ELECTROLYTE DOSING UNITS |  | 2021-03-14 | 2021-03-20
16 | CENTRIFUGE FEED PUMPS |  | 2021-03-14 | 2021-03-20
17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  | 2021-03-14 | 2021-03-20
18 | CENTRATE TRANSFER PUMPS |  | 2021-03-14 | 2021-03-20
19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2021-03-14 | 2021-03-20
20 | PROCESS AIR BLOWERS |  | 2021-03-14 | 2021-03-20
21 | MOTORS FOR AIR BLOWERS |  | 2021-03-14 | 2021-03-20
22 | GATE VALVES |  | 2021-05-14 | 2021-05-20
23 | KNIFE GATE VALVES |  | 2021-05-14 | 2021-05-20
24 | NON RETURN VALVES |  | 2021-05-14 | 2021-05-20
25 | BALL VALVES |  | 2021-05-14 | 2021-05-20
26 | BUTTERFLY VALVES |  | 2021-05-14 | 2021-05-20
27 | DI PIPES & FITTINGS |  | 2021-05-14 | 2021-05-20
28 | SS PIPES & FITTINGS |  | 2021-05-14 | 2021-05-20
29 | MS PIPES & FITTINGS |  | 2021-05-14 | 2021-05-20
30 | EOT/HOT HOIST ARRANGEMENTS |  | 2021-06-13 | 2021-06-19
31 | TRANSFORMER |  | 2021-06-04 | 2021-06-10
32 | HT PANELS |  | 2021-06-04 | 2021-06-10
33 | LT PANELS |  | 2021-06-04 | 2021-06-10
34 | DISTRIBUTION BOXES |  | 2021-06-04 | 2021-06-10
35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2021-06-04 | 2021-06-10
36 | INSTRUMENTATION (AS PER APPROVED LIST) |  | 2021-06-11 | 2021-06-17
37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  | 2021-06-11 | 2021-06-17
38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  | 2021-06-28 | 2021-07-04
39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-07-06 | 2021-07-12
40 | UPS |  | 2021-03-14 | 2021-03-20
41 | LAB EQUIPMENT |  | 2021-03-21 | 2021-03-27
V | Installation of Plant & Machineries
1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
2 | MECHANICAL FINE SCREEN & BELT CONVEYOR
3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
4 | DECANTERS
5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING
6 | PUMPING MACHINERY
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
7 | AIR SCOUR BLOWERS
8 | UNDERDRAIN COMPONENTS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
9 | PLANT SERVICE WATER PUMPS INCL. MOTORS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
10 | FILTER FEED PUMPS INCL. MOTORS
11 | PLANT DRAIN PUMPS INCL. MOTORS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
12 | THICKENER FEED PUMPS INCL. MOTORS
13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
14 | THICKENER MECHANISM/MACHINERY
15 | POLY-ELECTROLYTE DOSING UNITS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
16 | CENTRIFUGE FEED PUMPS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY
18 | CENTRATE TRANSFER PUMPS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC.
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
20 | PROCESS AIR BLOWERS
21 | MOTORS FOR AIR BLOWERS
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
22 | GATE VALVES
23 | KNIFE GATE VALVES
24 | NON RETURN VALVES
25 | BALL VALVES
26 | BUTTERFLY VALVES
27 | DI PIPES & FITTINGS
28 | SS PIPES & FITTINGS |  |  |  | `
29 | MS PIPES & FITTINGS
30 | EOT/HOT HOIST ARRANGEMENTS
31 | TRANSFORMER
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
32 | HT PANELS
33 | LT PANELS
34 | DISTRIBUTION BOXES
35 | HT & LT CABLES & TRAYS (AS APPLICABLE)
| ERECTION | 60d | 2021-06-06 | 2021-08-04
| ERECTION OF ELECTRICAL EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
36 | INSTRUMENTATION (AS PER APPROVED LIST)
37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES
38 | INSTRUMENTATION CABLES TRAY & SUPPORTS
39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE)
| ERECTION | 60d | 2021-06-06 | 2021-08-04
| ERECTION OF ICA EQUIPMENT | 45d | 2021-06-06 | 2021-07-20
40 | UPS
41 | LAB EQUIPMENT
| ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15
| ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20
VI | Testing & Commissioning |  | 2021-08-05 | 2021-11-03
17) | Factory Acceptance Test (FAT) Document
1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR | 14d | 2021-02-14 | 2021-02-27
2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  | 2021-02-14 | 2021-02-27
3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2021-02-14 | 2021-02-27
4 | DECANTERS |  | 2021-02-10 | 2021-02-23
5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  | 2021-02-14 | 2021-02-27
6 | PUMPING MACHINERY |  | 2021-02-14 | 2021-02-27
7 | AIR SCOUR BLOWERS |  | 2021-02-14 | 2021-02-27
8 | UNDERDRAIN COMPONENTS |  | 2021-02-14 | 2021-02-27
9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27
10 | FILTER FEED PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27
11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27
12 | THICKENER FEED PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27
13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2021-02-14 | 2021-02-27
14 | THICKENER MECHANISM/MACHINERY |  | 2021-02-14 | 2021-02-27
15 | POLY-ELECTROLYTE DOSING UNITS |  | 2021-02-14 | 2021-02-27
16 | CENTRIFUGE FEED PUMPS |  | 2021-02-14 | 2021-02-27
17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  | 2021-02-14 | 2021-02-27
18 | CENTRATE TRANSFER PUMPS |  | 2021-02-14 | 2021-02-27
19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2021-02-14 | 2021-02-27
20 | PROCESS AIR BLOWERS |  | 2021-02-14 | 2021-02-27
21 | MOTORS FOR AIR BLOWERS |  | 2021-02-14 | 2021-02-27
22 | GATE VALVES |  | 2021-04-16 | 2021-04-29
23 | KNIFE GATE VALVES |  | 2021-04-16 | 2021-04-29
24 | NON RETURN VALVES |  | 2021-04-16 | 2021-04-29
25 | BALL VALVES |  | 2021-04-16 | 2021-04-29
26 | BUTTERFLY VALVES |  | 2021-04-16 | 2021-04-29
27 | DI PIPES & FITTINGS |  | 2021-04-16 | 2021-04-29
28 | SS PIPES & FITTINGS |  | 2021-04-16 | 2021-04-29
29 | MS PIPES & FITTINGS |  | 2021-04-16 | 2021-04-29
30 | EOT/HOT HOIST ARRANGEMENTS |  | 2021-04-16 | 2021-04-29
31 | TRANSFORMER |  | 2021-05-07 | 2021-05-20
32 | HT PANELS |  | 2021-05-07 | 2021-05-20
33 | LT PANELS |  | 2021-05-07 | 2021-05-20
34 | DISTRIBUTION BOXES |  | 2021-05-07 | 2021-05-20
35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2021-05-07 | 2021-05-20
36 | INSTRUMENTATION (AS PER APPROVED LIST) |  | 2021-05-14 | 2021-05-27
37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  | 2021-05-14 | 2021-05-27
38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  | 2021-05-31 | 2021-06-13
39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-06-08 | 2021-06-21
18) | Site Acceptance Test (SAT) Document
| SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04
19) | Pre-Commissioning Document
20) | Commissioning Philosophy Document
21) | As-Built Drawings |  | 2021-09-14 | 2021-11-02
22) | Training Requirement |  | 2021-10-24 | 2021-11-02
23) | O & M Manuals |  | 2021-09-14 | 2021-11-02
24) | Handing Over Documentations |  | 2021-11-03 | 2021-11-03
25) | Issue of Taking over certificate by Client |  | 2021-11-03 | 2021-11-03
4)

## Zuber_changed
| SL NO | TASK NAME | DURATION | START DATE | END DATE | Activity(Y/N)
| I | Engineering (Design, Drawings & Documentation)
| 11) | Construction / Execution of Work
| 1 | Handing Over of Site to the Contractor | 1d | 2021-05-20 | 2021-05-20 | Y | 11) Construction / Execution of Work
| 2 | Permission to start work |  | 2020-05-04 | 2020-05-04 | Y | 11) Construction / Execution of Work
| 3 | Organisation Chart |  | 2020-05-26 | 2020-05-26 | Y | 11) Construction / Execution of Work
| 4 | Deployment Schedule |  | 2020-05-27 | 2021-05-27 | Y | 11) Construction / Execution of Work
|  | APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL) | 80d | 2020-07-27 | 2020-10-14 | Y | 11) Construction / Execution of Work | Deployment Schedule
|  | FINALISATION FOR CIVIL WORKS | 30d | 2020-07-27 | 2020-08-25 | Y | 11) Construction / Execution of Work | Deployment Schedule | APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL)
|  | FINALISATION FOR MECHANICAL WORKS | 30d | 2020-08-11 | 2020-09-09 | Y | 11) Construction / Execution of Work | Deployment Schedule | APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL)
|  | FINALISATION FOR PIPING WORKS | 30d | 2020-08-21 | 2020-09-19 | Y | 11) Construction / Execution of Work | Deployment Schedule | APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL)
|  | FINALISATION FOR ELECTRICAL WORKS | 30d | 2020-09-05 | 2020-10-04 | Y | 11) Construction / Execution of Work | Deployment Schedule | APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL)
|  | FINALISATION FOR INSTRUMENTATION WORKS | 30d | 2020-09-15 | 2020-10-14 | Y | 11) Construction / Execution of Work | Deployment Schedule | APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL)
|  | MOBILISATION OF SITE TEAMS | 259d | 2020-11-11 | 2021-07-27 | Y | 11) Construction / Execution of Work | Deployment Schedule
|  | MOBILISATION FOR CIVIL WORKS | 6d | 2020-11-11 | 2020-11-16 | Y | 11) Construction / Execution of Work | Deployment Schedule | MOBILISATION OF SITE TEAMS
|  | MOBILISATION FOR MECHANICAL WORKS | 20d | 2021-03-28 | 2021-04-16 | Y | 11) Construction / Execution of Work | Deployment Schedule | MOBILISATION OF SITE TEAMS
|  | MOBILISATION FOR PIPING WORKS WORKS | 7d | 2021-04-10 | 2021-04-16 | Y | 11) Construction / Execution of Work | Deployment Schedule | MOBILISATION OF SITE TEAMS
|  | MOBILISATION FOR ELECTRICAL WORKS | 7d | 2021-07-14 | 2021-07-20 | Y | 11) Construction / Execution of Work | Deployment Schedule | MOBILISATION OF SITE TEAMS
|  | MOBILISATION FOR INSTRUMENTATION WORKS | 7d | 2021-07-21 | 2021-07-27 | Y | 11) Construction / Execution of Work | Deployment Schedule | MOBILISATION OF SITE TEAMS
| 5 | Topographical Survey |  | 2020-05-13 | 2020-07-31 | Y | 11) Construction / Execution of Work
|  | Mobilization & Demobilization |  | 2020-05-13 | 2020-07-20 | Y | 11) Construction / Execution of Work | Topographical Survey
|  | Approval of document |  | 2020-06-02 | 2020-07-31 | Y | 11) Construction / Execution of Work | Topographical Survey
| 6 | Geo-Technical Investigation
|  | Mobilization & Demobilization |  | 2020-05-27 | 2020-07-25 | Y | 11) Construction / Execution of Work | Geo-Technical Investigation
|  | Approval of document |  | 2020-06-02 | 2020-07-31 | Y | 11) Construction / Execution of Work | Geo-Technical Investigation
|  | TEMPORARY SITE ESTABLISHMENT | 95d | 2020-05-29 | 2020-08-31 | Y | 11) Construction / Execution of Work
|  | ESTABLISHMENT OF SITE OFFICE | 24d | 2020-05-29 | 2020-06-21 | Y | 11) Construction / Execution of Work | TEMPORARY SITE ESTABLISHMENT
|  | EST. OF CONSTRUCTION - POWER & WATER | 60d | 2020-06-15 | 2020-08-13 | Y | 11) Construction / Execution of Work | TEMPORARY SITE ESTABLISHMENT
|  | EST. OF LABORATORY | 60d | 2020-07-03 | 2020-08-31 | Y | 11) Construction / Execution of Work | TEMPORARY SITE ESTABLISHMENT
|  | EST. OF STORAGE YARD | 15d | 2020-08-17 | 2020-08-31 | Y | 11) Construction / Execution of Work | TEMPORARY SITE ESTABLISHMENT
|  | EST. OF OTHER TEMPORARY STRUCTURES (As Req.) | 60d | 2020-07-03 | 2020-08-31 | Y | 11) Construction / Execution of Work | TEMPORARY SITE ESTABLISHMENT
| 7 | Existing structures Demolition and Dismantling Scheme |  | 2020-05-25 | 2020-07-31 | Y | 11) Construction / Execution of Work
|  | STATUTORY CLEARANCE FOR DEMOLITION OF EXISTING STRUCTURES BY EMPLOYER | 40d | 2020-05-25 | 2020-07-03 | Y | 11) Construction / Execution of Work | Existing structures Demolition and Dismantling Scheme
|  | DISMANTLING OF EQUIPMENT, PIPES, FITTINGS ETC. | 7d | 2020-05-29 | 2020-06-04 | Y | 11) Construction / Execution of Work | Existing structures Demolition and Dismantling Scheme
|  | DEMOLITION OF APPROVED EXISTING STRUCTURES | 31d | 2020-07-01 | 2020-07-31 | Y | 11) Construction / Execution of Work | Existing structures Demolition and Dismantling Scheme
| 8 | Process Design Calculation/Process Flow Diagram/Mass Flow Diagram (BEP) |  | 2020-05-19 | 2021-06-08 | Y | 11) Construction / Execution of Work
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 10d | 2020-05-19 | 2020-07-26 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 9 | Hydraulic Flow Calculation/Hydraulic Flow Diagram |  | 2020-05-19 | 2021-06-08 | Y | 11) Construction / Execution of Work
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 10d | 2020-05-19 | 2020-07-26 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N | 11) Construction / Execution of Work
| 10 | Construction Programme |  |  |  | N
| 11 | Billing Breakup & Cash Flow Chart |  |  |  | N
| 12 | Civil Design Basis Report |  | 2020-07-27 | 2021-06-08 | Y | 11) Construction / Execution of Work
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-07-27 | 2020-09-02 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 13 | Construction Methodology |  |  |  | N
| 14 | Health and Safety Manual |  |  |  | N
| 15 | Environmental Management Plan |  |  |  | N
| 16 | Quality Assurance Plan |  |  |  | N
| 17 | Site/Plant Layout |  | 2020-05-19 | 2021-06-08 | Y | 11) Construction / Execution of Work
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 10d | 2020-05-19 | 2020-07-26 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 12) | Process & Instruments Diagram (P&ID) |  | 2020-07-27 | 2021-06-08 | N
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-07-27 | 2020-08-25 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 13) | Civil GA Drawings and Structural Design and Drawings
| 1) | TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.) |  |  |  | N
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 2) | STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER |  |  |  | N
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 3) | SEQUENTIAL BATCH REACTORS
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 4) | DEEP BED MEDIA FILTERS
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 5) | CHLORINE CONTACT TANK
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 6) | INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 7) | THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 8) | SLUDGE THICKENER
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 9) | THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 10) | CENTRIFUGE BUILDING & CENTRATE SUMP
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 11) | DRIED SLUDGE STORAGE SHED
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 12) | CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 13) | AIR BLOWER ROOM (PROCESS)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-30 | 2020-11-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-09 | 2021-07-11 | N
| 14) | ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-03 | 2020-10-21 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 15) | HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-11-30 | 2021-01-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 16) | DG ROOM
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-11-30 | 2021-01-10 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 17) | GUARD ROOM
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-09-03 | 2020-10-21 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 18) | ROAD, DRAINS, & LANDSCAPING WORKS
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2021-01-11 | 2021-02-21 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-21 | 2021-07-23 | N
| 19) | VENDOR CREDENTIALS
|  | SUBMISSION & APPROVAL OF VENDOR CREDENTIALS FOR PROCUREMENT OF CEMENT/ STEEL/ AGGREGATES/ OTHER CIVIL ITEMS ETC. AS APPLICABLE | 90d | 2020-05-29 | 2020-08-26 | N
| 14) | Mechanical Technical Data Sheets/Drawings
| 14A) | Mechanical GA drawings
| 1) | TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 2) | STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 3) | SEQUENTIAL BATCH REACTORS
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 4) | DEEP BED MEDIA FILTERS
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 5) | CHLORINE CONTACT TANK
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 6) | INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 7) | THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 8) | SLUDGE THICKENER
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 9) | THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 10) | CENTRIFUGE BUILDING & CENTRATE SUMP
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 11) | DRIED SLUDGE STORAGE SHED
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 12) | CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 13) | AIR BLOWER ROOM (PROCESS)
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-08-26 | 2020-09-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 14B) | Mechanical Datasheet
| 1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 2 | SUBMERSIBLE PUMPS & ACCESSORIES
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 3 | MECHANICAL FINE SCREEN & BELT CONVEYOR
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 4 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 5 | DECANTERS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-07 | N
| 6 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 7 | PUMPING MACHINERY
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 8 | AIR SCOUR BLOWERS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 9 | UNDERDRAIN COMPONENTS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 10 | PLANT SERVICE WATER PUMPS INCL. MOTORS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 11 | FILTER FEED PUMPS INCL. MOTORS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 12 | PLANT DRAIN PUMPS INCL. MOTORS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 13 | THICKENER FEED PUMPS INCL. MOTORS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 14 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 15 | THICKENER MECHANISM/MACHINERY
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 16 | POLY-ELECTROLYTE DOSING UNITS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 17 | CENTRIFUGE FEED PUMPS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 18 | SLUDGE DEWATERING CENTRIFUGE MACHINERY
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 19 | CENTRATE TRANSFER PUMPS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 20 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC.
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 21 | PROCESS AIR BLOWERS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 22 | MOTORS FOR AIR BLOWERS
|  | Submission to client and approval in Code 'A' |  | 2020-08-10 | 2020-10-11 | N
| 23 | GATE VALVES
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 24 | KNIFE GATE VALVES
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 25 | NON RETURN VALVES
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 26 | BALL VALVES
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 27 | BUTTERFLY VALVES
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 28 | DI PIPES & FITTINGS
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 29 | SS PIPES & FITTINGS
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 30 | MS PIPES & FITTINGS
|  | Submission to client and approval in Code 'A' |  | 2020-10-10 | 2020-12-11 | N
| 31 | EOT/HOT HOIST ARRANGEMENTS
|  | Submission to client and approval in Code 'A' |  | 2020-11-09 | 2021-01-10
| 15) | Electrical General Arrangement Drawings/ Datasheet
| 15A) | Electrical GA drawings
| 1 | TRANSFORMER SIZING CALCULATION
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 2 | DG SIZING CALCULATION
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 3 | LT CAPACITOR SIZING CALCULATION
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 4 | SINGLE LINE DIAGRAM
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-27 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 5 | ELECTRICAL HT SUBSTATION LAYOUT
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08
| 6 | EARTHING GRID DESIGN & LAYOUT
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 7 | LIGHTING DESIGN & LAYOUT
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-05 | 2021-01-15 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 8 | POWER & CONTROL CABLE SCHEDULE
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 9 | CABLE ROUTING DRAWING
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-11-28 | 2021-01-08 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 10 | HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2020-09-06 | 2020-09-10 | N
| 11 | DG ROOM
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-17 | 2020-11-29 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2020-09-06 | 2020-09-10 | N
| 15B | Electrical Datasheet
| 1 | TRANSFORMER |  | 2020-10-31 | 2021-01-01 | N
Submission to client and approval in Code 'A'
| 2 | HT PANELS |  | 2020-10-31 | 2021-01-01 | N
Submission to client and approval in Code 'A'
| 3 | LT PANELS |  | 2020-10-31 | 2021-01-01 | N
Submission to client and approval in Code 'A'
| 4 | DISTRIBUTION BOXES |  | 2020-10-31 | 2021-01-01 | N
Submission to client and approval in Code 'A'
| 5 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2020-10-31 | 2021-01-01 | N
Submission to client and approval in Code 'A'
| 16) | Instrumentation,Control & Automation Documents
| 16A | Intruments documents
| 1 | FUNCTIONAL DESIGN SPECIFICATION
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-10-24 | 2020-12-04 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-05-07 | 2021-06-08 | N
| 2 | INSTRUMENT SCHEDULE
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-05 | 2021-01-15 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 3 | INSTRUMENT DATASHEETS
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-05 | 2021-01-15 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 4 | I/O SCHEDULE
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-10 | 2021-01-20 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 5 | INSTRUMENT LOCATION LAYOUT WITH CABLE ROUTING
|  | ENGINEER'S REVIEW AND CODE-B APPROVAL | 7d | 2020-12-12 | 2021-01-22 | N
|  | ENGINEER'S REVIEW AND CODE-A APPROVAL | 18d | 2021-06-06 | 2021-07-08 | N
| 16B | Technical Datasheet |  |  |  | N
| 1 | INSTRUMENTATION (AS PER APPROVED LIST)
|  | Submission to client and approval in Code 'A' |  | 2020-11-07 | 2021-01-08 | N
| 2 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES
|  | Submission to client and approval in Code 'A' |  | 2020-11-07 | 2021-01-08 | N
| 3 | INSTRUMENTATION CABLES TRAY & SUPPORTS
|  | Submission to client and approval in Code 'A' |  | 2021-01-23 | 2021-03-26 | N
| 4 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE)
|  | Submission to client and approval in Code 'A' |  | 2021-01-23 | 2021-03-19 | N
| II | (I) Place orders for plant and equipments |  | 2020-07-27 | 2020-11-08 | Y | 11) Construction / Execution of Work | Construction Programme
| 1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR |  | 2020-07-27 | 2020-08-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  | 2020-07-27 | 2020-08-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2020-07-27 | 2020-08-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 4 | DECANTERS |  | 2020-07-27 | 2020-08-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 6 | PUMPING MACHINERY |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 7 | AIR SCOUR BLOWERS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 8 | UNDERDRAIN COMPONENTS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 10 | FILTER FEED PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 12 | THICKENER FEED PUMPS INCL. MOTORS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 14 | THICKENER MECHANISM/MACHINERY |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 15 | POLY-ELECTROLYTE DOSING UNITS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 16 | CENTRIFUGE FEED PUMPS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 18 | CENTRATE TRANSFER PUMPS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 20 | PROCESS AIR BLOWERS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 21 | MOTORS FOR AIR BLOWERS |  | 2020-07-27 | 2020-09-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 22 | GATE VALVES |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 23 | KNIFE GATE VALVES |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 24 | NON RETURN VALVES |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 25 | BALL VALVES |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 26 | BUTTERFLY VALVES |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 27 | DI PIPES & FITTINGS |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 28 | SS PIPES & FITTINGS |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 29 | MS PIPES & FITTINGS |  | 2020-09-26 | 2020-10-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 30 | EOT/HOT HOIST ARRANGEMENTS |  | 2020-10-26 | 2020-11-08 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 31 | TRANSFORMER |  | 2020-10-17 | 2020-10-30 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 32 | HT PANELS |  | 2020-10-17 | 2020-10-30 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 33 | LT PANELS |  | 2020-10-17 | 2020-10-30 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 34 | DISTRIBUTION BOXES |  | 2020-10-17 | 2020-10-30 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2020-10-17 | 2020-10-30 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 36 | INSTRUMENTATION (AS PER APPROVED LIST) |  | 2020-10-24 | 2020-11-06 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  | 2020-10-24 | 2020-11-06 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  | 2021-01-09 | 2021-01-22 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-01-09 | 2021-01-22 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 40 | UPS |  | 2020-07-27 | 2020-08-09 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
| 41 | LAB EQUIPMENT |  | 2020-07-27 | 2020-08-16 | Y | 11) Construction / Execution of Work | Construction Programme | (I) Place orders for plant and equipments
Construction Programme
| III | (II) Construction of Civil Structures |  | 2020-11-11 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme
| 1 | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.) |  | 2020-11-11 | 2021-07-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 15d | 2020-11-11 | 2020-11-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF PCC | 12d | 2020-11-26 | 2020-12-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF RAFT | 30d | 2020-12-08 | 2021-01-06 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF 50% SIDE WALL | 75d | 2020-12-23 | 2021-03-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION 100% SIDE WALL | 65d | 2021-02-21 | 2021-04-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF PLINTH LEVEL SLAB | 25d | 2021-04-17 | 2021-05-11 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF COLUMN/BEAM UPTO TOP SLAB | 15d | 2021-05-07 | 2021-05-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF TOP SLAB | 28d | 2021-05-12 | 2021-06-08 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF BLOCK MASONRY | 20d | 2021-06-09 | 2021-06-28 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-29 | 2021-07-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF WATER PROOFING | 20d | 2021-06-22 | 2021-07-11 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
|  | COMPLETION OF FINISHING WORKS | 25d | 2021-07-02 | 2021-07-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 1)TSPS & ALLIED UNITS(RC & CS-MECH. & MAN.)
Construction Programme
| 2 | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER |  | 2021-04-01 | 2021-07-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 7d | 2021-04-01 | 2021-04-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | COMPLETION OF PCC | 12d | 2021-04-08 | 2021-04-19 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | COMPLETION OF RAFT/COLUMNS | 25d | 2021-04-20 | 2021-05-14 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | COMPLETION OF 50% SIDE WALL & BASE SLABS | 60d | 2021-05-05 | 2021-07-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | COMPLETION 100% SIDE WALL | 45d | 2021-06-19 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
|  | COMPLETION OF FINISHING WORKS | 30d | 2021-06-28 | 2021-07-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 2)STILLING CHAMBER, SCREEN CHANNEL, GRIT CHAMBER & DISTRIBUTION CHAMBER
| 3 | 3)SEQUENTIAL BATCH REACTORS |  | 2020-12-08 | 2021-08-01 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2020-12-08 | 2020-12-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
|  | COMPLETION OF PCC | 12d | 2020-12-18 | 2020-12-29 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
|  | COMPLETION OF RAFT | 30d | 2020-12-30 | 2021-01-28 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
|  | COMPLETION OF 50% SIDE WALL | 80d | 2021-01-09 | 2021-03-29 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
|  | COMPLETION 100% SIDE WALL | 110d | 2021-03-10 | 2021-06-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
|  | COMPLETION OF HYDRO TEST | 30d | 2021-06-28 | 2021-07-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
|  | COMPLETION OF FINISHING WORKS | 35d | 2021-06-28 | 2021-08-01 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 3)SEQUENTIAL BATCH REACTORS
| 4 | 4)DEEP BED MEDIA FILTERS |  | 2021-01-29 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 7d | 2021-01-29 | 2021-02-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF PCC | 10d | 2021-02-05 | 2021-02-14 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF RAFT | 30d | 2021-02-15 | 2021-03-16 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF 50% SIDE WALL | 30d | 2021-03-02 | 2021-03-31 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION 100% SIDE WALL | 45d | 2021-03-17 | 2021-04-30 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF TROUGHS & ALLIED CHANNELS | 28d | 2021-03-24 | 2021-04-20 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF TOP SLAB | 28d | 2021-04-21 | 2021-05-18 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF HYDRO TEST | 28d | 2021-05-19 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF BLOCK MASONRY FOR MACHINE ROOM | 25d | 2021-05-19 | 2021-06-12 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF WATER PROOFING | 21d | 2021-06-13 | 2021-07-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
|  | COMPLETION OF FINISHING WORKS | 30d | 2021-07-04 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 4)DEEP BED MEDIA FILTERS
| 5 | 5)CHLORINE CONTACT TANK |  | 2021-01-29 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
|  | COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
|  | COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
|  | COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
|  | COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 5)CHLORINE CONTACT TANK
| 6 | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP |  | 2021-01-29 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 6)INTERMEDIATE SUMP & PLANT DRAIN SUMP
| 7 | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP) |  | 2021-01-29 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 7)THICKENER FEED SUMP (SURPLUS SLUDGE SUMP)
| 8 | 8)SLUDGE THICKENER |  | 2021-01-29 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
|  | COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
|  | COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
|  | COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
|  | COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 8)SLUDGE THICKENER
| 9 | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP) |  | 2021-01-29 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | COMPLETION OF RAFT | 45d | 2021-02-18 | 2021-04-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | COMPLETION OF 50% SIDE WALL | 60d | 2021-03-25 | 2021-05-23 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | COMPLETION 100% SIDE WALL | 45d | 2021-05-14 | 2021-06-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | COMPLETION OF HYDRO TEST | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-28 | 2021-07-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 9)THICK SLUDGE SUMP (CENTRIFUGE FEED SUMP)
| 10 | 10)CENTRIFUGE BUILDING & CENTRATE SUMP |  | 2021-01-29 | 2021-05-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 10d | 2021-01-29 | 2021-02-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF PCC | 10d | 2021-02-08 | 2021-02-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF RAFT | 30d | 2021-02-18 | 2021-03-19 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF 50% SIDE WALL | 48d | 2021-03-05 | 2021-04-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF 100% SIDE WALL | 45d | 2021-04-07 | 2021-05-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL FOR CENTRIFUGE BUILDING | 28d | 2021-04-07 | 2021-05-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF HYDRO TEST OF CENTRATE SUMP | 28d | 2021-05-22 | 2021-06-18 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
|  | COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 10)CENTRIFUGE BUILDING & CENTRATE SUMP
| 11 | 11)DRIED SLUDGE STORAGE SHED |  | 2021-02-08 | 2021-07-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 7d | 2021-02-08 | 2021-02-14 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
|  | COMPLETION OF PCC | 12d | 2021-02-15 | 2021-02-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
|  | COMPLETION OF GRADE SLAB/PCC | 28d | 2021-05-05 | 2021-06-01 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
|  | COMPLETION OF WORK UPTO ROOF SHED | 28d | 2021-05-05 | 2021-06-01 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
|  | COMPLETION OF TOP ROOF | 28d | 2021-06-02 | 2021-06-29 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-30 | 2021-07-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 11)DRIED SLUDGE STORAGE SHED
| 12 | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA |  | 2021-01-29 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 12d | 2021-01-29 | 2021-02-09 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-04-07 | 2021-05-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | COMPLETION OF GRADE SLAB/PCC | 10d | 2021-05-05 | 2021-05-14 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-05-05 | 2021-05-25 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | COMPLETION OF TOP SLAB | 30d | 2021-05-26 | 2021-06-24 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | COMPLETION OF BLOCK MASONRY | 14d | 2021-06-25 | 2021-07-08 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
|  | COMPLETION OF FINISHING WORKS | 25d | 2021-07-09 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 12)CHEMICAL ROOM / CHLORINATION ROOM & SCRUBBER AREA
| 13 | 13)AIR BLOWER ROOM (PROCESS) |  | 2021-03-02 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 7d | 2021-03-02 | 2021-03-08 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 21d | 2021-03-09 | 2021-03-29 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
|  | COMPLETION OF GRADE SLAB/PCC | 28d | 2021-03-30 | 2021-04-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
|  | COMPLETION OF RCC UPTO TOP SLAB | 56d | 2021-03-30 | 2021-05-24 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
|  | COMPLETION OF TOP SLAB | 28d | 2021-05-25 | 2021-06-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
|  | COMPLETION OF BLOCK MASONRY | 21d | 2021-06-22 | 2021-07-12 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
|  | COMPLETION OF FINISHING WORKS | 21d | 2021-07-13 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 13)AIR BLOWER ROOM (PROCESS)
| 14 | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP |  | 2020-12-18 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 6d | 2020-12-18 | 2020-12-23 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2020-12-24 | 2021-01-20 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF GRADE SLAB/PCC | 15d | 2021-01-21 | 2021-02-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-01-21 | 2021-02-19 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF GF SLAB | 30d | 2021-02-20 | 2021-03-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF RCC UPTO TOP SLAB | 21d | 2021-03-22 | 2021-04-11 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF TOP SLAB | 28d | 2021-04-12 | 2021-05-09 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF BLOCK MASONRY | 25d | 2021-05-10 | 2021-06-03 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF WATERPROOFING | 28d | 2021-06-04 | 2021-07-01 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
|  | COMPLETION OF FINISHING WORKS | 60d | 2021-06-04 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 14)ADMIN BUILDING, PLC ROOM, LABORATORY & WORKSHOP
| 15 | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM |  | 2021-01-11 | 2021-07-24 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 7d | 2021-01-11 | 2021-01-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-18 | 2021-02-14 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-15 | 2021-03-07 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF RCC UPTO GF SLAB | 30d | 2021-02-15 | 2021-03-16 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF GF SLAB | 28d | 2021-03-17 | 2021-04-13 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-04-14 | 2021-05-11 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF TOP SLAB | 21d | 2021-05-12 | 2021-06-01 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF BLOCK MASONRY | 25d | 2021-06-02 | 2021-06-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF WATERPROOFING | 21d | 2021-06-27 | 2021-07-17 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-06-27 | 2021-07-24 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 15)HT ROOM/SUBSTATION, TRF. YARD & LT MCC ROOM
| 16 | 16)DG ROOM |  | 2021-01-11 | 2021-05-28 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 12d | 2021-01-11 | 2021-01-22 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 28d | 2021-01-23 | 2021-02-19 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF GRADE SLAB/PCC | 21d | 2021-02-20 | 2021-03-12 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF RCC UPTO TOP SLAB | 28d | 2021-02-20 | 2021-03-19 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF TOP SLAB | 21d | 2021-03-20 | 2021-04-09 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF BLOCK MASONRY | 21d | 2021-04-10 | 2021-04-30 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF WATERPROOFING | 21d | 2021-05-01 | 2021-05-21 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
|  | COMPLETION OF FINISHING WORKS | 28d | 2021-05-01 | 2021-05-28 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 16)DG ROOM
| 17 | 17)GUARD ROOM |  | 2021-05-07 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | COMPLETION OF EXCAVATION | 7d | 2021-05-07 | 2021-05-13 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF RCC WORK UPTO PLINTH LEVEL | 14d | 2021-05-14 | 2021-05-27 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF GRADE SLAB/PCC | 14d | 2021-05-28 | 2021-06-10 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF RCC UPTO TOP SLAB | 15d | 2021-05-28 | 2021-06-11 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF TOP SLAB | 21d | 2021-06-12 | 2021-07-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF BLOCK MASONRY | 10d | 2021-07-03 | 2021-07-12 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF WATERPROOFING | 14d | 2021-07-13 | 2021-07-26 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
|  | COMPLETION OF FINISHING WORKS | 7d | 2021-07-27 | 2021-08-02 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 17)GUARD ROOM
| 18 | 18)ROAD, DRAINS, & LANDSCAPING WORKS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures
|  | CIVIL WORKS - ROADS - 100% COMPLETION | 45d | 2021-06-21 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 18)ROAD, DRAINS, & LANDSCAPING WORKS
|  | CIVIL WORKS - DRAINS - 100% COMPLETION | 60d | 2021-06-06 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 18)ROAD, DRAINS, & LANDSCAPING WORKS
|  | COMPOUND WALL(AS SUITABLE/APPLICABLE) | 60d | 2021-06-06 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 18)ROAD, DRAINS, & LANDSCAPING WORKS
|  | PLANTATION WORKS - LANDSCAPING - 100% COMPLETION INCL. SOIL FILL UP AND DRESSING | 90d | 2021-05-07 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme | (II) Construction of Civil Structures | 18)ROAD, DRAINS, & LANDSCAPING WORKS
| IV | (III) Supply & Delivery to site Plant & Machineries |  | 2021-03-14 | 2021-07-12 | Y | 11) Construction / Execution of Work | Construction Programme
| 1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR | 7d | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 4 | DECANTERS |  | 2021-03-10 | 2021-03-16 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 6 | PUMPING MACHINERY |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 7 | AIR SCOUR BLOWERS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 8 | UNDERDRAIN COMPONENTS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 10 | FILTER FEED PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 12 | THICKENER FEED PUMPS INCL. MOTORS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 14 | THICKENER MECHANISM/MACHINERY |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 15 | POLY-ELECTROLYTE DOSING UNITS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 16 | CENTRIFUGE FEED PUMPS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 18 | CENTRATE TRANSFER PUMPS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 20 | PROCESS AIR BLOWERS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 21 | MOTORS FOR AIR BLOWERS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 22 | GATE VALVES |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 23 | KNIFE GATE VALVES |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 24 | NON RETURN VALVES |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 25 | BALL VALVES |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 26 | BUTTERFLY VALVES |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 27 | DI PIPES & FITTINGS |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 28 | SS PIPES & FITTINGS |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 29 | MS PIPES & FITTINGS |  | 2021-05-14 | 2021-05-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 30 | EOT/HOT HOIST ARRANGEMENTS |  | 2021-06-13 | 2021-06-19 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 31 | TRANSFORMER |  | 2021-06-04 | 2021-06-10 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 32 | HT PANELS |  | 2021-06-04 | 2021-06-10 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 33 | LT PANELS |  | 2021-06-04 | 2021-06-10 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 34 | DISTRIBUTION BOXES |  | 2021-06-04 | 2021-06-10 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2021-06-04 | 2021-06-10 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 36 | INSTRUMENTATION (AS PER APPROVED LIST) |  | 2021-06-11 | 2021-06-17 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  | 2021-06-11 | 2021-06-17 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  | 2021-06-28 | 2021-07-04 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-07-06 | 2021-07-12 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 40 | UPS |  | 2021-03-14 | 2021-03-20 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| 41 | LAB EQUIPMENT |  | 2021-03-21 | 2021-03-27 | Y | 11) Construction / Execution of Work | Construction Programme | (III) Supply & Delivery to site Plant & Machineries
| V | (IV) Installation of Plant & Machineries |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme
| 1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | MECHANICAL COARSE SCREEN & BELT CONVEYOR
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | MECHANICAL COARSE SCREEN & BELT CONVEYOR
| 2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
MECHANICAL GRIT REMOVAL DETRITOR MECHANISM | 3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM
| 4 | DECANTERS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 6 | PUMPING MACHINERY |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PUMPING MACHINERY
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PUMPING MACHINERY
| 7 | AIR SCOUR BLOWERS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 8 | UNDERDRAIN COMPONENTS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | UNDERDRAIN COMPONENTS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | UNDERDRAIN COMPONENTS
| 9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PLANT SERVICE WATER PUMPS INCL. MOTORS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PLANT SERVICE WATER PUMPS INCL. MOTORS
| 10 | FILTER FEED PUMPS INCL. MOTORS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PLANT DRAIN PUMPS INCL. MOTORS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PLANT DRAIN PUMPS INCL. MOTORS
| 12 | THICKENER FEED PUMPS INCL. MOTORS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION
| 14 | THICKENER MECHANISM/MACHINERY |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 15 | POLY-ELECTROLYTE DOSING UNITS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | POLY-ELECTROLYTE DOSING UNITS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | POLY-ELECTROLYTE DOSING UNITS
| 16 | CENTRIFUGE FEED PUMPS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | CENTRIFUGE FEED PUMPS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | CENTRIFUGE FEED PUMPS
| 17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 18 | CENTRATE TRANSFER PUMPS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | CENTRATE TRANSFER PUMPS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | CENTRATE TRANSFER PUMPS
| 19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC.
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC.
| 20 | PROCESS AIR BLOWERS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 21 | MOTORS FOR AIR BLOWERS |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | MOTORS FOR AIR BLOWERS
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | MOTORS FOR AIR BLOWERS
| 22 | GATE VALVES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 23 | KNIFE GATE VALVES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 24 | NON RETURN VALVES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 25 | BALL VALVES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 26 | BUTTERFLY VALVES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 27 | DI PIPES & FITTINGS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 28 | SS PIPES & FITTINGS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 29 | MS PIPES & FITTINGS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 30 | EOT/HOT HOIST ARRANGEMENTS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 31 | TRANSFORMER |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | TRANSFORMER
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | TRANSFORMER
| 32 | HT PANELS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 33 | LT PANELS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 34 | DISTRIBUTION BOXES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION | 60d | 2021-06-06 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | HT & LT CABLES & TRAYS (AS APPLICABLE)
|  | ERECTION OF ELECTRICAL EQUIPMENT | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | HT & LT CABLES & TRAYS (AS APPLICABLE)
| 36 | INSTRUMENTATION (AS PER APPROVED LIST) |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION | 60d | 2021-06-06 | 2021-08-04 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE)
|  | ERECTION OF ICA EQUIPMENT | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE)
| 40 | UPS |  |  |  | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
| 41 | LAB EQUIPMENT |  | 2021-04-17 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries
|  | ERECTION OF MECHANICAL & PIPING EQUIPMENT | 60d | 2021-04-17 | 2021-06-15 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | LAB EQUIPMENT
|  | ERECTION OF ELECTRICAL & INSTRUMENTATION EQ. | 45d | 2021-06-06 | 2021-07-20 | Y | 11) Construction / Execution of Work | Construction Programme | (IV) Installation of Plant & Machineries | LAB EQUIPMENT
| VI | (V) Testing & Commissioning |  | 2021-08-05 | 2021-11-03 | Y | 11) Construction / Execution of Work | Construction Programme
| 17) | 17) Factory Acceptance Test(FAT) Document
| 1 | MECHANICAL COARSE SCREEN & BELT CONVEYOR | 14d | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 2 | MECHANICAL FINE SCREEN & BELT CONVEYOR |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 3 | MECHANICAL GRIT REMOVAL DETRITOR MECHANISM |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 4 | DECANTERS |  | 2021-02-10 | 2021-02-23 | Y | 17) Factory Acceptance Test(FAT) Document
| 5 | DIFFUSER ARRANGEMENT INCLUDING LATERAL PIPING |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 6 | PUMPING MACHINERY |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 7 | AIR SCOUR BLOWERS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 8 | UNDERDRAIN COMPONENTS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 9 | PLANT SERVICE WATER PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 10 | FILTER FEED PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 11 | PLANT DRAIN PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 12 | THICKENER FEED PUMPS INCL. MOTORS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 13 | AIR BLOWERS/MIXERS FOR SLUDGE AGITATION |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 14 | THICKENER MECHANISM/MACHINERY |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 15 | POLY-ELECTROLYTE DOSING UNITS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 16 | CENTRIFUGE FEED PUMPS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 17 | SLUDGE DEWATERING CENTRIFUGE MACHINERY |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 18 | CENTRATE TRANSFER PUMPS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 19 | CHLORINATION SYSTEM INCLUDING LEAK ABSORPTION UNIT, BOOSTER PUMPS, ETC. |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 20 | PROCESS AIR BLOWERS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 21 | MOTORS FOR AIR BLOWERS |  | 2021-02-14 | 2021-02-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 22 | GATE VALVES |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 23 | KNIFE GATE VALVES |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 24 | NON RETURN VALVES |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 25 | BALL VALVES |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 26 | BUTTERFLY VALVES |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 27 | DI PIPES & FITTINGS |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 28 | SS PIPES & FITTINGS |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 29 | MS PIPES & FITTINGS |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 30 | EOT/HOT HOIST ARRANGEMENTS |  | 2021-04-16 | 2021-04-29 | Y | 17) Factory Acceptance Test(FAT) Document
| 31 | TRANSFORMER |  | 2021-05-07 | 2021-05-20 | Y | 17) Factory Acceptance Test(FAT) Document
| 32 | HT PANELS |  | 2021-05-07 | 2021-05-20 | Y | 17) Factory Acceptance Test(FAT) Document
| 33 | LT PANELS |  | 2021-05-07 | 2021-05-20 | Y | 17) Factory Acceptance Test(FAT) Document
| 34 | DISTRIBUTION BOXES |  | 2021-05-07 | 2021-05-20 | Y | 17) Factory Acceptance Test(FAT) Document
| 35 | HT & LT CABLES & TRAYS (AS APPLICABLE) |  | 2021-05-07 | 2021-05-20 | Y | 17) Factory Acceptance Test(FAT) Document
| 36 | INSTRUMENTATION (AS PER APPROVED LIST) |  | 2021-05-14 | 2021-05-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 37 | INSTRUMENTATION CABLES - POWER & CONTROL CABLES |  | 2021-05-14 | 2021-05-27 | Y | 17) Factory Acceptance Test(FAT) Document
| 38 | INSTRUMENTATION CABLES TRAY & SUPPORTS |  | 2021-05-31 | 2021-06-13 | Y | 17) Factory Acceptance Test(FAT) Document
| 39 | PLC PANELS INCL. NECESSARY HARDWARE & SOFTWARE (AS APPLICABLE) |  | 2021-06-08 | 2021-06-21 | Y | 17) Factory Acceptance Test(FAT) Document
| 18) | Site Acceptance Test (SAT) Document
|  | SITE ACCEPTANCE TEST(DRY/WET) FOR MECHANICAL/ PIPING/ ELECTRICAL/ INSTRUMENTATION EQ. As Appl. | 15d | 2021-07-21 | 2021-08-04 | Y | 18) Site Acceptance Test(SAT) Document
| 19) | Pre-Commissioning Document
| 20) | Commissioning Philosophy Document |  |  |  | N
| 21) | As-Built Drawings |  | 2021-09-14 | 2021-11-02 | N
| 22) | Training Requirement |  | 2021-10-24 | 2021-11-02 | N
| 23) | O & M Manuals |  | 2021-09-14 | 2021-11-02 | N
| 24) | Handing Over Documentations |  | 2021-11-03 | 2021-11-03 | N
| 25) | Issue of Taking over certificate by Client |  | 2021-11-03 | 2021-11-03 | N
4)

## Sheet 1 changed
Task Name | Duration | Start Date | End Date
SITE ESTABLISHMENT | 95d | 2020-05-29 | 2020-08-31
ESTABLISHMENT OF SITE OFFICE | 24d | 2020-05-29 | 2020-06-21
EST. OF CONSTRUCTION - POWER & WATER | 60d | 2020-06-15 | 2020-08-13
EST. OF LABORATORY | 60d | 2020-07-03 | 2020-08-31
EST. OF STORAGE YARD | 15d | 2020-08-17 | 2020-08-31
EST. OF OTHER TEMPORARY STRUCTURES (As Req.) | 60d | 2020-07-03 | 2020-08-31
DEMOLITION ACTIVITIES | 68d | 2020-05-25 | 2020-07-31
STATUTORY CLEARANCE FOR DEMOLITION OF EXISTING STRUCTURES BY EMPLOYER | 40d | 2020-05-25 | 2020-07-03
DISMANTLING OF EQUIPMENT, PIPES, FITTINGS ETC. | 7d | 2020-05-29 | 2020-06-04
DEMOLITION OF APPROVED EXISTING STRUCTURES | 31d | 2020-07-01 | 2020-07-31
APPOINTMENT OF CONTRACTING TEAMS(INTERNAL/EXTERNAL) | 80d | 2020-07-27 | 2020-10-14
FINALISATION FOR CIVIL WORKS | 30d | 2020-07-27 | 2020-08-25
FINALISATION FOR MECHANICAL WORKS | 30d | 2020-08-11 | 2020-09-09
FINALISATION FOR PIPING WORKS | 30d | 2020-08-21 | 2020-09-19
FINALISATION FOR ELECTRICAL WORKS | 30d | 2020-09-05 | 2020-10-04
FINALISATION FOR INSTRUMENTATION WORKS | 30d | 2020-09-15 | 2020-10-14
MOBILISATION OF SITE TEAMS | 259d | 2020-11-11 | 2021-07-27
MOBILISATION FOR CIVIL WORKS | 6d | 2020-11-11 | 2020-11-16
MOBILISATION FOR MECHANICAL WORKS | 20d | 2021-03-28 | 2021-04-16
MOBILISATION FOR PIPING WORKS WORKS | 7d | 2021-04-10 | 2021-04-16
MOBILISATION FOR ELECTRICAL WORKS | 7d | 2021-07-14 | 2021-07-20
MOBILISATION FOR INSTRUMENTATION WORKS | 7d | 2021-07-21 | 2021-07-27