## CP 10 (hidden)
BALANCE PIPE - SUPPLY SCHEDULE | [17 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Required (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | TOTAL
|  |  |  | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | S
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2900
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3850
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 | 5000 | 523.055 | 2.425 | 2000 | 209.222 | 0.97 | 2000 | 209.222 | 0.97 |  | 0 | 0 | 9000 | 941.4991 | 4.365 | 4850
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 9970
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  | 0 | 0 | 2000 | 625.8905 | 3.25 | 2000 | 625.8905 | 3.25 | 4000 | 1251.7809 | 6.5 | 8000 | 2503.5619 | 13 | 16250
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 22495.5
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 7200 | 3148.451 | 16.9171 | 7200 | 3148.451 | 16.9171 | 23496
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 32000
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 | 2000 | 1322.3108 | 7 | 3000 | 1983.4661 | 10.5 | 3000 | 1983.4661 | 10.5 | 4000 | 2644.6215 | 14 | 12000 | 7933.8645 | 42 | 35000
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 |  | 0 | 0 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 | 42900
| Total | 65383 | 27468.5161 | 7000 | 1845.3658 | 9.425 | 9266 | 4473.2244 | 24.4411 | 7000 | 2818.5786 | 14.72 | 15200 | 7044.8535 | 37.4171 | 38466 | 16182.0223 | 86.0033
BALANCE PIPE - LAYING, JOINTING & HT SCHEDULE | [17 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Work (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | TOTAL
|  |  |  | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | LJ | T
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2030 | 870
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2695 | 1155
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 |  |  | 0 | 960 |  | 0.32592 | 2496 | 1200 | 1.022 | 2496 | 1200 | 1.022 | 5952 | 2400 | 2.3699 | 3395 | 1455
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 6979 | 2991
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  |  | 0 |  |  | 0 | 900 |  | 1.0237 | 1560 | 1200 | 2.3595 | 2460 | 1200 | 3.3833 | 11375 | 4875
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 15746.85 | 6748.65
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  |  | 0 |  |  | 0 |  |  | 0 | 300 |  | 0.49342 | 300 |  | 0.49342 | 16447.2 | 7048.8
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 22400 | 9600
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 |  |  | 0 | 360 |  | 0.882 | 936 |  | 2.2932 | 936 | 1200 | 3.5532 | 2232 |  | 6.7284 | 24500 | 10500
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  |  | 0 |  |  | 0 | 624 |  | 1.8739 | 624 |  | 1.8739 | 1248 |  | 3.7477 | 30030 | 12870
| Total | 65383 | 27468.5161 | 0 | 0 | 0 | 1320 | 0 | 1.2079 | 4956 | 1200 | 6.2128 | 5916 | 3600 | 9.302 | 12192 | 3600 | 16.7227

## CP 10 spk (hidden)
BALANCE PIPE - SUPPLY SCHEDULE | [32 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Required (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | Nov'20 |  |  | Dec'20 |  |  | Jan'20 |  |  | Feb'20 |  |  | Mar'20 |  |  | TOTAL
|  |  |  | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount |  |  |  | S
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 500 | 19.9752 | 0.145 | 606 | 24.21 | 0.17574 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1106 | 44.1852 | 0.32074 |  |  |  | 2900 |  | 1.2849 | 1433.9188 | 1.2597
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 500 | 37.509 | 0.1925 | 98 | 7.3518 | 0.03773 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 598 | 44.8608 | 0.23023 |  |  |  | 3850 |  | 1.6116 | 963.7305 | 1.5739
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 | 5000 | 523.055 | 2.425 | 2000 | 209.222 | 0.97 | 2000 | 209.222 | 0.97 |  | 0 | 0 |  | 0 | 0 | 824 | 86.1995 | 0.39964 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 9824 | 1027.6985 | 4.7646 |  |  |  | 4850 |  | 2.2399 | 22004.6744 | 2.2023
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 90 | 15.6606 | 0.08973 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 90 | 15.6606 | 0.08973 |  |  |  | 9970 |  | 3.1886 | 286.976 | 3.1447
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  | 0 | 0 | 2000 | 625.8905 | 3.25 | 2000 | 625.8905 | 3.25 | 4000 | 1251.7809 | 6.5 | 4000 | 1251.7809 | 6.5 | 1136 | 355.5058 | 1.846 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 13136 | 4110.8486 | 21.346 |  |  |  | 16250 |  | 4.4578 | 58557.5097 | 4.4014
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3229 | 1082.1668 | 7.2638 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3229 | 1082.1668 | 7.2638 |  |  |  | 22495.5 |  | 4.7719 | 15408.5894 | 4.7155
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 7200 | 3148.451 | 16.9171 | 7000 | 3060.994 | 16.4472 | 455 | 198.9646 | 1.0691 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 14655 | 6408.4097 | 34.4334 |  |  |  | 23496 |  | 5.0987 | 74720.7817 | 5.0297
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3639 | 1952.3956 | 11.6448 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3639 | 1952.3956 | 11.6448 |  |  |  | 32000 |  | 5.7332 | 20863.2513 | 5.658
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 | 2000 | 1322.3108 | 7 | 3000 | 1983.4661 | 10.5 | 3000 | 1983.4661 | 10.5 | 4000 | 2644.6215 | 14 | 3000 | 1983.4661 | 10.5 | 1830 | 1209.9143 | 6.405 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 16830 | 11127.245 | 58.905 |  |  |  | 35000 |  | 6.06 | 101989.0174 | 5.9722
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 |  |  |  | 42900 |  | 6.6883 | 15155.5824 | 6.6005
| Total | 65383 | 27468.5161 | 7000 | 1845.3658 | 9.425 | 9266 | 4473.2244 | 24.4411 | 7000 | 2818.5786 | 14.72 | 15200 | 7044.8535 | 37.4171 | 15090 | 6369.386 | 33.8744 | 11817 | 4916.7084 | 28.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65373 | 27468.1166 | 148.7195
BALANCE PIPE - LAYING, JOINTING & HT SCHEDULE | [32 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Work (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | Nov'20 |  |  | Dec'20 |  |  | Jan'20 |  |  | Feb'20 |  |  | Mar'20 |  |  | TOTAL
|  |  |  | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Laying | HT | Amount |  |  |  | LJ | T
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 2030 | 870 |  | 0 | 0 | 459 | 759 | 1459 | 0.459 | 0.759 | 1.459 | 0
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 2695 | 1155 |  | 0 | 0 | 563 | 863 | 1563 | 0.563 | 0.863 | 1.563 | 0
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 |  |  | 0 | 960 |  | 0.32592 | 2496 | 1200 | 1.022 | 2496 | 1200 | 1.022 | 2496 | 2400 | 1.1966 |  | 2400 | 0.3492 |  | 1200 | 0.1746 |  |  | 0 |  |  | 0 | 8448 | 8400 | 4.0903 |  |  |  | 3395 | 1455 |  | 18922.5865 | 18604.6625 | 763 | 1063 | 1763 | 0.763 | 1.063 | 1.763 | 12079.9189 |  | 12079.9189
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 6979 | 2991 |  | 0 | 0 | 1065 | 1365 | 2065 | 1.065 | 1.365 | 2.065 | 0 |  | 0
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  |  | 0 |  |  | 0 | 900 |  | 1.0237 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 10260 | 7200 | 15.1808 |  |  |  | 11375 | 4875 |  | 45736.91 | 45158.0696 | 1469 | 1769 | 2469 | 1.469 | 1.769 | 2.469 | 65829.1245 | 12504.6008 | 53324.5237
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 15746.85 | 6748.65 |  | 0 | 0 | 1569 | 1869 | 2569 | 1.569 | 1.869 | 2.569 | 0 | 0 | 0
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  |  | 0 |  |  | 0 |  |  | 0 | 360 |  | 0.5921 | 624 |  | 1.0263 | 624 |  | 1.0263 | 624 | 800 | 1.5902 | 624 | 800 | 1.5902 | 624 |  | 1.0263 | 3480 | 1600 | 6.8514 |  |  |  | 16447.2 | 7048.8 |  | 17743.3177 | 17503.3206 | 1673 | 1973 | 2673 | 1.673 | 1.973 | 2.673 | 30704.4434 | 7730.6736 | 22973.7698
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 198 |  | 0.44352 | 468 |  | 1.0483 | 468 |  | 1.0483 | 468 |  | 1.0483 | 1602 | 0 | 3.5885 |  |  |  | 22400 | 9600 |  | 9184.6465 | 9064.1294 | 1875 | 2175 | 2875 | 1.875 | 2.175 | 2.875 | 18782.8242 | 5716.5117 | 13066.3125
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 |  |  | 0 | 360 |  | 0.882 | 936 |  | 2.2932 | 936 | 1200 | 3.5532 | 936 |  | 2.2932 | 1872 |  | 4.5864 | 1872 | 2000 | 6.6864 | 1872 | 2000 | 6.6864 | 1872 | 1650 | 6.3189 | 10656 | 6850 | 33.2997 |  |  |  | 24500 | 10500 |  | 64574.8645 | 63639.4183 | 1979 | 2279 | 2979 | 1.979 | 2.279 | 2.979 | 143170.9262 | 47050.8012 | 96120.125
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  |  | 0 |  |  | 0 | 624 |  | 1.8739 | 624 |  | 1.8739 | 624 | 1000 | 3.1609 | 360 | 1200 | 2.6255 |  |  | 0 |  |  | 0 |  |  | 0 | 2232 | 2200 | 9.5341 |  |  |  | 30030 | 12870 |  | 14928.1818 | 14732.2851 | 2179 | 2479 | 3179 | 2.179 | 2.479 | 3.179 | 38328.2045 | 14214.8327 | 24113.3718
| Total | 65383 | 27468.5161 | 0 | 0 | 0 | 1320 | 0 | 1.2079 | 4956 | 1200 | 6.2128 | 5976 | 3600 | 9.4007 | 6240 | 4600 | 10.0365 | 4614 | 4800 | 11.3904 | 4524 | 5200 | 11.859 | 4524 | 4000 | 11.6844 | 4524 | 2850 | 10.753 | 36678 | 26250 | 72.5448
BALANCE E&M ITEM WISE SCHEDULE | [32 empty] | Amounts in Rs. Crore
S. No. | Item Description | Total Qty | JULY'20 |  | AUG'20 |  | SEPT'20 |  | OCT'20 |  | NOV'20 |  | DEC'20 |  | JAN'21 | [16 empty] | FEB'21 |  | MAR'21 |  | TOTAL
|  |  | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | [15 empty] | Amount | Qty | Amount | Qty | Amount | Qty | Amount
1 | Pumps | [29 empty] | 0 |  | 0 |  | 0 |  | 0
2 | Motors | [29 empty] | 0 |  | 0 |  | 0 |  | 0
3 | Panels | [29 empty] | 0 |  | 0 |  | 0 |  | 0
4 | Cable | [29 empty] | 0 |  | 0 |  | 0 |  | 0
5 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
6 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
7 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
8 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
9 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
10 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
11 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
| Total | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0

## to client - Supply (hidden)
PIPE - SUPPLY PLAN
S. No. | Pipe Dia | Bal. Required (in Rmt) |  | July'20 | Aug'20 | Sep'20 |  | Oct'20 |  | Nov'20 |  | Dec'20 |  | Jan'21 |  | Feb'21 |  | Mar'21 |  | Apr'21 |  | May'21 |  | Jun'21 |  | July'21 |  | Aug'21 |  | Sep'21 |  | Oct'21 |  | Nov'21 |  | Dec'21 |  | TOTAL
|  | in mtr | Rate |  |  | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | Amount | in mtr | in MT | S
1 | 401 mm ID 4mm thick | 1116 | 2900 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1116 | 0.32364 | 1116 | 0.32364 | 2900 | 1.2849 | 1433.9188 | 1.2597
2 | 501 mm ID 6mm thick | 598 | 3850 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 598 | 0.23023 | 598 | 0.23023 | 3850 | 1.6116 | 963.7305 | 1.5739
3 | 701 mm ID 6mm thick | 9824 | 4850 |  |  | 4992 | 2.4211 |  | 0 |  | 0 |  | 0 | 2160 | 1.0476 | 1440 | 0.6984 | 720 | 0.3492 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 512 | 0.24832 | 9824 | 4.7646 | 4850 | 2.2399 | 22004.6744 | 2.2023
4 | 1001 mm ID 7mm thick | 90 | 9970 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90 | 0.08973 | 90 | 0.08973 | 9970 | 3.1886 | 286.976 | 3.1447
5 | 1401 mm ID 9mm thick | 13136 | 16250 |  |  |  | 0 | 1020 | 1.6575 | 1020 | 1.6575 | 1020 | 1.6575 | 2004 | 3.2565 | 2004 | 3.2565 | 2004 | 3.2565 | 2004 | 3.2565 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 720 | 1.17 | 720 | 1.17 | 620 | 1.0075 | 13136 | 21.346 | 16250 | 4.4578 | 58557.5097 | 4.4014
6 | 1501 mm ID 9mm thick | 3229 | 22495.5 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 960 | 2.1596 | 960 | 2.1596 | 960 | 2.1596 | 349 | 0.78509 | 3229 | 7.2638 | 22495.5 | 4.7719 | 15408.5894 | 4.7155
7 | 1601 mm ID 11mm thick | 14655 | 23496 |  |  |  | 0 | 1002 | 2.3543 | 1002 | 2.3543 | 1002 | 2.3543 |  | 0 | 1002 | 2.3543 | 1002 | 2.3543 | 1002 | 2.3543 | 1002 | 2.3543 | 1002 | 2.3543 | 1002 | 2.3543 | 1002 | 2.3543 | 1260 | 2.9605 | 1002 | 2.3543 | 1980 | 4.6522 | 393 | 0.92339 | 14655 | 34.4334 | 23496 | 5.0987 | 74720.7817 | 5.0297
8 | 1801 mm ID 12mm thick | 3639 | 32000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 798 | 2.5536 | 798 | 2.5536 | 798 | 2.5536 | 798 | 2.5536 | 210 | 0.672 |  | 0 |  | 0 | 237 | 0.7584 | 3639 | 11.6448 | 32000 | 5.7332 | 20863.2513 | 5.658
9 | 1901 mm ID 14mm thick | 16830 | 35000 |  |  | 1980 | 6.93 | 1020 | 3.57 | 1020 | 3.57 | 1020 | 3.57 | 1020 | 3.57 | 1020 | 3.57 | 1020 | 3.57 | 1020 | 3.57 | 1440 | 5.04 | 1440 | 5.04 | 1440 | 5.04 | 1440 | 5.04 | 720 | 2.52 | 720 | 2.52 |  | 0 | 510 | 1.785 | 16830 | 58.905 | 35000 | 6.06 | 101989.0174 | 5.9722
10 | 2101 mm ID 14mm thick | 2266 | 42900 |  |  |  | 0 | 600 | 2.574 | 600 | 2.574 | 600 | 2.574 | 466 | 1.9991 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2266 | 9.7211 | 42900 | 6.6883 | 15155.5824 | 6.6005
| Total | 65383 | 193711.5 | 0 | 0 | 6972 | 9.3511 | 3642 | 10.1558 | 3642 | 10.1558 | 3642 | 10.1558 | 5650 | 9.8732 | 5466 | 9.8792 | 4746 | 9.53 | 4026 | 9.1808 | 3240 | 9.9479 | 3240 | 9.9479 | 3240 | 9.9479 | 3240 | 9.9479 | 3150 | 8.3121 | 3402 | 8.2039 | 3660 | 7.9818 | 4425 | 6.1513 | 65383 | 148.7224

## to client - laying (hidden)
LAYING & JOINTING PLAN | [33 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia |  |  | Bal. Work (in Rmt) |  | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL |  |  | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1116 | 1116 |  | Gang - 2 | [23 empty] | 550 | 566 |  |  | 1116 | 2900 | 2320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1276 | 0.13131 | 0 | 0 | 0.25891
2 | 501 mm ID 6mm thick | Non-Critical | 598 | 598 |  | Gang - 2 | [22 empty] | 405 | 192 |  |  |  | 597 | 3850 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12474 | 0.059136 | 0 | 0 | 0 | 0.18388
3 | 701 mm ID 6mm thick | Non-Critical | 9823 | 3200 |  | Gang - 2 |  |  |  | 1080 | 1080 | 1040 | [21 empty] | 3200 | 4850 | 3880 | 0 | 0 | 0 | 0.41904 | 0.41904 | 0.40352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2416
4 |  | Critical |  | 4086 |  | Gang - 2 | [5 empty] | 264 | 576 | 576 | 576 | 576 | 576 | 576 | 366 | [14 empty] | 4086 | 4850 | 3880 | 0 | 0 | 0 | 0 | 0 | 0.10243 | 0.22349 | 0.22349 | 0.22349 | 0.22349 | 0.22349 | 0.22349 | 0.14201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5854
5 |  | Critical |  | 2336 |  | Gang - 2 | [13 empty] | 96 | 96 | 96 | 120 | 528 | 528 | 528 | 344 | [6 empty] | 2336 | 4850 | 3880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037248 | 0.037248 | 0.037248 | 0.04656 | 0.20486 | 0.20486 | 0.20486 | 0.13347 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90637
6 |  | Non-Critical |  | 201 |  | Gang - 2 | [21 empty] | 201 | [5 empty] | 201 | 4850 | 3880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.077988 | 0 | 0 | 0 | 0 | 0 | 0.077988
7 | 1001 mm ID 7mm thick |  | 90 | 90 |  | Gang - 2 | [21 empty] | 90 | [5 empty] | 90 | 9970 | 7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.071784 | 0 | 0 | 0 | 0 | 0 | 0.071784
8 | 1401 mm ID 9mm thick | Non-Critical | 13136 | 9500 |  | Gang - 5 | [10 empty] | 810 | 1404 | 810 | 810 | 810 | 810 | 810 | 1404 | 1188 | 644 | [7 empty] | 9500 | 16250 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.053 | 1.8252 | 1.053 | 1.053 | 1.053 | 1.053 | 1.053 | 1.8252 | 1.5444 | 0.8372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.35
9 |  | Critical |  | 3500 |  | Gang - 5 |  |  |  |  | 120 | 624 | 624 | 624 | 624 | 624 | 260 | [16 empty] | 3500 | 16250 | 13000 | 0 | 0 | 0 | 0 | 0.156 | 0.8112 | 0.8112 | 0.8112 | 0.8112 | 0.8112 | 0.338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.55
10 |  | Non-Critical |  | 136 |  | Gang - 5 |  |  |  |  | 136 | [22 empty] | 136 | 16250 | 13000 | 0 | 0 | 0 | 0 | 0.1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1768
11 | 1501 mm ID 9mm thick | Critical | 3229 | 3229 |  | Gang - 5 | [19 empty] | 252 | 546 | 546 | 546 | 546 | 546 | 247 |  | 3229 | 22495.5 | 17996.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45351 | 0.9826 | 0.9826 | 0.9826 | 0.9826 | 0.9826 | 0.44451 | 0 | 5.811
12 | 1601 mm ID 11mm thick | Non-Critical | 14655 | 655 |  | Gang - 7 | [24 empty] | 480 | 175 |  | 655 | 23496 | 18796.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90225 | 0.32894 | 0 | 1.2312
13 |  | Critical |  | 14000 |  | Gang - 6 |  |  |  |  | 150 | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 240 | 240 | 240 | 240 | 240 | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 390 |  |  | 7200 | 23496 | 18796.8 | 0 | 0 | 0 | 0 | 0.28195 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.45112 | 0.45112 | 0.45112 | 0.45112 | 0.45112 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0 | 0 | 13.5337
14 | [5 empty] | Gang - 7 | [5 empty] | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 240 | 240 | 240 | 240 | 240 | 390 | 390 | 390 | 390 | 390 | 390 | 390 | 140 |  |  | 6800 | 23496 | 18796.8 | 0 | 0 | 0 | 0 | 0 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.45112 | 0.45112 | 0.45112 | 0.45112 | 0.45112 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.73308 | 0.26316 | 0 | 0 | 12.7818
15 | 1801 mm ID 12mm thick | Non-Critical | 3639 | 970 |  | Gang - 4 | [12 empty] | 270 | 270 | 270 | 160 | [11 empty] | 970 | 32000 | 25600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6912 | 0.6912 | 0.6912 | 0.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4832
16 |  | Critical |  | 300 |  | Gang - 4 | [15 empty] | 60 | 180 | 60 | [9 empty] | 300 | 32000 | 25600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1536 | 0.4608 | 0.1536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.768
17 |  | Critical |  | 2369 |  | Gang - 4 | [17 empty] | 252 | 312 | 312 | 312 | 312 | 312 | 312 | 245 |  |  | 2369 | 32000 | 25600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64512 | 0.79872 | 0.79872 | 0.79872 | 0.79872 | 0.79872 | 0.79872 | 0.6272 | 0 | 0 | 6.0646
18 | 1901 mm ID 14mm thick | Non-Critical | 16830 | 10670 |  | Gang - 1 |  |  |  | 540 | 540 | 936 | 936 | 936 | 936 | 936 | 936 | 936 | 540 | 540 | 540 | 540 | 540 | 338 | [9 empty] | 10670 | 35000 | 28000 | 0 | 0 | 0 | 1.512 | 1.512 | 2.6208 | 2.6208 | 2.6208 | 2.6208 | 2.6208 | 2.6208 | 2.6208 | 1.512 | 1.512 | 1.512 | 1.512 | 1.512 | 0.9464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.876
19 |  | Critical |  | 4000 |  | Gang - 3 | [5 empty] | 312 | 312 | 312 | 312 | 312 | 312 | 312 | [5 empty] | 312 | 312 | 312 | 312 | 312 | 256 |  |  |  |  | 4000 | 35000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0.8736 | 0.8736 | 0.8736 | 0.8736 | 0.8736 | 0.8736 | 0.8736 | 0 | 0 | 0 | 0 | 0 | 0.8736 | 0.8736 | 0.8736 | 0.8736 | 0.8736 | 0.7168 | 0 | 0 | 0 | 0 | 11.2
20 |  | Non-Critical |  | 1400 |  | Gang - 1 | [17 empty] | 576 | 576 | 248 | [7 empty] | 1400 | 35000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6128 | 1.6128 | 0.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.92
21 |  | Critical |  | 760 |  | Gang - 1 | [19 empty] | 240 | 240 | 240 | 40 |  |  |  |  | 760 | 35000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.672 | 0.672 | 0.672 | 0.112 | 0 | 0 | 0 | 0 | 2.128
22 | 2101 mm ID 14mm thick | Non-Critical | 2266 | 1006 |  | Gang - 4 | [10 empty] | 468 | 468 | 70 | [14 empty] | 1006 | 42900 | 34320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6062 | 1.6062 | 0.24024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4526
23 |  | Critical |  | 1260 |  | Gang - 4 |  |  |  |  | 90 | 234 | 234 | 234 | 234 | 234 | [17 empty] | 1260 | 42900 | 34320 | 0 | 0 | 0 | 0 | 0.30888 | 0.80309 | 0.80309 | 0.80309 | 0.80309 | 0.80309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3243
| Total |  | 65382 | 65382 |  |  | 0 | 0 | 0 | 1620 | 2116 | 4190 | 3462 | 3462 | 3462 | 3462 | 4142 | 4476 | 2536 | 2196 | 2196 | 2146 | 2130 | 4250 | 3696 | 3316 | 2534 | 2481 | 2339 | 2380 | 2367 | 422 | 0 | 65381 |  |  | 0 | 0 | 0 | 1.931 | 2.8547 | 7.0808 | 6.7983 | 6.7983 | 6.7983 | 6.7983 | 8.1812 | 8.6154 | 4.5407 | 4.1957 | 4.1957 | 4.0677 | 3.9746 | 7.7277 | 6.5005 | 6.0004 | 4.9265 | 4.9428 | 4.201 | 3.4342 | 3.6396 | 0.77346 | 0 | 118.9772
| Fabrication |  |  | 1039215
S. No. | Pipe Dia |  |  | Bal. Work (in Rmt) |  | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL |  |  | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1116 | 0.017069 | 17738.2757 | 17738.2757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8741.9817 | 8996.2939 | 0 | 0 | 17738.2757 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1017 | 0.10466 | 0 | 0 | 0.20636
2 | 501 mm ID 6mm thick | Non-Critical | 598 | 0.0091462 | 9504.9183 | 9504.9183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6437.2775 | 3051.7464 | 0 | 0 | 0 | 9489.0238 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074888 | 0.035502 | 0 | 0 | 0 | 0.11039
3 | 701 mm ID 6mm thick | Non-Critical | 9823 | 0.15024 | 50862.4392 | 156131.7938 | 0 | 0 | 0 | 17166.0732 | 17166.0732 | 16530.2927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50862.4392 |  | 116.3343 | 0 | 0 | 0 | 0.1997 | 0.1997 | 0.1923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5917
4 |  | Critical |  |  | 64944.9771 |  | 0 | 0 | 0 | 0 | 0 | 4196.1512 | 9155.2391 | 9155.2391 | 9155.2391 | 9155.2391 | 9155.2391 | 9155.2391 | 5817.3915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64944.9771 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0.048816 | 0.10651 | 0.10651 | 0.10651 | 0.10651 | 0.10651 | 0.10651 | 0.067676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75553
5 |  | Critical |  |  | 37129.5806 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525.8732 | 1525.8732 | 1525.8732 | 1907.3415 | 8392.3025 | 8392.3025 | 8392.3025 | 5467.7122 | 0 | 0 | 0 | 0 | 0 | 0 | 37129.5806 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017751 | 0.017751 | 0.017751 | 0.022189 | 0.097631 | 0.097631 | 0.097631 | 0.063608 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43194
6 |  | Non-Critical |  |  | 3194.797 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194.797 | 0 | 0 | 0 | 0 | 0 | 3194.797 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037166 | 0 | 0 | 0 | 0 | 0 | 0.037166
7 | 1001 mm ID 7mm thick |  | 90 | 0.0013765 | 1430.5061 | 1430.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430.5061 | 0 | 0 | 0 | 0 | 0 | 1430.5061 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016642 | 0 | 0 | 0 | 0 | 0 | 0.016642
8 | 1401 mm ID 9mm thick | Non-Critical | 13136 | 0.20091 | 150997.8664 | 208790.3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12874.5549 | 22315.8952 | 12874.5549 | 12874.5549 | 12874.5549 | 12874.5549 | 12874.5549 | 22315.8952 | 18882.6806 | 10236.0659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150997.8664 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14978 | 0.25961 | 0.14978 | 0.14978 | 0.14978 | 0.14978 | 0.14978 | 0.25961 | 0.21967 | 0.11908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7566
9 |  | Critical |  |  | 55630.7929 |  | 0 | 0 | 0 | 0 | 1907.3415 | 9918.1756 | 9918.1756 | 9918.1756 | 9918.1756 | 9918.1756 | 4132.5732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55630.7929 |  | 116.3343 | 0 | 0 | 0 | 0 | 0.022189 | 0.11538 | 0.11538 | 0.11538 | 0.11538 | 0.11538 | 0.048076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64718
10 |  | Non-Critical |  |  | 2161.6537 |  | 0 | 0 | 0 | 0 | 2161.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161.6537 |  | 116.3343 | 0 | 0 | 0 | 0 | 0.025147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025147
11 | 1501 mm ID 9mm thick | Critical | 3229 | 0.049387 | 51323.3801 | 51323.3801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4005.4171 | 8678.4037 | 8678.4037 | 8678.4037 | 8678.4037 | 8678.4037 | 3925.9445 | 0 | 51323.3801 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046597 | 0.10096 | 0.10096 | 0.10096 | 0.10096 | 0.10096 | 0.045672 | 0 | 0.59707
12 | 1601 mm ID 11mm thick | Non-Critical | 14655 | 0.22414 | 10410.9055 | 232934.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7629.3659 | 2781.5396 | 0 | 10410.9055 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088756 | 0.032359 | 0 | 0.12111
13 |  | Critical |  |  | 222523.1715 |  | 0 | 0 | 0 | 0 | 2384.1768 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 3814.6829 | 3814.6829 | 3814.6829 | 3814.6829 | 3814.6829 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 0 | 0 | 114440.4882 |  | 116.3343 | 0 | 0 | 0 | 0 | 0.027736 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.044378 | 0.044378 | 0.044378 | 0.044378 | 0.044378 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0 | 0 | 1.3313
14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 3814.6829 | 3814.6829 | 3814.6829 | 3814.6829 | 3814.6829 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 6198.8598 | 2225.2317 | 0 | 0 | 108082.6833 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.044378 | 0.044378 | 0.044378 | 0.044378 | 0.044378 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.072114 | 0.025887 | 0 | 0 | 1.2574
15 | 1801 mm ID 12mm thick | Non-Critical | 3639 | 0.055658 | 15417.6769 | 57840.1301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4291.5183 | 4291.5183 | 4291.5183 | 2543.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15417.6769 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.049925 | 0.049925 | 0.049925 | 0.029585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17936
16 |  | Critical |  |  | 4768.3537 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953.6707 | 2861.0122 | 953.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4768.3537 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011094 | 0.033283 | 0.011094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055472
17 |  | Critical |  |  | 37654.0995 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4005.4171 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 3894.1555 | 0 | 0 | 37654.0995 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046597 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.045302 | 0 | 0 | 0.43805
18 | 1901 mm ID 14mm thick | Non-Critical | 16830 | 0.25741 | 169594.4457 | 267504.6412 | 0 | 0 | 0 | 8583.0366 | 8583.0366 | 14877.2635 | 14877.2635 | 14877.2635 | 14877.2635 | 14877.2635 | 14877.2635 | 14877.2635 | 8583.0366 | 8583.0366 | 8583.0366 | 8583.0366 | 8583.0366 | 5372.3451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169594.4457 |  | 116.3343 | 0 | 0 | 0 | 0.09985 | 0.09985 | 0.17307 | 0.17307 | 0.17307 | 0.17307 | 0.17307 | 0.17307 | 0.17307 | 0.09985 | 0.09985 | 0.09985 | 0.09985 | 0.09985 | 0.062499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.973
19 |  | Critical |  |  | 63578.049 |  | 0 | 0 | 0 | 0 | 0 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 0 | 0 | 0 | 0 | 0 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4959.0878 | 4068.9951 | 0 | 0 | 0 | 0 | 63578.049 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0 | 0 | 0 | 0 | 0 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.057691 | 0.047336 | 0 | 0 | 0 | 0 | 0.73963
20 |  | Non-Critical |  |  | 22252.3172 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9155.2391 | 9155.2391 | 3941.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22252.3172 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10651 | 0.10651 | 0.045857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25887
21 |  | Critical |  |  | 12079.8293 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3814.6829 | 3814.6829 | 3814.6829 | 635.7805 | 0 | 0 | 0 | 0 | 12079.8293 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.044378 | 0.044378 | 0.044378 | 0.0073963 | 0 | 0 | 0 | 0 | 0.14053
22 | 2101 mm ID 14mm thick | Non-Critical | 2266 | 0.034658 | 15989.8793 | 36016.9648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7438.6317 | 7438.6317 | 1112.6159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15989.8793 |  | 116.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086537 | 0.086537 | 0.012944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18602
23 |  | Critical |  |  | 20027.0854 |  | 0 | 0 | 0 | 0 | 1430.5061 | 3719.3159 | 3719.3159 | 3719.3159 | 3719.3159 | 3719.3159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20027.0854 |  | 116.3343 | 0 | 0 | 0 | 0 | 0.016642 | 0.043268 | 0.043268 | 0.043268 | 0.043268 | 0.043268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23298
| Total |  | 65382 | 1 |  |  | 0 | 0 | 0 | 25749.1098 | 33632.7879 | 66598.0063 | 55026.8014 | 55026.8014 | 55026.8014 | 55026.8014 | 65835.0697 | 71143.8368 | 40308.4831 | 34904.3489 | 34904.3489 | 34109.6233 | 33855.3111 | 67551.6771 | 58746.1173 | 52706.2026 | 40276.694 | 39434.2849 | 37177.2642 | 37828.9392 | 37622.3105 | 6707.4842 | 0 | 1039199.1055 |  | 116.3343 | 0 | 0 | 0 | 0.29955 | 0.39126 | 0.77476 | 0.64015 | 0.64015 | 0.64015 | 0.64015 | 0.76589 | 0.82765 | 0.46893 | 0.40606 | 0.40606 | 0.39681 | 0.39385 | 0.78586 | 0.68342 | 0.61315 | 0.46856 | 0.45876 | 0.4325 | 0.44008 | 0.43768 | 0.078031 | 0 | 12.0895
S. No. | Pipe Dia |  |  | Bal. Work (in Rmt) |  | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1.282 | 1116 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705.1 | 725.612 | 0 | 0
2 | 501 mm ID 6mm thick | Non-Critical | 1.608 | 598 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651.24 | 308.736 | 0 | 0 | 0
3 | 701 mm ID 6mm thick | Non-Critical | 2.237 | 3200 |  | Gang - 2 |  |  |  | 2415.96 | 2415.96 | 2326.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
4 |  | Critical | 2.237 | 4086 |  | Gang - 2 |  |  |  | 0 | 0 | 590.568 | 1288.512 | 1288.512 | 1288.512 | 1288.512 | 1288.512 | 1288.512 | 818.742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Critical | 2.237 | 2336 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.752 | 214.752 | 214.752 | 268.44 | 1181.136 | 1181.136 | 1181.136 | 769.528 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Non-Critical | 2.237 | 201 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.637 | 0 | 0 | 0 | 0 | 0
7 | 1001 mm ID 7mm thick |  | 3.185 | 90 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.65 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
8 | 1401 mm ID 9mm thick | Non-Critical | 4.455 | 9500 |  | Gang - 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3608.55 | 6254.82 | 3608.55 | 3608.55 | 3608.55 | 3608.55 | 3608.55 | 6254.82 | 5292.54 | 2869.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
9 |  | Critical | 4.455 | 3500 |  | Gang - 5 |  |  |  | 0 | 534.6 | 2779.92 | 2779.92 | 2779.92 | 2779.92 | 2779.92 | 1158.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Non-Critical | 4.455 | 136 |  | Gang - 5 |  |  |  | 0 | 605.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1501 mm ID 9mm thick | Critical | 4.769 | 3229 |  | Gang - 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1201.788 | 2603.874 | 2603.874 | 2603.874 | 2603.874 | 2603.874 | 1177.943 | 0 | [18 empty] | 0
12 | 1601 mm ID 11mm thick | Non-Critical | 5.096 | 655 |  | Gang - 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2446.08 | 891.8 | 0 | [18 empty] | 0
13 |  | Critical | 5.096 | 14000 |  | Gang - 6 |  |  |  | 0 | 764.4 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1223.04 | 1223.04 | 1223.04 | 1223.04 | 1223.04 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 0 | 0
14 |  |  | 5.096 |  |  | Gang - 7 |  |  |  | 0 | 0 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1223.04 | 1223.04 | 1223.04 | 1223.04 | 1223.04 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 713.44 | 0 | 0
15 | 1801 mm ID 12mm thick | Non-Critical | 5.724 | 970 |  | Gang - 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545.48 | 1545.48 | 1545.48 | 915.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
16 |  | Critical | 5.724 | 300 |  | Gang - 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343.44 | 1030.32 | 343.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Critical | 5.724 | 2369 |  | Gang - 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442.448 | 1785.888 | 1785.888 | 1785.888 | 1785.888 | 1785.888 | 1785.888 | 1402.38 | 0 | 0
18 | 1901 mm ID 14mm thick | Non-Critical | 6.038 | 10670 |  | Gang - 1 |  |  |  | 3260.52 | 3260.52 | 5651.568 | 5651.568 | 5651.568 | 5651.568 | 5651.568 | 5651.568 | 5651.568 | 3260.52 | 3260.52 | 3260.52 | 3260.52 | 3260.52 | 2040.844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
19 |  | Critical | 6.038 | 4000 |  | Gang - 3 |  |  |  | 0 | 0 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 0 | 0 | 0 | 0 | 0 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1545.728 | 0 | 0 | 0 | 0
20 |  | Non-Critical | 6.038 | 1400 |  | Gang - 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3477.888 | 3477.888 | 1497.424 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Critical | 6.038 | 760 |  | Gang - 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1449.12 | 1449.12 | 1449.12 | 241.52 | 0 | 0 | 0 | 0
22 | 2101 mm ID 14mm thick | Non-Critical | 6.666 | 1006 |  | Gang - 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3119.688 | 3119.688 | 466.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
23 |  | Critical | 6.666 | 1260 |  | Gang - 4 |  |  |  | 0 | 599.94 | 1559.844 | 1559.844 | 1559.844 | 1559.844 | 1559.844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 65382 |  |  | 0 | 0 | 0 | 5676.48 | 8181.3 | 18767.116 | 17138.58 | 17138.58 | 17138.58 | 17138.58 | 20685.354 | 22173.324 | 12145.992 | 11075.382 | 11075.382 | 10789.182 | 10613.91 | 20599.312 | 17596.188 | 15843.112 | 12467.146 | 12433.905 | 10803.13 | 9378.478 | 9878.826 | 2069.743 | 0 | 0
S. No. | Pipe Dia |  |  | Bal. Work (in Rmt) |  | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1.282 | 1116 |  | Gang - 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116 | 0 |  |  |  |  | 0 | 0
2 | 501 mm ID 6mm thick | Non-Critical | 1.608 | 598 |  | Gang - 2 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 77 |  |  |  | 0 | 0
3 | 701 mm ID 6mm thick | Non-Critical | 2.237 | 3200 |  | Gang - 2 |  |  | 648 | 1080 | 1056 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
4 |  | Critical | 2.237 | 4086 |  | Gang - 2 |  |  | 0 | 0 |  | 454 | 900 | 900 | 900 | 900 | 32 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Critical | 2.237 | 2336 |  | Gang - 2 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 840 | 900 | 240 | 356 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Non-Critical | 2.237 | 201 |  | Gang - 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201 |  | 0 | 0 | 0 | 0 | 0
7 | 1001 mm ID 7mm thick |  | 3.185 | 90 |  | Gang - 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 |  | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
8 | 1401 mm ID 9mm thick | Non-Critical | 4.455 | 9500 |  | Gang - 5 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 360 | 960 | 1047.6 | 810 | 810 | 810 | 810 | 1044 | 1176 | 1080 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
9 |  | Critical | 4.455 | 3500 |  | Gang - 5 |  |  | 0 | 72 | 420 | 624 | 624 | 624 | 624 | 300 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Non-Critical | 4.455 | 136 |  | Gang - 5 |  |  |  | 136 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1501 mm ID 9mm thick | Critical | 4.769 | 3229 |  | Gang - 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 708 | 870 | 1038 | 193 | [22 empty] | 0
12 | 1601 mm ID 11mm thick | Non-Critical | 5.096 | 655 |  | Gang - 7 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 240 | 235 | [22 empty] | 0
13 |  | Critical | 5.096 | 14000 |  | Gang - 6 |  |  | 0 | 90 | 294 | 390 | 390 | 390 | 390 | 384 | 204 | 192 | 240 | 84 | 240 | 240 | 156 | 390 | 390 | 390 | 390 | 390 | 1321
14 |  |  | 5.096 |  |  | Gang - 7 |  |  | 0 | 0 | 234 | 390 | 390 | 390 | 390 | 390 |  | 300 | 240 | 240 | 240 | 240 | 330 | 390 | 390 | 390 | 390 | 390 | 1321
15 | 1801 mm ID 12mm thick | Non-Critical | 5.724 | 970 |  | Gang - 4 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 270 | 270 | 204 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
16 |  | Critical | 5.724 | 300 |  | Gang - 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 192 | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Critical | 5.724 | 2369 |  | Gang - 4 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151.2 | 288 | 312 | 312 | 312 | 994
18 | 1901 mm ID 14mm thick | Non-Critical | 6.038 | 10670 |  | Gang - 1 |  |  | 324 | 540 | 780 | 936 | 936 | 936 | 936 | 768 | 768 | 696 | 540 | 528 | 540 | 540 | 418.8 | 435 | 48 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
19 |  | Critical | 6.038 | 4000 |  | Gang - 3 |  |  | 0 | 0 |  | 192 | 312 | 312 | 312 | 312 | 312 | 300 | 216 | 0 | 0 | 0 |  |  | 360 | 528 | 528 | 316 |  | 0 | 0 | 0 | 0
20 |  | Non-Critical | 6.038 | 1400 |  | Gang - 1 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.6 | 576 | 379.2 | 99.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Critical | 6.038 | 760 |  | Gang - 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 240 | 376 |  |  | 0 | 0 | 0 | 0
22 | 2101 mm ID 14mm thick | Non-Critical | 6.666 | 1006 |  | Gang - 4 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 280.8 | 468 | 229.2 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
23 |  | Critical | 6.666 | 1260 |  | Gang - 4 |  |  | 0 | 54 | 180 | 234 | 234 | 234 | 234 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 65382 |  |  | 0 | 0 | 972 | 1972 | 2964 | 3636 | 3786 | 3786 | 3786 | 3784.8 | 3796 | 3826.8 | 2584 | 2288 | 2088 | 2086 | 2499.6 | 3255 | 3523.2 | 4375.2 | 3857 | 3445 | 3072 | 0 | 0 | 0 | 0 | 0
[9 empty] | 3405.888 | 7421.724 | 12833.58 | 17071.698 | 17863.368 | 17863.368 | 17863.368 | 17890.6968 | 17852.236 | 17656.5732 | 12888.366 | 10789.57 | 10791.942 | 10780.494 | 12917.688 | 16966.89 | 18197.7336 | 18441.4456 | 17857.877 | 17869.622 | 15581.609 | 0 | 0 | 0 | 0
[9 empty] | 162 | 328.6667 | 494 | 606 | 631 | 631 | 631 | 630.8 | 632.6667 | 637.8 | 430.6667 | 381.3333 | 348 | 347.6667 | 416.6 | 542.5 | 587.2 | 729.2 | 642.8333 | 574.1667 | 512 | 0 | 0 | 0
S. No. | Pipe Dia |  |  | Bal. Work (in Rmt) |  | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1.282 | 1116 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430.712 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 501 mm ID 6mm thick | Non-Critical | 1.608 | 598 |  | Gang - 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 836.16 | 123.816 | 0 | 0 | 0 | 0 | 0
3 | 701 mm ID 6mm thick | Non-Critical | 2.237 | 3200 |  | Gang - 2 |  |  | 1449.576 | 2415.96 | 2362.272 | 930.592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
4 |  | Critical | 2.237 | 4086 |  | Gang - 2 |  |  | 0 | 0 | 0 | 1015.598 | 2013.3 | 2013.3 | 2013.3 | 2013.3 | 71.584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Critical | 2.237 | 2336 |  | Gang - 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.08 | 2013.3 | 536.88 | 796.372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Non-Critical | 2.237 | 201 |  | Gang - 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449.637 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1001 mm ID 7mm thick |  | 3.185 | 90 |  | Gang - 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.65 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
8 | 1401 mm ID 9mm thick | Non-Critical | 4.455 | 9500 |  | Gang - 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1603.8 | 4276.8 | 4667.058 | 3608.55 | 3608.55 | 3608.55 | 3608.55 | 4651.02 | 5239.08 | 4811.4 | 2637.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
9 |  | Critical | 4.455 | 3500 |  | Gang - 5 |  |  | 0 | 320.76 | 1871.1 | 2779.92 | 2779.92 | 2779.92 | 2779.92 | 1336.5 | 944.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Non-Critical | 4.455 | 136 |  | Gang - 5 |  |  | 0 | 605.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1501 mm ID 9mm thick | Critical | 4.769 | 3229 |  | Gang - 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002.98 | 3376.452 | 4149.03 | 4950.222 | 920.417 | 0 | 0 | 0 | 0 | [18 empty] | 0
12 | 1601 mm ID 11mm thick | Non-Critical | 5.096 | 655 |  | Gang - 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917.28 | 1223.04 | 1197.56 | 0 | 0 | 0 | 0 | [18 empty] | 0
13 |  | Critical | 5.096 | 14000 |  | Gang - 6 |  |  | 0 | 458.64 | 1498.224 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1956.864 | 1039.584 | 978.432 | 1223.04 | 428.064 | 1223.04 | 1223.04 | 794.976 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 6731.816 | 0 | 0 | 0 | 0
14 |  |  | 5.096 |  |  | Gang - 7 |  |  | 0 | 0 | 1192.464 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 0 | 1528.8 | 1223.04 | 1223.04 | 1223.04 | 1223.04 | 1681.68 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 1987.44 | 6731.816 | 0 | 0 | 0 | 0
15 | 1801 mm ID 12mm thick | Non-Critical | 5.724 | 970 |  | Gang - 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927.288 | 1545.48 | 1545.48 | 1167.696 | 366.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
16 |  | Critical | 5.724 | 300 |  | Gang - 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309.096 | 1099.008 | 309.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Critical | 5.724 | 2369 |  | Gang - 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 865.4688 | 1648.512 | 1785.888 | 1785.888 | 1785.888 | 5689.656 | 0 | 0 | 0 | 0 | 0
18 | 1901 mm ID 14mm thick | Non-Critical | 6.038 | 10670 |  | Gang - 1 |  |  | 1956.312 | 3260.52 | 4709.64 | 5651.568 | 5651.568 | 5651.568 | 5651.568 | 4637.184 | 4637.184 | 4202.448 | 3260.52 | 3188.064 | 3260.52 | 3260.52 | 2528.7144 | 2626.53 | 289.824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
19 |  | Critical | 6.038 | 4000 |  | Gang - 3 |  |  | 0 | 0 | 0 | 1159.296 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1883.856 | 1811.4 | 1304.208 | 0 | 0 | 0 | 0 | 0 | 2173.68 | 3188.064 | 3188.064 | 1908.008 | 0 | 0 | 0 | 0 | 0
20 |  | Non-Critical | 6.038 | 1400 |  | Gang - 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.7328 | 3477.888 | 2289.6096 | 598.9696 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Critical | 6.038 | 760 |  | Gang - 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869.472 | 1449.12 | 2270.288 | 0 | 0 | 0 | 0 | 0 | 0
22 | 2101 mm ID 14mm thick | Non-Critical | 6.666 | 1006 |  | Gang - 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1871.8128 | 3119.688 | 1527.8472 | 186.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0
23 |  | Critical | 6.666 | 1260 |  | Gang - 4 |  |  | 0 | 359.964 | 1199.88 | 1559.844 | 1559.844 | 1559.844 | 1559.844 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 65382 |  |  | 0 | 0 | 3405.888 | 7421.724 | 12833.58 | 17071.698 | 17863.368 | 17863.368 | 17863.368 | 17890.6968 | 17852.236 | 17656.5732 | 12888.366 | 10789.57 | 10791.942 | 10780.494 | 12917.688 | 16966.89 | 18197.7336 | 18441.4456 | 17857.877 | 17869.622 | 15581.609 | 0 | 0 | 0 | 0 | 0
|  |  |  | Rate |  |  |  |  | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276 | 1070.276
|  |  |  | Amount |  |  |  |  | 0.36452 | 0.79433 | 1.3735 | 1.8271 | 1.9119 | 1.9119 | 1.9119 | 1.9148 | 1.9107 | 1.8897 | 1.3794 | 1.1548 | 1.155 | 1.1538 | 1.3825 | 1.8159 | 1.9477 | 1.9737 | 1.9113 | 1.9125 | 1.6677
S. No. | Pipe Dia |  |  | Bal. Work (in Rmt) |  | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL |  |  | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1116 | 1116 |  | Gang - 2 | [24 empty] | 1116 |  |  | 1116 | 2900 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.064728 | 0 | 0 | 0.064728
2 | 501 mm ID 6mm thick | Non-Critical | 598 | 598 |  | Gang - 2 | [23 empty] | 597 |  |  |  | 597 | 3850 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045969 | 0 | 0 | 0 | 0.045969
3 | 701 mm ID 6mm thick | Non-Critical | 9823 | 3200 |  | Gang - 2 | [5 empty] | 2130 |  |  |  |  | 832 | [16 empty] | 2962 | 4850 | 970 | 0 | 0 | 0 | 0 | 0 | 0.20661 | 0 | 0 | 0 | 0 | 0.080704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28731
4 |  | Critical |  | 4086 |  | Gang - 2 | [7 empty] | 1416 |  | 1152 | 240 | 818 | 700 | [14 empty] | 4326 | 4850 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13735 | 0 | 0.11174 | 0.02328 | 0.079346 | 0.0679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41962
5 |  | Critical |  | 2336 |  | Gang - 2 | [18 empty] | 766 | 698 | 872 | [6 empty] | 2336 | 4850 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.074302 | 0.067706 | 0.084584 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22659
6 |  | Non-Critical |  | 201 |  | Gang - 2 | [21 empty] | 201 | [5 empty] | 201 | 4850 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019497 | 0 | 0 | 0 | 0 | 0 | 0.019497
7 | 1001 mm ID 7mm thick |  | 90 | 90 |  | Gang - 2 | [21 empty] | 90 | [5 empty] | 90 | 9970 | 1994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017946 | 0 | 0 | 0 | 0 | 0 | 0.017946
8 | 1401 mm ID 9mm thick | Non-Critical | 13136 | 9500 |  | Gang - 5 | [10 empty] | 570 | 1644 | 1000 |  |  |  | 1700 | 1350 | 1404 | 1188 | 644 | [6 empty] | 9500 | 16250 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18525 | 0.5343 | 0.325 | 0 | 0 | 0 | 0.5525 | 0.43875 | 0.4563 | 0.3861 | 0.2093 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0875
9 |  | Critical |  | 3500 |  | Gang - 5 | [6 empty] | 1368 |  | 1040 | 832 | 260 | [16 empty] | 3500 | 16250 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4446 | 0 | 0.338 | 0.2704 | 0.0845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1375
10 |  | Non-Critical |  | 136 |  | Gang - 5 | [6 empty] | 136 | [20 empty] | 136 | 16250 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0442
11 | 1501 mm ID 9mm thick | Critical | 3229 | 3229 |  | Gang - 5 | [23 empty] | 1501 |  | 1728 |  | 3229 | 22495.5 | 4499.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67531 | 0 | 0.77744 | 0 | 1.4528
12 | 1601 mm ID 11mm thick | Non-Critical | 14655 | 655 |  | Gang - 7 | [25 empty] | 655 |  | 655 | 23496 | 4699.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3078 | 0 | 0.3078
13 |  | Critical |  | 14000 |  | Gang - 6 | [6 empty] | 540 | 540 | 780 | 780 | 390 | 630 | [5 empty] | 720 |  | 1020 |  |  | 1170 | 780 | 390 |  |  | 7740 | 23496 | 4699.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25376 | 0.25376 | 0.36654 | 0.36654 | 0.18327 | 0.29605 | 0 | 0 | 0 | 0 | 0 | 0.33834 | 0 | 0.47932 | 0 | 0 | 0.54981 | 0.36654 | 0.18327 | 0 | 0 | 3.6372
14 | [5 empty] | Gang - 7 | [7 empty] | 458 | 944 |  | 180 | 608 |  | 480 |  |  |  |  | 720 |  | 833 |  | 890 | 822 | 325 |  |  | 6260 | 23496 | 4699.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21522 | 0.4436 | 0 | 0.084586 | 0.28571 | 0 | 0.22556 | 0 | 0 | 0 | 0 | 0.33834 | 0 | 0.39144 | 0 | 0.41823 | 0.38627 | 0.15272 | 0 | 0 | 2.9417
15 | 1801 mm ID 12mm thick | Non-Critical | 3639 | 970 |  | Gang - 4 | [17 empty] | 970 | [9 empty] | 970 | 32000 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6208
16 |  | Critical |  | 300 |  | Gang - 4 | [20 empty] | 300 | [6 empty] | 300 | 32000 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.192 | 0 | 0 | 0 | 0 | 0 | 0 | 0.192
17 |  | Critical |  | 2369 |  | Gang - 4 | [20 empty] | 427 | 1073 |  |  | 869 |  |  | 2369 | 32000 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27328 | 0.68672 | 0 | 0 | 0.55616 | 0 | 0 | 1.5162
18 | 1901 mm ID 14mm thick | Non-Critical | 16830 | 10670 |  | Gang - 1 | [5 empty] | 1570 | 1656 | 662 | 936 | 936 | 322 |  |  |  |  | 1700 |  | 660 | 810 | 794 | 624 | [6 empty] | 10670 | 35000 | 7000 | 0 | 0 | 0 | 0 | 0 | 1.099 | 1.1592 | 0.4634 | 0.6552 | 0.6552 | 0.2254 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0.462 | 0.567 | 0.5558 | 0.4368 | 0 | 0 | 0 | 0 | 0 | 0 | 7.469
19 |  | Critical |  | 4000 |  | Gang - 3 | [7 empty] | 624 |  |  | 906 |  |  | 654 | [7 empty] | 936 | 880 |  |  |  |  | 4000 | 35000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4368 | 0 | 0 | 0.6342 | 0 | 0 | 0.4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6552 | 0.616 | 0 | 0 | 0 | 0 | 2.8
20 |  | Non-Critical |  | 1400 |  | Gang - 1 | [21 empty] | 1400 | [5 empty] | 1400 | 35000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0.98
21 |  | Critical |  | 760 |  | Gang - 1 | [22 empty] | 760 |  |  |  |  | 760 | 35000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.532 | 0 | 0 | 0 | 0 | 0.532
22 | 2101 mm ID 14mm thick | Non-Critical | 2266 | 1006 |  | Gang - 4 | [14 empty] | 1006 | [12 empty] | 1006 | 42900 | 8580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86315
23 |  | Critical |  | 1260 |  | Gang - 4 | [13 empty] | 566 | 694 | [12 empty] | 1260 | 42900 | 8580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48563 | 0.59545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0811
| Total |  | 65382 | 65382 |  |  | 0 | 0 | 0 | 0 | 0 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 1700 | 1700 | 1700 | 1700 | 1700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 2700 | 2383 | 0 | 65383 |  |  | 0 | 0 | 0 | 0 | 0 | 1.3056 | 1.9018 | 1.5065 | 1.8033 | 1.4039 | 1.5012 | 1.1954 | 0.3929 | 1.169 | 1.4586 | 1.19 | 0.5525 | 1.8599 | 1.4359 | 1.4889 | 1.5874 | 2.3594 | 2.116 | 1.4741 | 0.95688 | 1.0852 | 0 | 29.7445
[12 empty] | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 1700 | 1700 | 1700 | 1700 | 1700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 2700 | 2383
S. No. | Pipe Dia |  | L | B | D | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL | [7 empty] | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1 | 1 | 1.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 905.6 | 0 | 0 | 1785.6 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02457 | 0.025285 | 0 | 0 | 0.049854
2 | 501 mm ID 6mm thick | Non-Critical | 1 | 1.1 | 1.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757.35 | 359.04 | 0 | 0 | 0 | 1116.39 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021145 | 0.010024 | 0 | 0 | 0 | 0.03117
3 | 701 mm ID 6mm thick | Non-Critical | 1 | 1.3 | 1.9 |  | 0 | 0 | 0 | 2667.6 | 2667.6 | 2568.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7904 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0.07448 | 0.07448 | 0.071722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22068
4 |  | Critical | 1 | 1.3 | 1.9 |  | 0 | 0 | 0 | 0 | 0 | 652.08 | 1422.72 | 1422.72 | 1422.72 | 1422.72 | 1422.72 | 1422.72 | 904.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10092.42 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0.018206 | 0.039723 | 0.039723 | 0.039723 | 0.039723 | 0.039723 | 0.039723 | 0.02524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28178
5 |  | Critical | 1 | 1.3 | 1.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237.12 | 237.12 | 237.12 | 296.4 | 1304.16 | 1304.16 | 1304.16 | 849.68 | 0 | 0 | 0 | 0 | 0 | 0 | 5769.92 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0066204 | 0.0066204 | 0.0066204 | 0.0082756 | 0.036412 | 0.036412 | 0.036412 | 0.023723 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1611
6 |  | Non-Critical | 1 | 1.3 | 1.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496.47 | 0 | 0 | 0 | 0 | 0 | 496.47 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.013862 | 0 | 0 | 0 | 0 | 0 | 0.013862
7 | 1001 mm ID 7mm thick |  | 1 | 1.6 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 288 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.008041 | 0 | 0 | 0 | 0 | 0 | 0.008041
8 | 1401 mm ID 9mm thick | Non-Critical | 1 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3240 | 5616 | 3240 | 3240 | 3240 | 3240 | 3240 | 5616 | 4752 | 2576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090462 | 0.1568 | 0.090462 | 0.090462 | 0.090462 | 0.090462 | 0.090462 | 0.1568 | 0.13268 | 0.071923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.061
9 |  | Critical | 1 | 2 | 2 |  | 0 | 0 | 0 | 0 | 480 | 2496 | 2496 | 2496 | 2496 | 2496 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0.013402 | 0.069689 | 0.069689 | 0.069689 | 0.069689 | 0.069689 | 0.029037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39088
10 |  | Non-Critical | 1 | 2 | 2 |  | 0 | 0 | 0 | 0 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0.015189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015189
11 | 1501 mm ID 9mm thick | Critical | 1 | 2.1 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058.4 | 2293.2 | 2293.2 | 2293.2 | 2293.2 | 2293.2 | 1037.4 | 0 | 13561.8 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.029551 | 0.064027 | 0.064027 | 0.064027 | 0.064027 | 0.064027 | 0.028964 | 0 | 0.37865
12 | 1601 mm ID 11mm thick | Non-Critical | 1 | 2.2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112 | 770 | 0 | 2882 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.058968 | 0.021499 | 0 | 0.080466
13 |  | Critical | 1 | 2.2 | 2 |  | 0 | 0 | 0 | 0 | 660 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1056 | 1056 | 1056 | 1056 | 1056 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 0 | 0 | 31680 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0.018427 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.029484 | 0.029484 | 0.029484 | 0.029484 | 0.029484 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0 | 0 | 0.88451
14 |  |  | 1 | 2.2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1056 | 1056 | 1056 | 1056 | 1056 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 1716 | 616 | 0 | 0 | 29920 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.029484 | 0.029484 | 0.029484 | 0.029484 | 0.029484 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.047911 | 0.017199 | 0 | 0 | 0.83537
15 | 1801 mm ID 12mm thick | Non-Critical | 1 | 2.4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 1296 | 1296 | 768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4656 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.036185 | 0.036185 | 0.036185 | 0.021443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13
16 |  | Critical | 1 | 2.4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 864 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.008041 | 0.024123 | 0.008041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.040205
17 |  | Critical | 1 | 2.4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209.6 | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 1497.6 | 1176 | 0 | 0 | 11371.2 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033772 | 0.041813 | 0.041813 | 0.041813 | 0.041813 | 0.041813 | 0.041813 | 0.032834 | 0 | 0 | 0.31749
18 | 1901 mm ID 14mm thick | Non-Critical | 1 | 2.5 | 2 |  | 0 | 0 | 0 | 2700 | 2700 | 4680 | 4680 | 4680 | 4680 | 4680 | 4680 | 4680 | 2700 | 2700 | 2700 | 2700 | 2700 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53350 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0.075385 | 0.075385 | 0.13067 | 0.13067 | 0.13067 | 0.13067 | 0.13067 | 0.13067 | 0.13067 | 0.075385 | 0.075385 | 0.075385 | 0.075385 | 0.075385 | 0.047185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4895
19 |  | Critical | 1 | 2.5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 1560 | 0 | 0 | 0 | 0 | 0 | 1560 | 1560 | 1560 | 1560 | 1560 | 1280 | 0 | 0 | 0 | 0 | 20000 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0.043556 | 0.043556 | 0.043556 | 0.043556 | 0.043556 | 0.043556 | 0.043556 | 0 | 0 | 0 | 0 | 0 | 0.043556 | 0.043556 | 0.043556 | 0.043556 | 0.043556 | 0.035738 | 0 | 0 | 0 | 0 | 0.5584
20 |  | Non-Critical | 1 | 2.5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 2880 | 1240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08041 | 0.08041 | 0.034621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19544
21 |  | Critical | 1 | 2.5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 200 | 0 | 0 | 0 | 0 | 3800 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033504 | 0.033504 | 0.033504 | 0.005584 | 0 | 0 | 0 | 0 | 0.1061
22 | 2101 mm ID 14mm thick | Non-Critical | 1 | 2.7 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527.2 | 2527.2 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5432.4 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07056 | 0.07056 | 0.010554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15167
23 |  | Critical | 1 | 2.7 | 2 |  | 0 | 0 | 0 | 0 | 486 | 1263.6 | 1263.6 | 1263.6 | 1263.6 | 1263.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6804 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0 | 0.013569 | 0.03528 | 0.03528 | 0.03528 | 0.03528 | 0.03528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18997
| Total | [5 empty] | 0 | 0 | 0 | 5367.6 | 7537.6 | 16652.48 | 14854.32 | 14854.32 | 14854.32 | 14854.32 | 17901.92 | 19237.92 | 10630.02 | 9585.12 | 9585.12 | 9345.12 | 9212.4 | 17979.76 | 15425.76 | 13868.16 | 10832.48 | 10767.27 | 9460.15 | 8461.84 | 8818.8 | 1807.4 | 0 | 271894.2 | [6 empty] | 279.2024 | 0 | 0 | 0 | 0.14986 | 0.21045 | 0.46494 | 0.41474 | 0.41474 | 0.41474 | 0.41474 | 0.49983 | 0.53713 | 0.29679 | 0.26762 | 0.26762 | 0.26092 | 0.25721 | 0.502 | 0.43069 | 0.3872 | 0.30245 | 0.30062 | 0.26413 | 0.23626 | 0.24622 | 0.050463 | 0 | 7.5914 | 4.6813 | 2.91
S. No. | Pipe Dia |  | L | B | D | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL | [7 empty] | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 401 mm ID 4mm thick | Non-Critical | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 501 mm ID 6mm thick | Non-Critical | 1 | 1.1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 701 mm ID 6mm thick | Non-Critical | 1 | 1.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Critical | 1 | 1.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Critical | 1 | 1.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Non-Critical | 1 | 1.3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1001 mm ID 7mm thick |  | 1 | 1.6 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8 | 0 | 0 | 0 | 0 | 0 | 28.8 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00097833 | 0 | 0 | 0 | 0 | 0 | 0.00097833
8 | 1401 mm ID 9mm thick | Non-Critical | 1 | 2 | 0.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 972 | 1684.8 | 972 | 972 | 972 | 972 | 972 | 1684.8 | 1425.6 | 772.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11400 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033018 | 0.057232 | 0.033018 | 0.033018 | 0.033018 | 0.033018 | 0.033018 | 0.057232 | 0.048427 | 0.026252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38725
9 |  | Critical | 1 | 2 | 0.6 |  | 0 | 0 | 0 | 0 | 144 | 748.8 | 748.8 | 748.8 | 748.8 | 748.8 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0.0048916 | 0.025436 | 0.025436 | 0.025436 | 0.025436 | 0.025436 | 0.010599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14267
10 |  | Non-Critical | 1 | 2 | 0.6 |  | 0 | 0 | 0 | 0 | 163.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.2 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0.0055438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0055438
11 | 1501 mm ID 9mm thick | Critical | 1 | 2.1 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.44 | 802.62 | 802.62 | 802.62 | 802.62 | 802.62 | 363.09 | 0 | 4746.63 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012584 | 0.027265 | 0.027265 | 0.027265 | 0.027265 | 0.027265 | 0.012334 | 0 | 0.16124
12 | 1601 mm ID 11mm thick | Non-Critical | 1 | 2.2 | 0.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844.8 | 308 | 0 | 1152.8 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028698 | 0.010463 | 0 | 0.03916
13 |  | Critical | 1 | 2.2 | 0.8 |  | 0 | 0 | 0 | 0 | 264 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 422.4 | 422.4 | 422.4 | 422.4 | 422.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 0 | 0 | 12672 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0.008968 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.014349 | 0.014349 | 0.014349 | 0.014349 | 0.014349 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0 | 0 | 0.43046
14 |  |  | 1 | 2.2 | 0.8 |  | 0 | 0 | 0 | 0 | 0 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 422.4 | 422.4 | 422.4 | 422.4 | 422.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 686.4 | 246.4 | 0 | 0 | 11968 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.014349 | 0.014349 | 0.014349 | 0.014349 | 0.014349 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.023317 | 0.0083701 | 0 | 0 | 0.40655
15 | 1801 mm ID 12mm thick | Non-Critical | 1 | 2.4 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648 | 648 | 648 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2328 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.022012 | 0.022012 | 0.022012 | 0.013044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079081
16 |  | Critical | 1 | 2.4 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 432 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0048916 | 0.014675 | 0.0048916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.024458
17 |  | Critical | 1 | 2.4 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604.8 | 748.8 | 748.8 | 748.8 | 748.8 | 748.8 | 748.8 | 588 | 0 | 0 | 5685.6 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020545 | 0.025436 | 0.025436 | 0.025436 | 0.025436 | 0.025436 | 0.025436 | 0.019974 | 0 | 0 | 0.19314
18 | 1901 mm ID 14mm thick | Non-Critical | 1 | 2.5 | 1.1 |  | 0 | 0 | 0 | 1485 | 1485 | 2574 | 2574 | 2574 | 2574 | 2574 | 2574 | 2574 | 1485 | 1485 | 1485 | 1485 | 1485 | 929.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29342.5 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0.050445 | 0.050445 | 0.087438 | 0.087438 | 0.087438 | 0.087438 | 0.087438 | 0.087438 | 0.087438 | 0.050445 | 0.050445 | 0.050445 | 0.050445 | 0.050445 | 0.031575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99675
19 |  | Critical | 1 | 2.5 | 1.1 |  | 0 | 0 | 0 | 0 | 0 | 858 | 858 | 858 | 858 | 858 | 858 | 858 | 0 | 0 | 0 | 0 | 0 | 858 | 858 | 858 | 858 | 858 | 704 | 0 | 0 | 0 | 0 | 11000 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0.029146 | 0.029146 | 0.029146 | 0.029146 | 0.029146 | 0.029146 | 0.029146 | 0 | 0 | 0 | 0 | 0 | 0.029146 | 0.029146 | 0.029146 | 0.029146 | 0.029146 | 0.023915 | 0 | 0 | 0 | 0 | 0.37367
20 |  | Non-Critical | 1 | 2.5 | 1.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584 | 1584 | 682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053808 | 0.053808 | 0.023167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13078
21 |  | Critical | 1 | 2.5 | 1.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 660 | 660 | 110 | 0 | 0 | 0 | 0 | 2090 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02242 | 0.02242 | 0.02242 | 0.0037367 | 0 | 0 | 0 | 0 | 0.070997
22 | 2101 mm ID 14mm thick | Non-Critical | 1 | 2.7 | 1.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642.68 | 1642.68 | 245.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531.06 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055801 | 0.055801 | 0.0083463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11995
23 |  | Critical | 1 | 2.7 | 1.3 |  | 0 | 0 | 0 | 0 | 315.9 | 821.34 | 821.34 | 821.34 | 821.34 | 821.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4422.6 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0 | 0.010731 | 0.027901 | 0.027901 | 0.027901 | 0.027901 | 0.027901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15023
| Total | [5 empty] | 0 | 0 | 0 | 1485 | 2372.1 | 6374.94 | 6374.94 | 6374.94 | 6374.94 | 6374.94 | 7731.48 | 8132.28 | 4195.5 | 3949.8 | 3949.8 | 3829.8 | 3733.8 | 7177.9 | 5989.2 | 5464.84 | 4442.22 | 4471.02 | 3738.22 | 2924.22 | 3168.22 | 671.09 | 0 | 109301.19 | [6 empty] | 339.6962 | 0 | 0 | 0 | 0.050445 | 0.080579 | 0.21655 | 0.21655 | 0.21655 | 0.21655 | 0.21655 | 0.26264 | 0.27625 | 0.14252 | 0.13417 | 0.13417 | 0.1301 | 0.12684 | 0.24383 | 0.20345 | 0.18564 | 0.1509 | 0.15188 | 0.12699 | 0.099335 | 0.10762 | 0.022797 | 0 | 3.7129 | 2.5431 | 1.1698
[42 empty] | 0 | 0 | 0 | 0.20031 | 0.29103 | 0.6815 | 0.63129 | 0.63129 | 0.63129 | 0.63129 | 0.76246 | 0.81338 | 0.43931 | 0.40179 | 0.40179 | 0.39101 | 0.38405 | 0.74583 | 0.63414 | 0.57284 | 0.45335 | 0.4525 | 0.39112 | 0.33559 | 0.35385 | 0.07326 | 0 | 11.3043
[65 empty] | 1.34 | 1.5 | 1.5 |  | 4.34
[47 empty] | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.83 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 19.03
[45 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.99
[46 empty] | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.39 | 0.4 | 0.4 | 0.4 | 0.4 | 0.36 |  | 8.11
[47 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.43 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 5.5 | 6 |  | 20.33
[52 empty] | 0.36 | 0.09 | 0.28 | 0.32 | 0.32 | 0.31 | 0.32 | 0.05 | 0.17 | 0.17 | 0.21 | 0.2 | 0.29 | 0.34 | 0.33 | 1.43 |  | 5.19
[45 empty] | 0.24031 | 0.69103 | 2.2815 | 2.2313 | 2.2313 | 2.2313 | 2.2313 | 2.7225 | 2.5334 | 2.4193 | 2.4218 | 2.4518 | 2.601 | 2.604 | 2.6958 | 2.7041 | 2.6528 | 2.6033 | 2.6025 | 2.6311 | 3.9656 | 9.1338 | 10.4133 |  | 69.2943

## to client - Supply TO MAIL
M/s. MEGHA ENGINEERING & INFRASTRUCTURE LIMITED
City Trunk Main Along Western Route CP-10 Under JICA Loan ID P266
WORK DONE VALUE
All Values in Crs
S. No. | Pipe Dia | Scope | Start Date | Finish Date | Duration in days | Qty / value |  | Mar'20 | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Supply of Materials
1 | MS Bare Pipe Supply | 65383 | 2020-09-01 | 2021-12-30 | 485 | Qty in mtrs | for the Month |  | 6: 6972; 7: 3642; 8: 3642; 9: 3642; 10: 5650; 11: 5466; 12: 4746; 13: 4026; 14: 3240; 15: 3240; 16: 3240; 17: 3240; 18: 3150; 19: 3402; 20: 3660; 21: 4425
2 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 6972 | 10614 | 14256 | 17898 | 23548 | 29014 | 33760 | 37786 | 41026 | 44266 | 47506 | 50746 | 53896 | 57298 | 60958 | 65383 | 65383 | 65383 | 65383 | 65383 | 65383 | 65383 | 65383 | 65383 | 65383
3 | [5 empty] | Value | for the Month |  | 6: 9.3511; 7: 10.1558; 8: 10.1558; 9: 10.1558; 10: 9.8732; 11: 9.8792; 12: 9.53; 13: 9.1808; 14: 9.9479; 15: 9.9479; 16: 9.9479; 17: 9.9479; 18: 8.3121; 19: 8.2039; 20: 7.9818; 21: 6.1513
4 | [6 empty] | Cumulative | [6 empty] | 9.3511 | 19.5069 | 29.6627 | 39.8185 | 49.6918 | 59.571 | 69.101 | 78.2818 | 88.2297 | 98.1776 | 108.1255 | 118.0734 | 126.3854 | 134.5893 | 142.5711 | 148.7224 | 148.7224 | 148.7224 | 148.7224 | 148.7224 | 148.7224 | 148.7224 | 148.7224 | 148.7224 | 148.7224
5 | MS Coated Pipes Supply | 65383 | 2020-09-03 | 2022-05-27 | 631 | Qty in mtrs | for the Month | [6 empty] | 972 | 1972 | 2964 | 3636 | 3786 | 3786 | 3786 | 3784.8 | 3796 | 3826.8 | 2584 | 2288 | 2088 | 2086 | 2499.6 | 3255 | 3523.2 | 4375.2 | 3857 | 3445 | 3072 | 0 | 0
6 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 972 | 2944 | 5908 | 9544 | 13330 | 17116 | 20902 | 24686.8 | 28482.8 | 32309.6 | 34893.6 | 37181.6 | 39269.6 | 41355.6 | 43855.2 | 47110.2 | 50633.4 | 55008.6 | 58865.6 | 62310.6 | 65382.6 | 65382.6 | 65382.6 | 65382.6 | 65382.6
7 | [5 empty] | Value | for the Month | [6 empty] | 0.36452 | 0.79433 | 1.3735 | 1.8271 | 1.9119 | 1.9119 | 1.9119 | 1.9148 | 1.9107 | 1.8897 | 1.3794 | 1.1548 | 1.155 | 1.1538 | 1.3825 | 1.8159 | 1.9477 | 1.9737 | 1.9113 | 1.9125 | 1.6677 | 0.245
8 | [6 empty] | Cumulative | [6 empty] | 0.36452 | 1.1589 | 2.5324 | 4.3595 | 6.2714 | 8.1833 | 10.0952 | 12.01 | 13.9206 | 15.8104 | 17.1898 | 18.3446 | 19.4996 | 20.6534 | 22.036 | 23.8519 | 25.7996 | 27.7733 | 29.6846 | 31.5971 | 33.2648 | 33.5098 | 33.5098 | 33.5098 | 33.5098
9 | Valves Delivery at site | 160 | 2020-06-01 | 2021-02-28 | 272 | Qty in Nos | for the Month |  | 15: 19; 16: 19; 17: 19; 18: 0; 19: 0; 20: 0; 21: 50; 22: 47; 23: 6
10 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 38 | 57 | 57 | 57 | 57 | 107 | 154 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
11 | [5 empty] | Value | for the Month |  | 15: 0.105; 16: 0.105; 17: 2.2725; 21: 0.12142; 22: 0.11413; 23: 0.2975
12 | [6 empty] | Cumulative | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0.105 | 0.21 | 2.4825 | 2.4825 | 2.4825 | 2.4825 | 2.6039 | 2.7181 | 3.0156 | 3.0156 | 3.0156 | 3.0156 | 3.0156 | 3.0156 | 3.0156 | 3.0156
Execution of works
13 | MS Pipeline Laying & Jointing | 65383 | 2020-09-03 | 2022-08-15 | 711 | Qty in mtrs | for the Month | [7 empty] | 1620 | 2116 | 4190 | 3462 | 3462 | 3462 | 3462 | 4142 | 4476 | 2536 | 2196 | 2196 | 2146 | 2130 | 4250 | 3696 | 3316 | 2534 | 2481 | 2339 | 2380 | 2367 | 424
14 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 3736 | 7926 | 11388 | 14850 | 18312 | 21774 | 25916 | 30392 | 32928 | 35124 | 37320 | 39466 | 41596 | 45846 | 49542 | 52858 | 55392 | 57873 | 60212 | 62592 | 64959 | 65383 | 65383
[6 empty] | Laying & Jointing | [8 empty] | 1.931 | 2.8547 | 7.0808 | 6.7983 | 6.7983 | 6.7983 | 6.7983 | 8.1812 | 8.6154 | 4.5407 | 4.1957 | 4.1957 | 4.0677 | 3.9746 | 7.7277 | 6.5005 | 6.0004 | 4.9265 | 4.9428 | 4.201 | 3.4342 | 3.6396 | 0.77346 | 0
[6 empty] | Specials Fab. | [8 empty] | 0.29955 | 0.39126 | 0.77476 | 0.64015 | 0.64015 | 0.64015 | 0.64015 | 0.76589 | 0.82765 | 0.46893 | 0.40606 | 0.40606 | 0.39681 | 0.39385 | 0.78586 | 0.68342 | 0.61315 | 0.46856 | 0.45876 | 0.4325 | 0.44008 | 0.43768 | 0.078031
[6 empty] | EW Excavation | [8 empty] | 0.24031 | 0.69103 | 2.2815 | 2.2313 | 2.2313 | 2.2313 | 2.2313 | 2.7225 | 2.5334 | 2.4193 | 2.4218 | 2.4518 | 2.601 | 2.604 | 2.6958 | 2.7041 | 2.6528 | 2.6033 | 2.6025 | 2.6311 | 3.9656 | 5.1338 | 6.4133 | 8
15 | [5 empty] | Value | for the Month | [7 empty] | 2.4709 | 3.937 | 10.137 | 9.6698 | 9.6698 | 9.6698 | 9.6698 | 11.6696 | 11.9764 | 7.4289 | 7.0235 | 7.0535 | 7.0655 | 6.9725 | 11.2094 | 9.8881 | 9.2664 | 7.9984 | 8.0041 | 7.2646 | 7.8399 | 9.2111 | 7.2647 | 8
16 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.4709 | 6.4079 | 16.5449 | 26.2147 | 35.8845 | 45.5542 | 55.224 | 66.8936 | 78.87 | 86.2989 | 93.3225 | 100.376 | 107.4415 | 114.414 | 125.6235 | 135.5116 | 144.778 | 152.7764 | 160.7805 | 168.0452 | 175.8851 | 185.0962 | 192.3609 | 200.3609
17 | MS Pipes Hydro Testing | 65383 | 2020-12-01 | 2022-08-30 | 637 | Qty in mtrs | for the Month | [9 empty] | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 1700 | 1700 | 1700 | 1700 | 1700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 3700 | 2700 | 2383
18 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 7400 | 11100 | 14800 | 18500 | 22200 | 25900 | 27600 | 29300 | 31000 | 32700 | 34400 | 38100 | 41800 | 45500 | 49200 | 52900 | 56600 | 60300 | 63000 | 65383 | 65383
19 | [5 empty] | Value | for the Month | [9 empty] | 1.3056 | 1.9018 | 1.5065 | 1.8033 | 1.4039 | 1.5012 | 1.1954 | 0.3929 | 1.169 | 1.4586 | 1.19 | 0.5525 | 1.8599 | 1.4359 | 1.4889 | 1.5874 | 2.3594 | 2.116 | 1.4741 | 0.95688 | 1.0852
20 | [6 empty] | Cumulative | [7 empty] | 0 | 0 | 1.3056 | 3.2074 | 4.7139 | 6.5172 | 7.9211 | 9.4223 | 10.6177 | 11.0106 | 12.1796 | 13.6382 | 14.8282 | 15.3807 | 17.2406 | 18.6765 | 20.1655 | 21.7529 | 24.1122 | 26.2283 | 27.7024 | 28.6593 | 29.7445 | 29.7445
21 | Fixing / Installation of Valves | 160 | 2021-09-01 | 2022-06-28 | 300 | Qty in Nos | for the Month |  | 18: 8; 19: 8; 20: 5; 21: 7; 22: 7; 23: 7; 24: 32; 25: 32; 26: 27; 27: 27
22 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 21 | 28 | 35 | 42 | 74 | 106 | 133 | 160 | 160 | 160 | 160
23 | [5 empty] | Value | for the Month |  | 18: 0.39; 19: 0.39; 20: 0.24375; 21: 0.34125; 22: 0.34125; 23: 0.34125; 24: 0.43178; 25: 0.43178; 26: 0.47371; 27: 0.46371
24 | [6 empty] | Cumulative |  | 15: 0; 16: 0; 17: 0; 18: 0.39; 19: 0.78; 20: 1.0237; 21: 1.365; 22: 1.7062; 23: 2.0475; 24: 2.4793; 25: 2.9111; 26: 3.3848; 27: 3.8485; 28: 3.8485; 29: 3.8485; 30: 3.8485
25 | Construction of Valve Chambers | 160 | 2021-04-01 | 2022-06-30 | 455 | Qty in Nos | for the Month |  | 13: 16; 14: 16; 15: 16; 16: 6; 17: 6; 18: 6; 19: 6; 20: 8; 21: 12; 22: 12; 23: 12; 24: 12; 25: 12; 26: 12; 27: 8
26 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 32 | 48 | 54 | 60 | 66 | 72 | 80 | 92 | 104 | 116 | 128 | 140 | 152 | 160 | 160 | 160 | 160
27 | [5 empty] | Value | for the Month |  | 13: 8.818; 14: 8.818; 15: 8.818; 16: 3.3068; 17: 3.3068; 18: 3.3068; 19: 3.3068; 20: 4.409; 21: 6.6135; 22: 6.6135; 23: 6.6135; 24: 6.6135; 25: 6.6135; 26: 6.6135; 27: 4.409
28 | [6 empty] | Cumulative | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8.818 | 17.636 | 26.454 | 29.7608 | 33.0675 | 36.3743 | 39.681 | 44.09 | 50.7035 | 57.317 | 63.9305 | 70.544 | 77.1575 | 83.771 | 88.18 | 88.18 | 88.18 | 88.18
29 | Construction of Pipe Bridge | 1 | 2020-12-14 | 2022-04-17 | 489 | Qty in Nos | for the Month |  | 9: 0.05; 10: 0.1; 11: 0.1; 12: 0.1; 13: 0.1; 14: 0.1; 15: 0.1; 16: 0.1; 17: 0.1; 18: 0.1; 25: 0.05
30 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.15 | 0.25 | 0.35 | 0.45 | 0.55 | 0.65 | 0.75 | 0.85 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 1 | 1 | 1 | 1 | 1 | 1
31 | [5 empty] | Value | for the Month |  | 9: 0.07525; 10: 0.1505; 11: 0.1505; 12: 0.1505; 13: 0.1505; 14: 0.1505; 15: 0.1505; 16: 0.1505; 17: 0.1505; 18: 0.1505; 25: 0.07525
32 | [6 empty] | Cumulative | [7 empty] | 0 | 0 | 0.07525 | 0.22575 | 0.37625 | 0.52675 | 0.67725 | 0.82775 | 0.97825 | 1.1287 | 1.2792 | 1.4298 | 1.4298 | 1.4298 | 1.4298 | 1.4298 | 1.4298 | 1.4298 | 1.505 | 1.505 | 1.505 | 1.505 | 1.505 | 1.505
33 | Pipeline Crossings (Trenchless) | 720 | 2021-03-24 | 2022-07-31 | 494 | Qty in Nos | for the Month |  | 13: 37.5; 14: 77.5; 15: 77.5; 16: 77.5; 21: 30; 22: 65; 23: 65; 24: 65; 25: 65; 26: 65; 27: 65; 28: 30
34 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 | 115 | 192.5 | 270 | 270 | 270 | 270 | 270 | 300 | 365 | 430 | 495 | 560 | 625 | 690 | 720 | 720 | 720
35 | [5 empty] | Value | for the Month |  | 13: 0.61958; 14: 1.2805; 15: 1.2805; 16: 1.2805; 21: 0.49567; 22: 1.0739; 23: 1.0739; 24: 1.0739; 25: 1.0739; 26: 1.0739; 27: 1.0739; 28: 0.49567
36 | [6 empty] | Cumulative | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.61958 | 1.9001 | 3.1805 | 4.461 | 4.461 | 4.461 | 4.461 | 4.461 | 4.9567 | 6.0306 | 7.1046 | 8.1785 | 9.2524 | 10.3264 | 11.4003 | 11.896 | 11.896 | 11.896
37 | Commissioning | 65383 | 2022-08-31 | 2022-09-30 | 30 |  | for the Month |  | 30: 65383
38 | [6 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65383
| GRAND TOTAL | [5 empty] | for the Month |  | 0 | 0 | 0 | 0 | 0 | 9.7156 | 13.421 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 31.7573 | 35.2783 | 35.3635 | 23.9919 | 25.025 | 21.8265 | 21.3099 | 21.5421 | 28.6084 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 8.35 | 8
[7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 9.7156 | 23.1367 | 38.603 | 62.1038 | 85.611 | 108.7288 | 131.7943 | 163.5517 | 198.83 | 234.1934 | 258.1853 | 283.2103 | 305.0367 | 326.3467 | 347.8888 | 376.4972 | 397.9117 | 418.967 | 438.5833 | 459.0538 | 478.2633 | 493.7689 | 504.4326 | 512.7826 | 520.7826

## Statement - 2
M/s. MEGHA ENGINEERING & INFRASTRUCTURE LIMITED
City Trunk Main Along Western Route CP-10 Under JICA Loan ID P266
CASH FLOW
Sl.No | Description | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
1 | WORK DONE - GROSS | 0 | 0 | 0 | 0 | 0 | 9.7156 | 13.421 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 31.7573 | 35.2783 | 35.3635 | 23.9919 | 25.025 | 21.8265 | 21.3099 | 21.5421 | 28.6084 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 8.35 | 8 | 0
2 | CASH FLOW - PAYMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1367 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 31.7573 | 35.2783 | 35.3635 | 23.9919 | 25.025 | 21.8265 | 21.3099 | 21.5421 | 28.6084 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 0 | 16.35 | 26.04
3 | MOBILIZATION ADVANCE 10% |  |  | 26.0966 |  | 26.0966
4
| DEDUCTIONS MOBILIZATION ADVANCE 10% | [13 empty] | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35 | 4.35
5 | CASH FLOW - GROSS (PAYMENT) | 0 | 0 | 26.0966 | 0 | 26.0966 | 0 | 0 | 23.1367 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 27.4073 | 30.9283 | 31.0135 | 19.6419 | 20.675 | 17.4765 | 16.9599 | 17.1921 | 24.2584 | 17.0645 | 16.7053 | 15.2664 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 0 | 16.35 | 26.04
6
| DEDUCTIONS IT 2% | 0 | 0 | 0.52193 | 0
| DEDUCTIONS IT 1.5% |  |  |  |  | 0.39145 | 0 | 0 | 0.34705 | 0.23199 | 0.35251 | 0.35261 | 0.34677 | 0.34598 | 0.41111 | 0.46392 | 0.4652 | 0.29463 | 0.31012 | 0.26215 | 0.2544 | 0.25788 | 0.36388 | 0.25597 | 0.25058 | 0.229 | 0.30706 | 0.28814 | 0.23258 | 0.15995 | 0 | 0.24525
| DEDUCTIONS CGST 1% | 0 | 0 | 0.26097 | 0 | 0.26097 | 0 | 0 | 0.23137 | 0.15466 | 0.23501 | 0.23507 | 0.23118 | 0.23065 | 0.27407 | 0.30928 | 0.31013 | 0.19642 | 0.20675 | 0.17476 | 0.1696 | 0.17192 | 0.24258 | 0.17065 | 0.16705 | 0.15266 | 0.2047 | 0.19209 | 0.15506 | 0.10664 | 0 | 0.1635
| DEDUCTIONS SGST 1% | 0 | 0 | 0.26097 | 0 | 0.26097 | 0 | 0 | 0.23137 | 0.15466 | 0.23501 | 0.23507 | 0.23118 | 0.23065 | 0.27407 | 0.30928 | 0.31013 | 0.19642 | 0.20675 | 0.17476 | 0.1696 | 0.17192 | 0.24258 | 0.17065 | 0.16705 | 0.15266 | 0.2047 | 0.19209 | 0.15506 | 0.10664 | 0 | 0.1635
| DEDUCTIONS RETENTION 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1568 | 0.77332 | 1.175 | 1.1754 | 1.1559 | 1.1533 | 1.5879 | 1.7639 | 1.7682 | 1.1996 | 1.2512 | 1.0913 | 1.0655 | 1.0771 | 1.4304 | 1.0707 | 1.0528 | 0.98082 | 1.0235 | 0.96047 | 0.77528 | 0.53318 | 0 | 0.8175
7 |  | 0 | 0 | 25.0527 | 0 | 25.1832 | 0 | 0 | 21.1701 | 14.1517 | 21.5033 | 21.509 | 21.1529 | 21.1049 | 24.8602 | 28.0819 | 28.1598 | 17.7548 | 18.7001 | 15.7735 | 15.3009 | 15.5133 | 21.9789 | 15.3965 | 15.0678 | 13.7512 | 18.7305 | 17.5767 | 14.1877 | 9.7573 | 0 | 14.9602 | 26.0391
[15 empty] | 25.8195 | 0.51639
520.78
26.039

## S-Curve All
[8 empty] | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
WORK DONE - GROSS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 9.7156 | 13.421 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 31.7573 | 35.2783 | 35.3635 | 23.9919 | 25.025 | 21.8265 | 21.3099 | 21.5421 | 28.6084 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 8.35 | 8 | 0 | 0
CASH FLOW - GROSS (PAYMENT) | [7 empty] | 0 | 0 | 26.0966 | 0 | 26.0966 | 0 | 0 | 23.1367 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 27.4073 | 30.9283 | 31.0135 | 19.6419 | 20.675 | 17.4765 | 16.9599 | 17.1921 | 24.2584 | 17.0645 | 16.7053 | 15.2664 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 0 | 16.35 | 26.04
CASH FLOW - NET (PAYMENT) | [7 empty] | 0 | 0 | 25.0527 | 0 | 25.1832 | 0 | 0 | 21.1701 | 14.1517 | 21.5033 | 21.509 | 21.1529 | 21.1049 | 24.8602 | 28.0819 | 28.1598 | 17.7548 | 18.7001 | 15.7735 | 15.3009 | 15.5133 | 21.9789 | 15.3965 | 15.0678 | 13.7512 | 18.7305 | 17.5767 | 14.1877 | 9.7573 | 0 | 14.9602 | 26.0391
|  | WORK DONE VALUE | CASH FLOW - GROSS VALUE | CASH FLOW - NET VALUE | WORK DONE - GROSS | CASH FLOW - GROSS (PAYMENT) | CASH FLOW - NET (PAYMENT)
| 2020-04-01 | 0 | 0 | 0 | 0 | 0 | 0
| 2020-05-01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | City Trunk Main along Western Route - CP10 (Turnkey Basis) - Under JICA Loan ID - P266
| 2020-06-01 | 0 | 26.0966 | 25.0527 | 0 | 26.0966 | 25.0527
| 2020-07-01 | 0 | 26.0966 | 25.0527 | 0 | 0 | 0
| 2020-08-01 | 0 | 52.1931 | 50.2359 | 0 | 26.0966 | 25.1832
| 2020-09-01 | 9.7156 | 52.1931 | 50.2359 | 9.7156 | 0 | 0
| 2020-10-01 | 23.1367 | 52.1931 | 50.2359 | 13.421 | 0 | 0
| 2020-11-01 | 38.603 | 75.3298 | 71.4059 | 15.4663 | 23.1367 | 21.1701
| 2020-12-01 | 62.1038 | 90.7961 | 85.5576 | 23.5009 | 15.4663 | 14.1517
| 2021-01-01 | 85.611 | 114.2969 | 107.0609 | 23.5071 | 23.5009 | 21.5033
| 2021-02-01 | 108.7288 | 137.8041 | 128.5699 | 23.1179 | 23.5071 | 21.509
| 2021-03-01 | 131.7943 | 160.922 | 149.7228 | 23.0655 | 23.1179 | 21.1529
| 2021-04-01 | 163.5517 | 183.9874 | 170.8277 | 31.7573 | 23.0655 | 21.1049
| 2021-05-01 | 198.83 | 211.3948 | 195.6879 | 35.2783 | 27.4073 | 24.8602
| 2021-06-01 | 234.1934 | 242.3231 | 223.7698 | 35.3635 | 30.9283 | 28.0819
| 2021-07-01 | 258.1853 | 273.3365 | 251.9296 | 23.9919 | 31.0135 | 28.1598
| 2021-08-01 | 283.2103 | 292.9784 | 269.6844 | 25.025 | 19.6419 | 17.7548
| 2021-09-01 | 305.0367 | 313.6534 | 288.3845 | 21.8265 | 20.675 | 18.7001
| 2021-10-01 | 326.3467 | 331.1299 | 304.158 | 21.3099 | 17.4765 | 15.7735
| 2021-11-01 | 347.8888 | 348.0898 | 319.4588 | 21.5421 | 16.9599 | 15.3009
| 2021-12-01 | 376.4972 | 365.2819 | 334.9721 | 28.6084 | 17.1921 | 15.5133
| 2022-01-01 | 397.9117 | 389.5403 | 356.951 | 21.4145 | 24.2584 | 21.9789
| 2022-02-01 | 418.967 | 406.6048 | 372.3476 | 21.0553 | 17.0645 | 15.3965
| 2022-03-02 | 438.5833 | 423.3101 | 387.4154 | 19.6164 | 16.7053 | 15.0678
| 2022-04-01 | 459.0538 | 438.5765 | 401.1666 | 20.4705 | 15.2664 | 13.7512
| 2022-05-02 | 478.2633 | 459.0469 | 419.8971 | 19.2095 | 20.4705 | 18.7305
| 2022-06-01 | 493.7689 | 478.2564 | 437.4738 | 15.5056 | 19.2095 | 17.5767
| 2022-07-02 | 504.4326 | 493.7621 | 451.6615 | 10.6637 | 15.5056 | 14.1877
| 2022-08-02 | 512.7826 | 504.4257 | 461.4187 | 8.35 | 10.6637 | 9.7573
| 2022-09-01 | 520.7826 | 504.4257 | 461.4187 | 8 | 0 | 0
| 2022-10-01 | 520.7826 | 520.7757 | 476.3789 | 0 | 16.35 | 14.9602
| 2022-11-01 | 520.7826 | 546.8157 | 502.4181 | 0 | 26.04 | 26.0391

## S-Curve - WD
|  |  | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
WORK DONE - GROSS |  |  | 0 | 0 | 0 | 0 | 0 | 9.7156 | 13.421 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 31.7573 | 35.2783 | 35.3635 | 23.9919 | 25.025 | 21.8265 | 21.3099 | 21.5421 | 28.6084 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 8.35 | 8 | 0 | 0
CASH FLOW - GROSS (PAYMENT) |  |  | 0 | 0 | 26.0966 | 0 | 26.0966 | 0 | 0 | 23.1367 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 27.4073 | 30.9283 | 31.0135 | 19.6419 | 20.675 | 17.4765 | 16.9599 | 17.1921 | 24.2584 | 17.0645 | 16.7053 | 15.2664 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 0 | 16.35 | 26.04
CASH FLOW - NET (PAYMENT) |  |  | 0 | 0 | 25.0527 | 0 | 25.1832 | 0 | 0 | 21.1701 | 14.1517 | 21.5033 | 21.509 | 21.1529 | 21.1049 | 24.8602 | 28.0819 | 28.1598 | 17.7548 | 18.7001 | 15.7735 | 15.3009 | 15.5133 | 21.9789 | 15.3965 | 15.0678 | 13.7512 | 18.7305 | 17.5767 | 14.1877 | 9.7573 | 0 | 14.9602 | 26.0391
WORK DONE VALUE
| 2020-04-01 | 0
| 2020-05-01 | 0 |  |  | City Trunk Main along Western Route - CP10 (Turnkey Basis) - Under JICA Loan ID - P266
| 2020-06-01 | 0
| 2020-07-01 | 0
| 2020-08-01 | 0
| 2020-09-01 | 9.7156
| 2020-10-01 | 23.1367
| 2020-11-01 | 38.603
| 2020-12-01 | 62.1038
| 2021-01-01 | 85.611
| 2021-02-01 | 108.7288
| 2021-03-01 | 131.7943
| 2021-04-01 | 163.5517
| 2021-05-01 | 198.83
| 2021-06-01 | 234.1934
| 2021-07-01 | 258.1853
| 2021-08-01 | 283.2103
| 2021-09-01 | 305.0367
| 2021-10-01 | 326.3467
| 2021-11-01 | 347.8888
| 2021-12-01 | 376.4972
| 2022-01-01 | 397.9117
| 2022-02-01 | 418.967
| 2022-03-02 | 438.5833
| 2022-04-01 | 459.0538
| 2022-05-02 | 478.2633
| 2022-06-01 | 493.7689
| 2022-07-02 | 504.4326
| 2022-08-02 | 512.7826
| 2022-09-01 | 520.7826
| 2022-10-01 | 520.7826
| 2022-11-01 | 520.7826

## S-Curve - CASH FLOW GROSS
CASH FLOW - GROSS VALUE
2020-04-01 | 0
2020-05-01 | 0 | City Trunk Main along Western Route - CP10 (Turnkey Basis) - Under JICA Loan ID - P266
2020-06-01 | 26.0966
2020-07-01 | 26.0966
2020-08-01 | 52.1931
2020-09-01 | 52.1931
2020-10-01 | 52.1931
2020-11-01 | 75.3298
2020-12-01 | 90.7961
2021-01-01 | 114.2969
2021-02-01 | 137.8041
2021-03-01 | 160.922
2021-04-01 | 183.9874
2021-05-01 | 211.3948
2021-06-01 | 242.3231
2021-07-01 | 273.3365
2021-08-01 | 292.9784
2021-09-01 | 313.6534
2021-10-01 | 331.1299
2021-11-01 | 348.0898
2021-12-01 | 365.2819
2022-01-01 | 389.5403
2022-02-01 | 406.6048
2022-03-02 | 423.3101
2022-04-01 | 438.5765
2022-05-02 | 459.0469
2022-06-01 | 478.2564
2022-07-02 | 493.7621
2022-08-02 | 504.4257
2022-09-01 | 504.4257
2022-10-01 | 520.7757
2022-11-01 | 546.8157

## S-Curve - CASH FLOW NET
CASH FLOW - NET VALUE
2020-04-01 | 0
2020-05-01 | 0
2020-06-01 | 25.0527 | City Trunk Main along Western Route - CP10 (Turnkey Basis) - Under JICA Loan ID - P266
2020-07-01 | 25.0527
2020-08-01 | 50.2359
2020-09-01 | 50.2359
2020-10-01 | 50.2359
2020-11-01 | 71.4059
2020-12-01 | 85.5576
2021-01-01 | 107.0609
2021-02-01 | 128.5699
2021-03-01 | 149.7228
2021-04-01 | 170.8277
2021-05-01 | 195.6879
2021-06-01 | 223.7698
2021-07-01 | 251.9296
2021-08-01 | 269.6844
2021-09-01 | 288.3845
2021-10-01 | 304.158
2021-11-01 | 319.4588
2021-12-01 | 334.9721
2022-01-01 | 356.951
2022-02-01 | 372.3476
2022-03-02 | 387.4154
2022-04-01 | 401.1666
2022-05-02 | 419.8971
2022-06-01 | 437.4738
2022-07-02 | 451.6615
2022-08-02 | 461.4187
2022-09-01 | 461.4187
2022-10-01 | 476.3789
2022-11-01 | 502.4181