## CP 10 (hidden)
BALANCE PIPE - SUPPLY SCHEDULE | [17 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Required (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | TOTAL
|  |  |  | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | S
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2900
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3850
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 | 5000 | 523.055 | 2.425 | 2000 | 209.222 | 0.97 | 2000 | 209.222 | 0.97 |  | 0 | 0 | 9000 | 941.4991 | 4.365 | 4850
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 9970
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  | 0 | 0 | 2000 | 625.8905 | 3.25 | 2000 | 625.8905 | 3.25 | 4000 | 1251.7809 | 6.5 | 8000 | 2503.5619 | 13 | 16250
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 22495.5
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 7200 | 3148.451 | 16.9171 | 7200 | 3148.451 | 16.9171 | 23496
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 32000
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 | 2000 | 1322.3108 | 7 | 3000 | 1983.4661 | 10.5 | 3000 | 1983.4661 | 10.5 | 4000 | 2644.6215 | 14 | 12000 | 7933.8645 | 42 | 35000
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 |  | 0 | 0 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 | 42900
| Total | 65383 | 27468.5161 | 7000 | 1845.3658 | 9.425 | 9266 | 4473.2244 | 24.4411 | 7000 | 2818.5786 | 14.72 | 15200 | 7044.8535 | 37.4171 | 38466 | 16182.0223 | 86.0033
BALANCE PIPE - LAYING, JOINTING & HT SCHEDULE | [17 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Work (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | TOTAL
|  |  |  | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | LJ | T
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2030 | 870
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2695 | 1155
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 |  |  | 0 | 960 |  | 0.32592 | 2496 | 1200 | 1.022 | 2496 | 1200 | 1.022 | 5952 | 2400 | 2.3699 | 3395 | 1455
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 6979 | 2991
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  |  | 0 |  |  | 0 | 900 |  | 1.0237 | 1560 | 1200 | 2.3595 | 2460 | 1200 | 3.3833 | 11375 | 4875
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 15746.85 | 6748.65
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  |  | 0 |  |  | 0 |  |  | 0 | 300 |  | 0.49342 | 300 |  | 0.49342 | 16447.2 | 7048.8
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 22400 | 9600
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 |  |  | 0 | 360 |  | 0.882 | 936 |  | 2.2932 | 936 | 1200 | 3.5532 | 2232 |  | 6.7284 | 24500 | 10500
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  |  | 0 |  |  | 0 | 624 |  | 1.8739 | 624 |  | 1.8739 | 1248 |  | 3.7477 | 30030 | 12870
| Total | 65383 | 27468.5161 | 0 | 0 | 0 | 1320 | 0 | 1.2079 | 4956 | 1200 | 6.2128 | 5916 | 3600 | 9.302 | 12192 | 3600 | 16.7227

## CP 10 spk (hidden)
BALANCE PIPE - SUPPLY SCHEDULE | [32 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Required (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | Nov'20 |  |  | Dec'20 |  |  | Jan'20 |  |  | Feb'20 |  |  | Mar'20 |  |  | TOTAL
|  |  |  | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount |  |  |  | S
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 500 | 19.9752 | 0.145 | 606 | 24.21 | 0.17574 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1106 | 44.1852 | 0.32074 |  |  |  | 2900 |  | 1.2849 | 1433.9188 | 1.2597
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 500 | 37.509 | 0.1925 | 98 | 7.3518 | 0.03773 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 598 | 44.8608 | 0.23023 |  |  |  | 3850 |  | 1.6116 | 963.7305 | 1.5739
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 | 5000 | 523.055 | 2.425 | 2000 | 209.222 | 0.97 | 2000 | 209.222 | 0.97 |  | 0 | 0 |  | 0 | 0 | 824 | 86.1995 | 0.39964 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 9824 | 1027.6985 | 4.7646 |  |  |  | 4850 |  | 2.2399 | 22004.6744 | 2.2023
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 90 | 15.6606 | 0.08973 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 90 | 15.6606 | 0.08973 |  |  |  | 9970 |  | 3.1886 | 286.976 | 3.1447
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  | 0 | 0 | 2000 | 625.8905 | 3.25 | 2000 | 625.8905 | 3.25 | 4000 | 1251.7809 | 6.5 | 4000 | 1251.7809 | 6.5 | 1136 | 355.5058 | 1.846 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 13136 | 4110.8486 | 21.346 |  |  |  | 16250 |  | 4.4578 | 58557.5097 | 4.4014
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3229 | 1082.1668 | 7.2638 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3229 | 1082.1668 | 7.2638 |  |  |  | 22495.5 |  | 4.7719 | 15408.5894 | 4.7155
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 7200 | 3148.451 | 16.9171 | 7000 | 3060.994 | 16.4472 | 455 | 198.9646 | 1.0691 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 14655 | 6408.4097 | 34.4334 |  |  |  | 23496 |  | 5.0987 | 74720.7817 | 5.0297
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3639 | 1952.3956 | 11.6448 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3639 | 1952.3956 | 11.6448 |  |  |  | 32000 |  | 5.7332 | 20863.2513 | 5.658
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 | 2000 | 1322.3108 | 7 | 3000 | 1983.4661 | 10.5 | 3000 | 1983.4661 | 10.5 | 4000 | 2644.6215 | 14 | 3000 | 1983.4661 | 10.5 | 1830 | 1209.9143 | 6.405 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 16830 | 11127.245 | 58.905 |  |  |  | 35000 |  | 6.06 | 101989.0174 | 5.9722
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2266 | 1654.6458 | 9.7211 |  |  |  | 42900 |  | 6.6883 | 15155.5824 | 6.6005
| Total | 65383 | 27468.5161 | 7000 | 1845.3658 | 9.425 | 9266 | 4473.2244 | 24.4411 | 7000 | 2818.5786 | 14.72 | 15200 | 7044.8535 | 37.4171 | 15090 | 6369.386 | 33.8744 | 11817 | 4916.7084 | 28.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65373 | 27468.1166 | 148.7195
BALANCE PIPE - LAYING, JOINTING & HT SCHEDULE | [32 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia | Bal. Work (in Rmt) | Bal. Required (in MT) | July'20 |  |  | Aug'20 |  |  | Sep'20 |  |  | Oct'20 |  |  | Nov'20 |  |  | Dec'20 |  |  | Jan'20 |  |  | Feb'20 |  |  | Mar'20 |  |  | TOTAL
|  |  |  | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Laying | HT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Rmt. | MT | Amount | Laying | HT | Amount |  |  |  | LJ | T
1 | 401 mm ID 4mm thick | 1116 | 44.5847 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 2030 | 870 |  | 0 | 0 | 459 | 759 | 1459 | 0.459 | 0.759 | 1.459 | 0
2 | 501 mm ID 6mm thick | 598 | 44.8608 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 2695 | 1155 |  | 0 | 0 | 563 | 863 | 1563 | 0.563 | 0.863 | 1.563 | 0
3 | 701 mm ID 6mm thick | 9824 | 1027.6985 |  |  | 0 | 960 |  | 0.32592 | 2496 | 1200 | 1.022 | 2496 | 1200 | 1.022 | 2496 | 2400 | 1.1966 |  | 2400 | 0.3492 |  | 1200 | 0.1746 |  |  | 0 |  |  | 0 | 8448 | 8400 | 4.0903 |  |  |  | 3395 | 1455 |  | 18922.5865 | 18604.6625 | 763 | 1063 | 1763 | 0.763 | 1.063 | 1.763 | 12079.9189 |  | 12079.9189
4 | 1001 mm ID 7mm thick | 90 | 15.6606 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 6979 | 2991 |  | 0 | 0 | 1065 | 1365 | 2065 | 1.065 | 1.365 | 2.065 | 0 |  | 0
5 | 1401 mm ID 9mm thick | 13136 | 4110.8486 |  |  | 0 |  |  | 0 | 900 |  | 1.0237 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 1560 | 1200 | 2.3595 | 10260 | 7200 | 15.1808 |  |  |  | 11375 | 4875 |  | 45736.91 | 45158.0696 | 1469 | 1769 | 2469 | 1.469 | 1.769 | 2.469 | 65829.1245 | 12504.6008 | 53324.5237
6 | 1501 mm ID 9mm thick | 3229 | 1082.1668 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 15746.85 | 6748.65 |  | 0 | 0 | 1569 | 1869 | 2569 | 1.569 | 1.869 | 2.569 | 0 | 0 | 0
7 | 1601 mm ID 11mm thick | 14655 | 6408.4097 |  |  | 0 |  |  | 0 |  |  | 0 | 360 |  | 0.5921 | 624 |  | 1.0263 | 624 |  | 1.0263 | 624 | 800 | 1.5902 | 624 | 800 | 1.5902 | 624 |  | 1.0263 | 3480 | 1600 | 6.8514 |  |  |  | 16447.2 | 7048.8 |  | 17743.3177 | 17503.3206 | 1673 | 1973 | 2673 | 1.673 | 1.973 | 2.673 | 30704.4434 | 7730.6736 | 22973.7698
8 | 1801 mm ID 12mm thick | 3639 | 1952.3956 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 198 |  | 0.44352 | 468 |  | 1.0483 | 468 |  | 1.0483 | 468 |  | 1.0483 | 1602 | 0 | 3.5885 |  |  |  | 22400 | 9600 |  | 9184.6465 | 9064.1294 | 1875 | 2175 | 2875 | 1.875 | 2.175 | 2.875 | 18782.8242 | 5716.5117 | 13066.3125
9 | 1901 mm ID 14mm thick | 16830 | 11127.245 |  |  | 0 | 360 |  | 0.882 | 936 |  | 2.2932 | 936 | 1200 | 3.5532 | 936 |  | 2.2932 | 1872 |  | 4.5864 | 1872 | 2000 | 6.6864 | 1872 | 2000 | 6.6864 | 1872 | 1650 | 6.3189 | 10656 | 6850 | 33.2997 |  |  |  | 24500 | 10500 |  | 64574.8645 | 63639.4183 | 1979 | 2279 | 2979 | 1.979 | 2.279 | 2.979 | 143170.9262 | 47050.8012 | 96120.125
10 | 2101 mm ID 14mm thick | 2266 | 1654.6458 |  |  | 0 |  |  | 0 | 624 |  | 1.8739 | 624 |  | 1.8739 | 624 | 1000 | 3.1609 | 360 | 1200 | 2.6255 |  |  | 0 |  |  | 0 |  |  | 0 | 2232 | 2200 | 9.5341 |  |  |  | 30030 | 12870 |  | 14928.1818 | 14732.2851 | 2179 | 2479 | 3179 | 2.179 | 2.479 | 3.179 | 38328.2045 | 14214.8327 | 24113.3718
| Total | 65383 | 27468.5161 | 0 | 0 | 0 | 1320 | 0 | 1.2079 | 4956 | 1200 | 6.2128 | 5976 | 3600 | 9.4007 | 6240 | 4600 | 10.0365 | 4614 | 4800 | 11.3904 | 4524 | 5200 | 11.859 | 4524 | 4000 | 11.6844 | 4524 | 2850 | 10.753 | 36678 | 26250 | 72.5448
BALANCE E&M ITEM WISE SCHEDULE | [32 empty] | Amounts in Rs. Crore
S. No. | Item Description | Total Qty | JULY'20 |  | AUG'20 |  | SEPT'20 |  | OCT'20 |  | NOV'20 |  | DEC'20 |  | JAN'21 | [16 empty] | FEB'21 |  | MAR'21 |  | TOTAL
|  |  | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | [15 empty] | Amount | Qty | Amount | Qty | Amount | Qty | Amount
1 | Pumps | [29 empty] | 0 |  | 0 |  | 0 |  | 0
2 | Motors | [29 empty] | 0 |  | 0 |  | 0 |  | 0
3 | Panels | [29 empty] | 0 |  | 0 |  | 0 |  | 0
4 | Cable | [29 empty] | 0 |  | 0 |  | 0 |  | 0
5 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
6 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
7 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
8 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
9 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
10 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
11 | [30 empty] | 0 |  | 0 |  | 0 |  | 0
| Total | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SPK ref (hidden)
0 | 1120 | 1120 | NC
1120 | 1690 | 570 | C
1690 | 1780 | 90 | NC
1780 | 2570 | 790 | C
2570 | 2970 | 400 | NC
2970 | 3260 | 290 | C
3260 | 3780 | 520 | NC
3780 | 4010 | 230 | C
4010 | 6060 | 2050 | NC
6060 | 6470 | 410 | C
6470 | 13400 | 6930 | NC | C | 2390
13400 | 13500 | 100 | C | NC | 11110
13500 | 18850 | 5350 | NC
18850 | 19430 | 580 | C
19430 | 19680 | 250 | NC
19680 | 20000 | 320 | C
20000 | 27380 | 7380 | NC | C | 900
27380 | 30000 | 2620 | C | NC | 5600
30000 | 30700 | 700 | C
30700 | 30940 | 240 | NC | C | 2620
30940 | 31360 | 420 | C | NC | 7380
31360 | 39210 | 7850 | NC
39210 | 39550 | 340 | C | C | 2030
39550 | 43180 | 3630 | NC | NC | 11720
43180 | 43750 | 570 | C
43750

## to client - laying (hidden)
LAYING & JOINTING PLAN | [33 empty] | Amounts in Rs. Crore
S. No. | Pipe Dia |  |  |  | Bal. Work (in Rmt) | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 3001 mm ID 18mm thick | 0 to 13.50 Km | Non-Critical | 11100 | Team - 1 |  |  |  |  | 150 | 225 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 225 | 225 | 225 | 225 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 |  | 9562.5 | #REF! | #REF! | #REF! | #REF! | 459 | 759 | 1459 | 0.459 | 0.759 | 1.459 | 4860.5028
2 |  |  |  |  | Team - 3 | [5 empty] | 225 | [8 empty] | 225 | 225 | 225 | 225 | 412.5 | [9 empty] | 1537.5
3 |  |  | Critical | 2400 | Team - 3 | [6 empty] | 247.5 | 247.5 | 247.5 | 247.5 | 247.5 | 247.5 | 247.5 | 247.5 | [5 empty] | 172.75 | 247.5 | [7 empty] | 2400.25 | #REF! | #REF! | #REF! | #REF! | 563 | 863 | 1563 | 0.563 | 0.863 | 1.563 | 1822.7816
4 |  | 13.50 Km to 20.00 Km | Non-Critical | 5600 | Team - 3 | [21 empty] | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 |  | 2925 | #REF! | #REF! | #REF! | #REF! | 763 | 1063 | 1763 | 0.763 | 1.063 | 1.763 | 4182.5003 |  | 4182.5003
5 |  |  |  |  | Team - 5 | [21 empty] | 237.75 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 |  | 2675.25
6 |  |  | Critical | 900 | Team - 2 | [20 empty] | 56.25 | 225 | 225 | 225 | 168.75 |  |  |  | 900
7 |  | 20.00 Km to 30.00km | Non-Critical | 7400 | Team - 5 | [6 empty] | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 225 | 225 | 225 | 225 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 162.75 |  |  |  |  | 7400.25
8 |  |  | Critical | 2600 | Team - 6 | [7 empty] | 150 | 150 | 150 | 150 | 150 | 150 | 75 | 75 | 75 | 75 | 75 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 225 |  | 2700
9 |  | 30.00km to 43.50 km | Non-Critical | 11500 | Team - 2 |  |  |  |  | 150 | 225 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 225 | 225 | 225 | 225 | 487.5 | 487.5 | 324.5 | [7 empty] | 6474.5 | #REF! | #REF! | #REF! | #REF! | 1065 | 1365 | 2065 | 1.065 | 1.365 | 2.065 | 19436.0743 |  | 19436.0743
10 |  |  |  |  | Team - 4 | [5 empty] | 225 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 487.5 | 225 | 225 | 225 | 225 | [10 empty] | 5025
11 |  |  | Critical | 2000 | Team - 4 | [18 empty] | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 200 |  | 2000 | #REF! | #REF! | #REF! | #REF! | 1469 | 1769 | 2469 | 1.469 | 1.769 | 2.469 | 12832.188 | 2437.544 | 10394.644
| Total |  |  | 43500 | 0 |  | 0 | 0 | 0 | 300 | 900 | 2197.5 | 2347.5 | 2347.5 | 2347.5 | 2347.5 | 2347.5 | 2347.5 | 2272.5 | 1200 | 1200 | 1200 | 1200 | 2250 | 2010.25 | 1978.25 | 2300.25 | 2550 | 2225.25 | 2006.25 | 1837.5 | 1887.5 | 0 | 43600.25
[10 empty] | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040
[10 empty] | 0.6912 | 2.0736 | 5.063 | 5.4086 | 5.4086 | 5.4086 | 5.4086 | 5.4086 | 5.4086 | 5.2358 | 2.7648 | 2.7648 | 2.7648 | 2.7648 | 5.184 | 4.6316 | 4.5579 | 5.2998 | 5.8752 | 5.127 | 4.6224 | 4.2336 | 4.2542
S. No. | Pipe Dia |  |  |  | Bal. Work (in Rmt) | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 3001 mm ID 18mm thick | 0 to 13.50 Km | Non-Critical | 9.538 | [5 empty] | 1430.7 | 2146.05 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 0 |  | #REF! | #REF! | #REF! | #REF! | 459 | 759 | 1459 | 0.459 | 0.759 | 1.459 | 0
2 |  |  |  | 9.538 | [5 empty] | 0 | 2146.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 3934.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | 563 | 863 | 1563 | 0.563 | 0.863 | 1.563 | 0
3 |  |  | Critical | 9.538 | [5 empty] | 0 | 0 | 2360.655 | 2360.655 | 2360.655 | 2360.655 | 2360.655 | 2360.655 | 2360.655 | 2360.655 | 0 | 0 | 0 | 0 | 0 | 1647.6895 | 2360.655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | 763 | 1063 | 1763 | 0.763 | 1.063 | 1.763 | 0 |  | 0
4 |  | 13.50 Km to 20.00 Km | Non-Critical | 9.538 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 0
5 |  |  |  | 9.538 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2267.6595 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 0
6 |  |  |  | 9.538 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536.5125 | 2146.05 | 2146.05 | 2146.05 | 1609.5375 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | 1065 | 1365 | 2065 | 1.065 | 1.365 | 2.065 | 0 |  | 0
7 |  | 20.00 Km to 30.00km | Non-Critical | 9.538 | [5 empty] | 0 | 0 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 1552.3095 | 0 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | 1469 | 1769 | 2469 | 1.469 | 1.769 | 2.469 | 0 | 0 | 0
8 |  |  | Critical | 9.538 | [5 empty] | 0 | 0 | 0 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 715.35 | 715.35 | 715.35 | 715.35 | 715.35 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 1430.7 | 2146.05 | 0
9 |  | 30.00km to 43.50 km | Non-Critical | 9.538 | [5 empty] | 1430.7 | 2146.05 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 4649.775 | 4649.775 | 3095.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | 1673 | 1973 | 2673 | 1.673 | 1.973 | 2.673 | 0 | 0 | 0
10 |  |  |  | 9.538 | [5 empty] | 0 | 2146.05 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 4649.775 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  |  | Critical | 9.538 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 2146.05 | 1907.6 | 0
| Total |  |  |  | 0 |  | 0 | 0 | 0 | 2861.4 | 8584.2 | 20959.755 | 22390.455 | 22390.455 | 22390.455 | 22390.455 | 22390.455 | 22390.455 | 21675.105 | 11445.6 | 11445.6 | 11445.6 | 11445.6 | 21460.5 | 19173.7645 | 18868.5485 | 21939.7845 | 24321.9 | 21224.4345 | 19135.6125 | 17526.075 | 18002.975 | 0 | 0
S. No. | Pipe Dia |  |  |  | Bal. Work (in Rmt) | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 3001 mm ID 18mm thick |  |  | 9.538 | 43500 |  |  |  | 75 | 1500 | 1500 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 1650 | 1650 | 1650 | 1800 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2275 |  |  | 0 |  | #REF! | #REF! | #REF! | #REF! | 459 | 759 | 1459 | 0.459 | 0.759 | 1.459 | 0
| Total |  |  |  | 43500 |  | 0 | 0 | 75 | 1500 | 1500 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 1650 | 1650 | 1650 | 1800 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2275 | 0 | 0 | 0 | 0
[9 empty] | 715.35 | 14307 | 14307 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 15737.7 | 15737.7 | 15737.7 | 17168.4 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21698.95 | 0 | 0 | 0
[9 empty] | 10 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 220 | 220 | 220 | 240 | 300 | 300 | 300 | 300 | 300 | 300 | 303.3333 | 0 | 0
S. No. | Pipe Dia |  |  |  | Bal. Work (in Rmt) | MS Team | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | June'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | TOTAL
1 | 3001 mm ID 18mm thick |  |  | 9.538 | 43500 |  |  | 0 | 715.35 | 14307 | 14307 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 15737.7 | 15737.7 | 15737.7 | 17168.4 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21698.95 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | 459 | 759 | 1459 | 0.459 | 0.759 | 1.459 | 0
|  |  |  | 9.425 | 43500 |  |  |  | 706.875 | 14137.5 | 14137.5 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 15551.25 | 15551.25 | 15551.25 | 16965 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21206.25 | 21441.875
| Total |  |  |  | 43500 |  | 0 | 0 | 715.35 | 14307 | 14307 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 15737.7 | 15737.7 | 15737.7 | 17168.4 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21460.5 | 21698.95 | 0 | 0 | 0 | 0
[8 empty] | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | 725
[8 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  | 301496180
[8 empty] | 0 | 0.051863 | 1.0373 | 1.0373 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.141 | 1.141 | 1.141 | 1.2447 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5559 | 1.5732 |  | 164372000
[8 empty] | 0 | 0.028275 | 0.5655 | 0.5655 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.62205 | 0.62205 | 0.62205 | 0.6786 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.84825 | 0.85767 |  | 465868180
[8 empty] | 0 | 0.080138 | 1.6028 | 1.6028 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 1.763 | 1.763 | 1.763 | 1.9233 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4468 |  | 161845
0.016184
466030025
[9 empty] | 75 | 1575 | 3075 | 5325 | 7575 | 9825 | 12075 | 14325 | 16575 | 18825 | 21075 | 22725 | 24375 | 26025 | 27825 | 30075 | 32325 | 34575 | 36825 | 39075 | 41325 | 43600 | 43600 | 43600 | 43600
[9 empty] | 0 | 300 | 1200 | 3397.5 | 5745 | 8092.5 | 10440 | 12787.5 | 15135 | 17482.5 | 19755 | 20955 | 22155 | 23355 | 24555 | 26805 | 28815.25 | 30793.5 | 33093.75 | 35643.75 | 37869 | 39875.25 | 41712.75 | 43600.25 | 43600.25
[8 empty] | 0 | 0 | 66450 | 66450 | 132900 | 132900 | 199350 | 199350 | 265800 | 265800 | 332250 | 332250 | 398700 | 398700 | 465150 | 465150 | 531600 | 531600 | 598050

## to client - Supply (hidden)
PLATE- SUPPLY PLAN
| S. No. | Pipe Dia | Bal. Required (in Rmt) |  | July'20 | Aug'20 |  | Sep'20 |  | Oct'20 |  | Nov'20 |  | Dec'20 |  | Jan'21 |  | Feb'21 |  | Mar'21 |  | Apr'21 |  | May'21 |  | Jun'21 |  | July'21 |  | Aug'21 |  | Sep'21 |  | Oct'21 |  | Nov'21 |  | Dec'21 |  | Jan'22 |  | Feb'22 |  | Mar'22 |  | Apr'22 |  | May'22 |  | Jun'22 |  | July'22 |  | Aug'22 |  | Sep'22 |  | TOTAL
|  |  | in nos | in MT |  | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in mtr | in MT | S
| 1 | 9500mX2500mX18mm | 17400 | 58392.225 |  | 1200 | 4027.05 | 295 | 989.9831 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1500 | 5033.8125 | 1500 | 5033.8125 | 1500 | 5033.8125 | 1605 | 5386.1794 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17400 | 695.1379 | 2900 | 1.2849 | 22356.7989 | 1.2597
| 2 | 8900mX3000mX10mm | 17 | 35.6312 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 3850 | 1.6116 | 27.397 | 1.5739
r |  | Total | 17417 | 58427.8561 | 0 | 1200 | 4027.05 | 295 | 989.9831 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1400 | 4698.225 | 1500 | 5033.8125 | 1500 | 5033.8125 | 1500 | 5033.8125 | 1605 | 5386.1794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17400 | 695.1379
|  | Rate |  |  |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125 |  | 94125
[6 empty] | 11.295 |  | 2.7767 |  | 13.1775 |  | 13.1775 |  | 13.1775 |  | 13.1775 |  | 13.1775 |  | 13.1775 |  | 13.1775 |  | 14.1188 |  | 14.1188 |  | 14.1188 |  | 15.1071
|  |  | 204.3728 |  | 14.0947 |  | 3.4649 |  | 16.4438 |  | 16.4438 |  | 16.4438 |  | 16.4438 |  | 16.4438 |  | 16.4438 |  | 16.4438 |  | 17.6183 |  | 17.6183 |  | 17.6183 |  | 18.8516
[5 empty] | 6.897% |  | 1.695%
PIPE- SUPPLY PLAN
| S. No. | Pipe Dia | Bal. Required (in Rmt) |  | July'20 | Aug'20 |  | Sep'20 |  | Oct'20 |  | Nov'20 |  | Dec'20 |  | Jan'21 |  | Feb'21 |  | Mar'21 |  | Apr'21 |  | May'21 |  | Jun'21 |  | July'21 |  | Aug'21 |  | Sep'21 |  | Oct'21 |  | Nov'21 |  | Dec'21 |  | Jan'22 |  | Feb'22 |  | Mar'22 |  | Apr'22 |  | May'22 | [9 empty] | TOTAL
|  |  | in mtr | in MT |  | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in mtr | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | in nos | in MT | [8 empty] | in mtr | in MT | S
| 1 | 3001 mm ID 18mm thick | 43500 | 58295.0388 |  |  | 0 | 810 | 1085.4938 | 1440 | 1929.7668 | 2160 | 2894.6502 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 2430 | 3256.4815 | 1500 | 2010.1738 | 1500 | 2010.1738 | 1500 | 2010.1738 | 2160 | 2894.6502 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | [14 empty] | 43500 | 1737.8448 | 2900 | 1.2849 | 55891.9973 | 1.2597
| 2 | 1401 mm ID 10mm thick | 100 | 34.7964 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 134.0116 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 100 | 7.5018 | 3850 | 1.6116 | 161.159 | 1.5739
| 3 | 75mm Dia UPVC Pipe | 87000 | [10 empty] | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 3000 | [15 empty] | 87000 | 6526.5727
r |  | Total | 130600 | 58329.8352 | 0 | 0 | 0 | 810 | 1085.4938 | 1440 | 1929.7668 | 2160 | 2894.6502 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3100 | 4154.3591 | 3000 | 4020.3475 | 2430 | 3256.4815 | 1500 | 2010.1738 | 1500 | 2010.1738 | 1500 | 2010.1738 | 2160 | 2894.6502 | 3000 | 4020.3475 | 3000 | 4020.3475 | 3000 | 4020.3475 | 0 | 0 | [12 empty] | 43600 | 1745.3466
[6 empty] | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650 |  | 37650
[6 empty] | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800 |  | 28800
[6 empty] | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450 |  | 66450
[6 empty] | 0 |  | 5.3825 |  | 9.5688 |  | 14.3532 |  | 19.935 |  | 19.935 |  | 19.935 |  | 19.935 |  | 19.935 |  | 20.1032 |  | 19.935 |  | 16.1473 |  | 9.9675 |  | 9.9675 |  | 9.9675 |  | 14.3532 |  | 19.935 |  | 19.935 |  | 19.935
16825
0.16825
[22 empty] | 163.7775 | 125.28 | 0.16825
[10 empty] | 400 |  |  |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
[10 empty] | 0 |  |  |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.24 |  | 0.12

## to client - Supply TO MAIL
M/s. MEGHA ENGINEERING & INFRASTRUCTURE LIMITED
Supplying, Fabrication and laying of Clear Water Transmission Main from TK Halli to Harohalli (Turnkey Basis) - Under JICA Loan P-266
CONSTRUCTION SCHEDULE
S. No. | Pipe Dia | Uom | Scope | Start Date | Finish Date | Duration in days | Qty / value |  | Mar'20 | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Supply of Materials
1 | MS Plate Supply | Nos | 17400 | 2020-08-01 | 2021-08-30 | 394 | Qty | for the Month |  | 5: 1200; 6: 295; 7: 1400; 8: 1400; 9: 1400; 10: 1400; 11: 1400; 12: 1400; 13: 1400; 14: 1500; 15: 1500; 16: 1500; 17: 1605; 18: 0; 19: 0; 20: 0; 21: 0
2 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 1200 | 1495 | 2895 | 4295 | 5695 | 7095 | 8495 | 9895 | 11295 | 12795 | 14295 | 15795 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400 | 17400
3 | [6 empty] | Value | for the Month |  | 5: 11.295; 6: 2.7767; 7: 13.1775; 8: 13.1775; 9: 13.1775; 10: 13.1775; 11: 13.1775; 12: 13.1775; 13: 13.1775; 14: 14.1188; 15: 14.1188; 16: 14.1188; 17: 15.1071
4 | [7 empty] | Cumulative | [5 empty] | 11.295 | 14.0717 | 27.2492 | 40.4267 | 53.6042 | 66.7817 | 79.9592 | 93.1367 | 106.3142 | 120.4329 | 134.5517 | 148.6704 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775 | 163.7775
5 | MS Bare Pipe Supply | mtr | 43600 | 2020-09-01 | 2021-12-30 | 485 | Qty | for the Month | [5 empty] | 0 | 810 | 1440 | 2160 | 3000 | 3000 | 3000 | 3000 | 3000 | 3100 | 3000 | 2430 | 1500 | 1500 | 1500 | 2160 | 3000 | 3000 | 3000
6 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 810 | 2250 | 4410 | 7410 | 10410 | 13410 | 16410 | 19410 | 22510 | 25510 | 27940 | 29440 | 30940 | 32440 | 34600 | 37600 | 40600 | 43600 | 43600 | 43600 | 43600 | 43600 | 43600 | 43600 | 43600
7 | [6 empty] | Value | for the Month | [5 empty] | 0 | 5.3825 | 9.5688 | 14.3532 | 19.935 | 19.935 | 19.935 | 19.935 | 19.935 | 20.1032 | 19.935 | 16.1473 | 9.9675 | 9.9675 | 9.9675 | 14.3532 | 19.935 | 19.935 | 19.935
8 | [7 empty] | Cumulative | [5 empty] | 0 | 5.3825 | 14.9512 | 29.3044 | 49.2394 | 69.1744 | 89.1094 | 109.0444 | 128.9794 | 149.0827 | 169.0177 | 185.165 | 195.1325 | 205.1 | 215.0675 | 229.4207 | 249.3557 | 269.2907 | 289.2257 | 289.2257 | 289.2257 | 289.2257 | 289.2257 | 289.2257 | 289.2257 | 289.2257
9 | MS Coated Pipes Supply | mtr | 43600 | 2020-09-03 | 2022-05-27 | 631 | Qty | for the Month | [5 empty] | 0 | 75 | 1500 | 1500 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 1650 | 1650 | 1650 | 1800 | 2250 | 2250 | 2250 | 2250 | 2250 | 2250 | 2275 | 0
10 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 75 | 1575 | 3075 | 5325 | 7575 | 9825 | 12075 | 14325 | 16575 | 18825 | 21075 | 22725 | 24375 | 26025 | 27825 | 30075 | 32325 | 34575 | 36825 | 39075 | 41325 | 43600 | 43600 | 43600 | 43600
11 | [6 empty] | Value | for the Month | [5 empty] | 0 | 0.080138 | 1.6028 | 1.6028 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 1.763 | 1.763 | 1.763 | 1.9233 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4041 | 2.4468
12 | [7 empty] | Cumulative | [5 empty] | 0 | 0.080138 | 1.6829 | 3.2857 | 5.6898 | 8.0939 | 10.4981 | 12.9022 | 15.3063 | 17.7105 | 20.1146 | 22.5187 | 24.2818 | 26.0448 | 27.8078 | 29.7312 | 32.1353 | 34.5394 | 36.9436 | 39.3477 | 41.7518 | 44.156 | 46.6028 | 46.6028 | 46.6028 | 46.6028
13 | UPVC Pipe Supply | mtr | 87000 | 2020-10-20 | 2022-01-15 | 452 | Qty | for the Month | [5 empty] | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3000
14 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 12000 | 18000 | 24000 | 30000 | 36000 | 42000 | 48000 | 54000 | 60000 | 66000 | 72000 | 78000 | 84000 | 87000 | 87000 | 87000 | 87000 | 87000 | 87000 | 87000 | 87000
15 | [6 empty] | Value | for the Month |  | 7: 0; 8: 0; 9: 0.24; 10: 0.24; 11: 0.24; 12: 0.24; 13: 0.24; 14: 0.24; 15: 0.24; 16: 0.24; 17: 0.24; 18: 0.24; 19: 0.24; 20: 0.24; 21: 0.24; 22: 0.24; 23: 0.12
16 | [7 empty] | Cumulative | [5 empty] | 0 | 0 | 0 | 0 | 0.24 | 0.48 | 0.72 | 0.96 | 1.2 | 1.44 | 1.68 | 1.92 | 2.16 | 2.4 | 2.64 | 2.88 | 3.12 | 3.36 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48
17 | Valves Delivery at site | Nos | 114 | 2021-06-01 | 2022-02-28 | 272 | Qty | for the Month |  | 15: 22; 16: 8; 17: 9; 18: 0; 19: 0; 20: 0; 21: 35; 22: 38; 23: 2
18 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 30 | 39 | 39 | 39 | 39 | 74 | 112 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
19 | [6 empty] | Value | for the Month |  | 15: 1.65; 16: 1.55; 17: 4.41; 21: 0.09625; 22: 0.1045; 23: 0.095; 24: 1.3269
20 | [7 empty] | Cumulative | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 3.2 | 7.61 | 7.61 | 7.61 | 7.61 | 7.7063 | 7.8108 | 7.9058 | 9.2326 | 9.2326 | 9.2326 | 9.2326 | 9.2326 | 9.2326 | 9.2326
Execution of works
21 | MS Pipeline Laying & Jointing | mtr | 43600 | 2020-10-01 | 2022-08-31 | 699 | Qty | for the Month | [7 empty] | 300 | 900 | 2197.5 | 2347.5 | 2347.5 | 2347.5 | 2347.5 | 2347.5 | 2347.5 | 2272.5 | 1200 | 1200 | 1200 | 1200 | 2250 | 2010.25 | 1978.25 | 2300.25 | 2550 | 2225.25 | 2006.25 | 1837.5 | 1887.5
22 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1200 | 3397.5 | 5745 | 8092.5 | 10440 | 12787.5 | 15135 | 17482.5 | 19755 | 20955 | 22155 | 23355 | 24555 | 26805 | 28815.25 | 30793.5 | 33093.75 | 35643.75 | 37869 | 39875.25 | 41712.75 | 43600.25 | 43600.25
[8 empty] | Laying & jointing | [7 empty] | 0.6912 | 2.0736 | 5.063 | 5.4086 | 5.4086 | 5.4086 | 5.4086 | 5.4086 | 5.4086 | 5.2358 | 2.7648 | 2.7648 | 2.7648 | 2.7648 | 5.184 | 4.6316 | 4.5579 | 5.2998 | 5.8752 | 5.127 | 4.6224 | 4.2336 | 4.2542
[8 empty] | Fabrication | [7 empty] | 0.20586 | 0.61759 | 1.508 | 1.6109 | 1.6109 | 1.6109 | 1.6109 | 1.6109 | 1.6109 | 1.5594 | 0.82346 | 0.82346 | 0.82346 | 0.82346 | 1.544 | 1.3795 | 1.3575 | 1.5785 | 1.7499 | 1.527 | 1.3767 | 1.2609 | 1.2952
[8 empty] | Excavation | [7 empty] | 0.57316 | 1.7195 | 3.1984 | 3.485 | 3.485 | 3.485 | 3.485 | 3.485 | 3.485 | 3.3417 | 2.2927 | 2.2927 | 2.2927 | 2.2927 | 3.7987 | 3.8407 | 3.7795 | 3.8947 | 4.3719 | 4.2514 | 3.833 | 3.5106 | 3.6062 | 9.5
23 | [6 empty] | Value | for the Month | [7 empty] | 1.4702 | 4.4107 | 9.7694 | 10.5045 | 10.5045 | 10.5045 | 10.5045 | 10.5045 | 10.5045 | 10.137 | 5.8809 | 5.8809 | 5.8809 | 5.8809 | 10.5267 | 9.8518 | 9.6949 | 10.773 | 11.9969 | 10.9054 | 9.8321 | 9.0051 | 9.1555 | 9.5
24 | [7 empty] | Cumulative | [7 empty] | 1.4702 | 5.8809 | 15.6503 | 26.1549 | 36.6594 | 47.1639 | 57.6685 | 68.173 | 78.6775 | 88.8145 | 94.6954 | 100.5763 | 106.4572 | 112.3382 | 122.8649 | 132.7166 | 142.4115 | 153.1845 | 165.1815 | 176.0869 | 185.919 | 194.9242 | 204.0797 | 213.5797
25 | MS Pipes Hydro Testing | mtr | 43600 | 2020-11-15 | 2022-08-31 | 654 | Qty | for the Month | [9 empty] | 500 | 1500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 1000 | 1000 | 1000 | 1000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2600
26 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2000 | 4500 | 7000 | 9500 | 12000 | 14500 | 17000 | 18000 | 19000 | 20000 | 21000 | 23500 | 26000 | 28500 | 31000 | 33500 | 36000 | 38500 | 41000 | 43600 | 43600
27 | [6 empty] | Value | for the Month | [9 empty] | 0.288 | 0.864 | 1.44 | 1.44 | 1.44 | 1.44 | 1.44 | 1.44 | 0.576 | 0.576 | 0.576 | 0.576 | 1.44 | 1.44 | 1.44 | 1.44 | 1.44 | 1.44 | 1.44 | 1.44 | 1.4736 |  |  | 1002240000
28 | [7 empty] | Cumulative | [7 empty] | 0 | 0 | 0.288 | 1.152 | 2.592 | 4.032 | 5.472 | 6.912 | 8.352 | 9.792 | 10.368 | 10.944 | 11.52 | 12.096 | 13.536 | 14.976 | 16.416 | 17.856 | 19.296 | 20.736 | 22.176 | 23.616 | 25.0897 | 25.0897 |  | 1346000
29 | UPVC Pipe Laying | mtr | 87000 | 2020-11-30 | 2022-08-31 | 639 | Qty | for the Month | [9 empty] | 4000 | 4000 | 4000 | 4000 | 4500 | 4500 | 4500 | 4500 | 2500 | 2500 | 2500 | 2500 | 4500 | 4500 | 4500 | 4500 | 5000 | 5000 | 5000 | 5000 | 5000 |  |  | 250560000
30 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 8000 | 12000 | 16000 | 20500 | 25000 | 29500 | 34000 | 36500 | 39000 | 41500 | 44000 | 48500 | 53000 | 57500 | 62000 | 67000 | 72000 | 77000 | 82000 | 87000 | 87000 |  | 336500
31 | [6 empty] | Value | for the Month | [9 empty] | 0.16 | 0.16 | 0.16 | 0.16 | 0.18 | 0.18 | 0.18 | 0.18 | 0.1 | 0.1 | 0.1 | 0.1 | 0.18 | 0.18 | 0.18 | 0.18 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
32 | [7 empty] | Cumulative | [7 empty] | 0 | 0 | 0.16 | 0.32 | 0.48 | 0.64 | 0.82 | 1 | 1.18 | 1.36 | 1.46 | 1.56 | 1.66 | 1.76 | 1.94 | 2.12 | 2.3 | 2.48 | 2.68 | 2.88 | 3.08 | 3.28 | 3.48 | 3.48
33 | Fixing / Installation of Valves | Nos | 114 | 2021-09-01 | 2022-07-31 | 333 | Qty | for the Month |  | 18: 5; 19: 5; 20: 5; 21: 5; 22: 5; 23: 5; 24: 15; 25: 15; 26: 15; 27: 19; 28: 20
34 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 45 | 60 | 75 | 94 | 114 | 114 | 114
35 | [6 empty] | Value | for the Month |  | 18: 0.3713; 19: 0.3713; 20: 0.3713; 21: 0.3713; 22: 0.3713; 23: 0.3713; 24: 1.1139; 25: 1.1139; 26: 1.1139; 27: 1.411; 28: 2.2521
36 | [7 empty] | Cumulative | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3713 | 0.74261 | 1.1139 | 1.4852 | 1.8565 | 2.2278 | 3.3417 | 4.4557 | 5.5696 | 6.9805 | 9.2326 | 9.2326 | 9.2326
37 | Construction of Valve Chambers | Nos | 114 | 2021-03-03 | 2022-07-31 | 515 | Qty | for the Month |  | 13: 10; 14: 12; 15: 12; 16: 4; 17: 4; 18: 5; 19: 5; 20: 5; 21: 7; 22: 7; 23: 7; 24: 7; 25: 7; 26: 7; 27: 7; 28: 8
38 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 22 | 34 | 38 | 42 | 47 | 52 | 57 | 64 | 71 | 78 | 85 | 92 | 99 | 106 | 114 | 114 | 114
39 | [6 empty] | Value | for the Month |  | 13: 9.1254; 14: 10.9505; 15: 10.9505; 16: 3.6502; 17: 3.6502; 18: 4.5627; 19: 4.5627; 20: 4.5627; 21: 6.3878; 22: 6.3878; 23: 6.3878; 24: 6.3878; 25: 6.3878; 26: 6.3878; 27: 6.3878; 28: 7.3003
40 | [7 empty] | Cumulative | [13 empty] | 9.1254 | 20.076 | 31.0265 | 34.6766 | 38.3268 | 42.8895 | 47.4523 | 52.015 | 58.4028 | 64.7906 | 71.1784 | 77.5662 | 83.954 | 90.3418 | 96.7296 | 104.0299 | 104.0299 | 104.0299
41 | Construction of Pipe Bridge, Surge Tank, Trenchless crossings | Nos | 2 | 2020-11-11 | 2022-05-24 | 559 | Qty | for the Month | [8 empty] | 0.02 | 0.05 | 0.05 | 0.05 | 0.08 | 0.1 | 0.1 | 0.1 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
42 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0.07 | 0.12 | 0.17 | 0.25 | 0.35 | 0.45 | 0.55 | 0.6 | 0.65 | 0.7 | 0.75 | 0.8 | 1 | 1.2 | 1.4 | 1.6 | 1.8 | 2 | 2 | 2 | 2 | 2
43 | [6 empty] | Value | for the Month | [8 empty] | 0.18412 | 0.46029 | 0.46029 | 0.46029 | 0.73646 | 0.92058 | 0.92058 | 0.92058 | 0.46029 | 0.46029 | 0.46029 | 0.46029 | 0.46029 | 1.8412 | 1.8412 | 1.8412 | 1.8412 | 1.8412 | 1.8412 |  |  | 7.69 | 5.69
44 | [7 empty] | Cumulative | [7 empty] | 0 | 0.18412 | 0.6444 | 1.1047 | 1.565 | 2.3014 | 3.222 | 4.1426 | 5.0632 | 5.5235 | 5.9838 | 6.444 | 6.9043 | 7.3646 | 9.2058 | 11.0469 | 12.8881 | 14.7293 | 16.5704 | 18.4116 | 18.4116 | 18.4116 | 26.1016 | 31.7916
45 | Commissioning | Nos | 43600 | 2022-08-31 | 2022-09-30 | 30 |  | for the Month |  | 30: 43600
46 | [7 empty] | Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43600
| GRAND TOTAL | [6 empty] | for the Month | 0 | 0 | 0 | 0 | 0 | 11.295 | 8.2393 | 25.8193 | 33.7283 | 46.4343 | 47.7455 | 48.3215 | 48.5976 | 57.9272 | 60.8618 | 62.3435 | 50.3277 | 42.155 | 23.9218 | 23.9218 | 28.4677 | 43.4224 | 42.7557 | 42.4693 | 25.4669 | 25.3839 | 24.2924 | 21.7178 | 20.1976 | 18.5192 | 15.19 | 0
[8 empty] | Cumulative |  |  | 0 | 0 | 0 | 11.295 | 19.5343 | 45.3536 | 79.0818 | 125.5162 | 173.2616 | 221.5831 | 270.1807 | 328.1079 | 388.9697 | 451.3132 | 501.6409 | 543.7958 | 567.7176 | 591.6393 | 620.1071 | 663.5294 | 706.2851 | 748.7544 | 774.2213 | 799.6052 | 823.8977 | 845.6154 | 865.813 | 884.3322 | 899.5222 | 0
Supply of Material
| MS Plate Supply | [12 empty] | 6.897% | 1.695% | 8.046% | 8.046% | 8.046% | 8.046% | 8.046% | 8.046% | 8.046% | 8.621% | 8.621% | 8.621% | 9.224% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MS Bare Pipe Supply | [12 empty] | 0% | 1.858% | 3.303% | 4.954% | 6.881% | 6.881% | 6.881% | 6.881% | 6.881% | 7.11% | 6.881% | 5.573% | 3.44% | 3.44% | 3.44% | 4.954% | 6.881% | 6.881% | 6.881% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MS Coated pipe Supply | [12 empty] | 0% | 0.172% | 3.44% | 3.44% | 5.161% | 5.161% | 5.161% | 5.161% | 5.161% | 5.161% | 5.161% | 5.161% | 3.784% | 3.784% | 3.784% | 4.128% | 5.161% | 5.161% | 5.161% | 5.161% | 5.161% | 5.161% | 5.218% | 0% | 0% | 0%
| UPVC Supply | [12 empty] | 0% | 0% | 0% | 0% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 6.897% | 3.448% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Valves | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.3% | 7.018% | 7.895% | 0% | 0% | 0% | 30.7% | 33.33% | 1.754% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Execution
| MS Pipe Laying and Jointing | [12 empty] | 0% | 0% | 0.6881% | 2.064% | 5.04% | 5.384% | 5.384% | 5.384% | 5.384% | 5.384% | 5.384% | 5.212% | 2.752% | 2.752% | 2.752% | 2.752% | 5.161% | 4.611% | 4.537% | 5.276% | 5.849% | 5.104% | 4.601% | 4.214% | 4.329% | 0%
[16 empty] | 0.6887% | 2.066% | 5.045% | 5.389% | 5.389% | 5.389% | 5.389% | 5.389% | 5.389% | 5.217% | 2.755% | 2.755% | 2.755% | 2.755% | 5.165% | 4.615% | 4.542% | 5.281% | 5.854% | 5.109% | 4.606% | 4.218% | 4.239% | 0%
[16 empty] | 0.6881% | 2.064% | 5.04% | 5.384% | 5.384% | 5.384% | 5.384% | 5.384% | 5.384% | 5.212% | 2.752% | 2.752% | 2.752% | 2.752% | 5.16% | 4.611% | 4.537% | 5.276% | 5.848% | 5.104% | 4.601% | 4.214% | 4.329% | 0%
[16 empty] | 0.6881% | 2.064% | 3.84% | 4.184% | 4.184% | 4.184% | 4.184% | 4.184% | 4.184% | 4.012% | 2.752% | 2.752% | 2.752% | 2.752% | 4.56% | 4.611% | 4.537% | 4.676% | 5.248% | 5.104% | 4.601% | 4.214% | 4.329% | 11.4%
| Hydro Test for MS Pipe | [12 empty] | 0% | 0% | 0% | 0% | 1.147% | 3.44% | 5.734% | 5.734% | 5.734% | 5.734% | 5.734% | 5.734% | 2.294% | 2.294% | 2.294% | 2.294% | 5.734% | 5.734% | 5.734% | 5.734% | 5.734% | 5.734% | 5.734% | 5.734% | 5.963% | 0%
| UPVC pipe laying | [12 empty] | 0% | 0% | 0% | 0% | 4.598% | 4.598% | 4.598% | 4.598% | 5.172% | 5.172% | 5.172% | 5.172% | 2.874% | 2.874% | 2.874% | 2.874% | 5.172% | 5.172% | 5.172% | 5.172% | 5.747% | 5.747% | 5.747% | 5.747% | 5.747% | 0%
| Fixing/Installation of Valves | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.386% | 4.386% | 4.386% | 4.386% | 4.386% | 4.386% | 13.16% | 13.16% | 13.16% | 16.67% | 17.54% | 0% | 0%
| Construction of Valve Chambers | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.772% | 10.53% | 10.53% | 3.509% | 3.509% | 4.386% | 4.386% | 4.386% | 6.14% | 6.14% | 6.14% | 6.14% | 6.14% | 6.14% | 6.14% | 7.018% | 0% | 0%
| Trenchless works / NH Crossings | [12 empty] | 0% | 0% | 0% | 1% | 2.5% | 2.5% | 2.5% | 4% | 5% | 5% | 5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 0% | 0% | 0%
| Pipe Bridge Crossing | [12 empty] | 0% | 0% | 0% | 1% | 2.5% | 2.5% | 2.5% | 4% | 5% | 5% | 5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 0% | 0% | 0%
| Construction of Surge Tank | [12 empty] | 0% | 0% | 0% | 1% | 2.5% | 2.5% | 2.5% | 4% | 5% | 5% | 5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 0% | 0% | 0%

## Statement - 2
M/s. MEGHA ENGINEERING & INFRASTRUCTURE LIMITED
Supplying, Fabrication and laying of Clear Water Transmission Main from TK Halli to Harohalli (Turnkey Basis) - Under JICA Loan P-266
CASH FLOW
Sl.No | Description | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
1 | WORK DONE - GROSS | 0 | 0 | 0 | 0 | 11.295 | 8.2393 | 25.8193 | 33.7283 | 46.4343 | 47.7455 | 48.3215 | 48.5976 | 57.9272 | 60.8618 | 62.3435 | 50.3277 | 42.155 | 23.9218 | 23.9218 | 28.4677 | 43.4224 | 42.7557 | 42.4693 | 25.4669 | 25.3839 | 24.2924 | 21.7178 | 20.1976 | 18.5192 | 15.19 | 0
2 | CASH FLOW - PAYMENT |  | 0 | 0 | 0 | 0 | 0 | 19.5343 | 25.8193 | 33.7283 | 46.4343 | 47.7455 | 48.3215 | 48.5976 | 57.9272 | 60.8618 | 62.3435 | 50.3277 | 42.155 | 23.9218 | 23.9218 | 28.4677 | 43.4224 | 42.7557 | 42.4693 | 25.4669 | 25.3839 | 24.2924 | 21.7178 | 20.1976 | 18.5192 | 15.19
3 | MOBILIZATION ADVANCE 10% | 3: 45.0338; 6: 45.0338
4 | DEDUCTIONS
| Mobilization Advance - 8.33% per bill from 7th Interm payment | 13: 7.5026; 14: 7.5026; 15: 7.5026; 16: 7.5026; 17: 7.5026; 18: 7.5026; 19: 7.5026; 20: 7.5026; 21: 7.5026; 22: 7.5026; 23: 7.5026; 24: 7.5387
5 | CASH FLOW - GROSS (PAYMENT) | 0 | 0 | 45.0338 | 0 | 0 | 45.0338 | 19.5343 | 25.8193 | 33.7283 | 46.4343 | 47.7455 | 48.3215 | 41.095 | 50.4245 | 53.3591 | 54.8409 | 42.825 | 34.6523 | 16.4191 | 16.4191 | 20.9651 | 35.9197 | 35.253 | 34.9307 | 25.4669 | 25.3839 | 24.2924 | 21.7178 | 20.1976 | 18.5192 | 15.19
6 | OTHER DEDUCTIONS
| IT 2% / 1.5% | 0 | 0 | 0.90068 | 0 | 0 | 0.67551 | 0.29301 | 0.38729 | 0.50592 | 0.69652 | 0.71618 | 0.72482 | 0.61642 | 0.75637 | 0.80039 | 0.82261 | 0.64238 | 0.51979 | 0.24629 | 0.24629 | 0.31448 | 0.5388 | 0.5288 | 0.52396 | 0.382 | 0.38076 | 0.36439 | 0.32577 | 0.30296 | 0.27779 | 0.22785
| CGST 1% | 0 | 0 | 0.40209 | 0 | 0 | 0.40209 | 0.17441 | 0.23053 | 0.30115 | 0.41459 | 0.4263 | 0.43144 | 0.36692 | 0.45022 | 0.47642 | 0.48965 | 0.38237 | 0.3094 | 0.1466 | 0.1466 | 0.18719 | 0.32071 | 0.31476 | 0.31188 | 0.22738 | 0.22664 | 0.2169 | 0.19391 | 0.18034 | 0.16535 | 0.13562
| SGST 1% | 0 | 0 | 0.40209 | 0 | 0 | 0.40209 | 0.17441 | 0.23053 | 0.30115 | 0.41459 | 0.4263 | 0.43144 | 0.36692 | 0.45022 | 0.47642 | 0.48965 | 0.38237 | 0.3094 | 0.1466 | 0.1466 | 0.18719 | 0.32071 | 0.31476 | 0.31188 | 0.22738 | 0.22664 | 0.2169 | 0.19391 | 0.18034 | 0.16535 | 0.13562
| WWF 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0.19534 | 0.25819 | 0.33728 | 0.46434 | 0.47745 | 0.48321 | 0.48598 | 0.57927 | 0.60862 | 0.62344 | 0.50328 | 0.42155 | 0.23922 | 0.23922 | 0.28468 | 0.43422 | 0.42756 | 0.42469 | 0.25467 | 0.25384 | 0.24292 | 0.21718 | 0.20198 | 0.18519 | 0.1519
| RETENTION 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0.97671 | 1.291 | 1.6864 | 2.3217 | 2.3873 | 2.4161 | 2.4299 | 2.8964 | 3.0431 | 3.1172 | 2.5164 | 2.1077 | 1.1961 | 1.1961 | 1.4234 | 2.1711 | 2.1378 | 2.1235 | 1.2733 | 1.2692 | 1.2146 | 1.0859 | 1.0099 | 0.92596 | 0.7595
| ROYALITY OTHERS | 1: SHALL DEDUCT AS PER ACTUALS
7 | CASH FLOW - NET (PAYMENT) | 0 | 0 | 43.329 | 0 | 0 | 43.5541 | 17.7204 | 23.4218 | 30.5963 | 42.1226 | 43.312 | 43.8345 | 36.8289 | 45.2921 | 47.9542 | 49.2984 | 38.3983 | 30.9845 | 14.4443 | 14.4443 | 18.5682 | 32.1342 | 31.5294 | 31.2348 | 23.1021 | 23.0269 | 22.0367 | 19.7011 | 18.3221 | 16.7995 | 13.7795 | 44.9761

## S-Curve All
[8 empty] | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
WORK DONE - GROSS | [7 empty] | 0 | 0 | 0 | 0 | 11.295 | 8.2393 | 25.8193 | 33.7283 | 46.4343 | 47.7455 | 48.3215 | 48.5976 | 57.9272 | 60.8618 | 62.3435 | 50.3277 | 42.155 | 23.9218 | 23.9218 | 28.4677 | 43.4224 | 42.7557 | 42.4693 | 25.4669 | 25.3839 | 24.2924 | 21.7178 | 20.1976 | 18.5192 | 15.19 | 0 | 0
CASH FLOW - GROSS (PAYMENT) | [7 empty] | 0 | 0 | 45.0338 | 0 | 0 | 45.0338 | 19.5343 | 25.8193 | 33.7283 | 46.4343 | 47.7455 | 48.3215 | 41.095 | 50.4245 | 53.3591 | 54.8409 | 42.825 | 34.6523 | 16.4191 | 16.4191 | 20.9651 | 35.9197 | 35.253 | 34.9307 | 25.4669 | 25.3839 | 24.2924 | 21.7178 | 20.1976 | 18.5192 | 15.19 | 0
CASH FLOW - NET (PAYMENT) | [7 empty] | 0 | 0 | 43.329 | 0 | 0 | 43.5541 | 17.7204 | 23.4218 | 30.5963 | 42.1226 | 43.312 | 43.8345 | 36.8289 | 45.2921 | 47.9542 | 49.2984 | 38.3983 | 30.9845 | 14.4443 | 14.4443 | 18.5682 | 32.1342 | 31.5294 | 31.2348 | 23.1021 | 23.0269 | 22.0367 | 19.7011 | 18.3221 | 16.7995 | 13.7795 | 44.9761
|  | WORK DONE VALUE | CASH FLOW - GROSS VALUE | CASH FLOW - NET VALUE | WORK DONE - GROSS | CASH FLOW - GROSS (PAYMENT) | CASH FLOW - NET (PAYMENT)
| 2020-04-01 | 0 | 0 | 0 | 0 | 0 | 0
| 2020-05-01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Supplying, Fabrication and laying of Clear Water Transmission Main from TK Halli to Harohalli (Turnkey Basis) - Under JICA Loan P-266
| 2020-06-01 | 0 | 45.0338 | 43.329 | 0 | 45.0338 | 43.329
| 2020-07-01 | 0 | 45.0338 | 43.329 | 0 | 0 | 0
| 2020-08-01 | 11.295 | 45.0338 | 43.329 | 11.295 | 0 | 0
| 2020-09-01 | 19.5343 | 90.0677 | 86.8831 | 8.2393 | 45.0338 | 43.5541
| 2020-10-01 | 45.3536 | 109.6019 | 104.6035 | 25.8193 | 19.5343 | 17.7204
| 2020-11-01 | 79.0818 | 135.4212 | 128.0253 | 33.7283 | 25.8193 | 23.4218
| 2020-12-01 | 125.5162 | 169.1495 | 158.6216 | 46.4343 | 33.7283 | 30.5963
| 2021-01-01 | 173.2616 | 215.5838 | 200.7442 | 47.7455 | 46.4343 | 42.1226
| 2021-02-01 | 221.5831 | 263.3293 | 244.0562 | 48.3215 | 47.7455 | 43.312
| 2021-03-01 | 270.1807 | 311.6507 | 287.8906 | 48.5976 | 48.3215 | 43.8345
| 2021-04-01 | 328.1079 | 352.7457 | 324.7195 | 57.9272 | 41.095 | 36.8289
| 2021-05-01 | 388.9697 | 403.1703 | 370.0116 | 60.8618 | 50.4245 | 45.2921
| 2021-06-01 | 451.3132 | 456.5294 | 417.9658 | 62.3435 | 53.3591 | 47.9542
| 2021-07-01 | 501.6409 | 511.3703 | 467.2642 | 50.3277 | 54.8409 | 49.2984
| 2021-08-01 | 543.7958 | 554.1953 | 505.6624 | 42.155 | 42.825 | 38.3983
| 2021-09-01 | 567.7176 | 588.8477 | 536.6469 | 23.9218 | 34.6523 | 30.9845
| 2021-10-01 | 591.6393 | 605.2668 | 551.0912 | 23.9218 | 16.4191 | 14.4443
| 2021-11-01 | 620.1071 | 621.6859 | 565.5356 | 28.4677 | 16.4191 | 14.4443
| 2021-12-01 | 663.5294 | 642.651 | 584.1037 | 43.4224 | 20.9651 | 18.5682
| 2022-01-01 | 706.2851 | 678.5707 | 616.2379 | 42.7557 | 35.9197 | 32.1342
| 2022-02-01 | 748.7544 | 713.8237 | 647.7673 | 42.4693 | 35.253 | 31.5294
| 2022-03-02 | 774.2213 | 748.7544 | 679.002 | 25.4669 | 34.9307 | 31.2348
| 2022-04-01 | 799.6052 | 774.2213 | 702.1041 | 25.3839 | 25.4669 | 23.1021
| 2022-05-02 | 823.8977 | 799.6052 | 725.131 | 24.2924 | 25.3839 | 23.0269
| 2022-06-01 | 845.6154 | 823.8977 | 747.1677 | 21.7178 | 24.2924 | 22.0367
| 2022-07-02 | 865.813 | 845.6154 | 766.8688 | 20.1976 | 21.7178 | 19.7011
| 2022-08-02 | 884.3322 | 865.813 | 785.1909 | 18.5192 | 20.1976 | 18.3221
| 2022-09-01 | 899.5222 | 884.3322 | 801.9905 | 15.19 | 18.5192 | 16.7995
| 2022-10-01 | 899.5222 | 899.5222 | 815.77 | 0 | 15.19 | 13.7795
| 2022-11-01 | 899.5222 | 899.5222 | 860.7461 | 0 | 0 | 44.9761

## S-Curve - WD
|  |  | Apr'20 | May'20 | Jun'20 | July'20 | Aug'20 | Sep'20 | Oct'20 | Nov'20 | Dec'20 | Jan'21 | Feb'21 | Mar'21 | Apr'21 | May'21 | Jun'21 | July'21 | Aug'21 | Sep'21 | Oct'21 | Nov'21 | Dec'21 | Jan'22 | Feb'22 | Mar'22 | Apr'22 | May'22 | Jun'22 | July'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
WORK DONE - GROSS |  |  | 0 | 0 | 0 | 0 | 0 | 9.7156 | 13.421 | 15.4663 | 23.5009 | 23.5071 | 23.1179 | 23.0655 | 31.7573 | 35.2783 | 35.3635 | 23.9919 | 25.025 | 21.8265 | 21.3099 | 21.5421 | 28.6084 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 8.35 | 8 | 0 | 0
CASH FLOW - GROSS (PAYMENT) |  |  | 0 | 0 | 26.0966 | 26.0966 | 0 | 0 | 9.7156 | 13.421 | 15.4663 | 21.327 | 19.1595 | 18.7702 | 18.7178 | 27.4096 | 30.9306 | 31.0158 | 19.6442 | 20.6773 | 17.4788 | 16.9623 | 17.184 | 26.4241 | 21.4145 | 21.0553 | 19.6164 | 20.4705 | 19.2095 | 15.5056 | 10.6637 | 8.35 | 8 | 0
CASH FLOW - NET (PAYMENT) |  |  | 0 | 0 | 23.7479 | 23.7479 | 0 | 0 | 8.8412 | 12.2131 | 14.0743 | 19.4076 | 17.4351 | 17.0809 | 17.0332 | 24.9428 | 28.1469 | 28.2244 | 17.8762 | 18.8163 | 15.9057 | 15.4357 | 15.6374 | 24.0459 | 19.4872 | 19.1603 | 17.8509 | 18.6281 | 17.4806 | 14.1101 | 9.7039 | 7.5985 | 7.28 | 26.0391
WORK DONE VALUE
| 2020-04-01 | 0
| 2020-05-01 | 0 |  |  | Supplying, Fabrication and laying of Clear Water Transmission Main from TK Halli to Harohalli (Turnkey Basis) - Under JICA Loan P-266
| 2020-06-01 | 0
| 2020-07-01 | 0
| 2020-08-01 | 11.295
| 2020-09-01 | 19.5343
| 2020-10-01 | 45.3536
| 2020-11-01 | 79.0818
| 2020-12-01 | 125.5162
| 2021-01-01 | 173.2616
| 2021-02-01 | 221.5831
| 2021-03-01 | 270.1807
| 2021-04-01 | 328.1079
| 2021-05-01 | 388.9697
| 2021-06-01 | 451.3132
| 2021-07-01 | 501.6409
| 2021-08-01 | 543.7958
| 2021-09-01 | 567.7176
| 2021-10-01 | 591.6393
| 2021-11-01 | 620.1071
| 2021-12-01 | 663.5294
| 2022-01-01 | 706.2851
| 2022-02-01 | 748.7544
| 2022-03-02 | 774.2213
| 2022-04-01 | 799.6052
| 2022-05-02 | 823.8977
| 2022-06-01 | 845.6154
| 2022-07-02 | 865.813
| 2022-08-02 | 884.3322
| 2022-09-01 | 899.5222
| 2022-10-01 | 899.5222
| 2022-11-01 | 899.5222

## S-Curve - CASH FLOW GROSS
CASH FLOW - GROSS VALUE
2020-04-01 | 0
2020-05-01 | 0 | Supplying, Fabrication and laying of Clear Water Transmission Main from TK Halli to Harohalli (Turnkey Basis) - Under JICA Loan P-266
2020-06-01 | 45.0338
2020-07-01 | 45.0338
2020-08-01 | 45.0338
2020-09-01 | 90.0677
2020-10-01 | 109.6019
2020-11-01 | 135.4212
2020-12-01 | 169.1495
2021-01-01 | 215.5838
2021-02-01 | 263.3293
2021-03-01 | 311.6507
2021-04-01 | 352.7457
2021-05-01 | 403.1703
2021-06-01 | 456.5294
2021-07-01 | 511.3703
2021-08-01 | 554.1953
2021-09-01 | 588.8477
2021-10-01 | 605.2668
2021-11-01 | 621.6859
2021-12-01 | 642.651
2022-01-01 | 678.5707
2022-02-01 | 713.8237
2022-03-02 | 748.7544
2022-04-01 | 774.2213
2022-05-02 | 799.6052
2022-06-01 | 823.8977
2022-07-02 | 845.6154
2022-08-02 | 865.813
2022-09-01 | 884.3322
2022-10-01 | 899.5222
2022-11-01 | 899.5222

## S-Curve - CASH FLOW NET
CASH FLOW - NET VALUE
2020-04-01 | 0
2020-05-01 | 0
2020-06-01 | 43.329 | Supplying, Fabrication and laying of Clear Water Transmission Main from TK Halli to Harohalli (Turnkey Basis) - Under JICA Loan P-266
2020-07-01 | 43.329
2020-08-01 | 43.329
2020-09-01 | 86.8831
2020-10-01 | 104.6035
2020-11-01 | 128.0253
2020-12-01 | 158.6216
2021-01-01 | 200.7442
2021-02-01 | 244.0562
2021-03-01 | 287.8906
2021-04-01 | 324.7195
2021-05-01 | 370.0116
2021-06-01 | 417.9658
2021-07-01 | 467.2642
2021-08-01 | 505.6624
2021-09-01 | 536.6469
2021-10-01 | 551.0912
2021-11-01 | 565.5356
2021-12-01 | 584.1037
2022-01-01 | 616.2379
2022-02-01 | 647.7673
2022-03-02 | 679.002
2022-04-01 | 702.1041
2022-05-02 | 725.131
2022-06-01 | 747.1677
2022-07-02 | 766.8688
2022-08-02 | 785.1909
2022-09-01 | 801.9905
2022-10-01 | 815.77
2022-11-01 | 860.7461