## Grand Summary
Design, Engineering, Construction and Commissioning of Sewage Treatment Plants and Intermediate Sewage Pumping Stations with Operation and Maintenance there of for Seven years(Work-A) and Procurement and Construction of Main sewers including Manholes in Byatarayanapura (Hebbal Valley Catchment)(Work-B) for Package No CP -25. Contract LOC.No. BWSSB/CEKTE/TA-11/04/2021/765/2021-222.Dt: 07.07.2021
Work Contract package BWSSB (III)/JICA/CP-25
Abstract of Billing Breakup for 7 MLD STP at Doddabettahalli
Page | Schedule no. | Description | Amount (INR) | GST | Price
Schedule 1 | 1 | Design, Drawings & Doucmentations | 13429517 | 0 | 0
Schedule 2 | 2 | Civil Works Installations and other services | 150547117 | 0 | 0
Schedule 3 | 3 | Plant and Equipment Supplies | 192931039 | 0 | 0
Schedule 4 | 4 | Requirement of office of the Engineer | 336560 | 0 | 0
Schedule 5 | 5 | Laboratory Equipments | 5776673 | 0 | 0
Schedule 6 | 6 | Operation & Maintenance for 7 years | 53373775 | 0 | 0
|  | Grand Total | 416394681

## Schedule 1
Design, Engineering, Construction and Commissioning of Sewage Treatment Plants and Intermediate Sewage Pumping Stations with Operation and Maintenance there of for Seven years(Work-A) and Procurement and Construction of Main sewers including Manholes in Byatarayanapura (Hebbal Valley Catchment)(Work-B) for Package No CP -25. Contract LOC.No. BWSSB/CEKTE/TA-11/04/2021/765/2021-222.Dt: 07.07.2021
7 MLD STP at Doddabettahalli
Schedule 1: Design, Drawings and Documentation
Level | Item No. | Description | Quantity | unit | Price in INR | Duties | Ex. Work | Local Transport | GST in INR | Total Price including GST in INR
A.Civil Works
2 | 1.1 | Process Design and Drawings | 1 | LS
3 | 1.1.1 | Concept report defining TSPS & STP. Flow charts and process design, Hydraulic Flow diagram, P&IDs, Mass Balance, Plant water & drain Philosophy, Service water usage plan | 1 | LS
4 | a) | Process Flow Diagram | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 71370 |  |  |  | 8564.4 | 79934.4
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
4 | b) | Process Design Calculation | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 71370 |  |  |  | 8564.4 | 79934.4
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
4 | c) | Hydraulic design calculation & Hydraulic Flow Diagram | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 71370 |  |  |  | 8564.4 | 79934.4
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
4 | d) | Mass Balance | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 15860 |  |  |  | 1903.2 | 17763.2
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 47580 |  |  |  | 5709.6 | 53289.6
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 15860 |  |  |  | 1903.2 | 17763.2
4 | e) | Piping & Instrumentation Diagram | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 71370 |  |  |  | 8564.4 | 79934.4
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
4 | f) | Plant water utility plan | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 7930 |  |  |  | 951.6 | 8881.6
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 7930 |  |  |  | 951.6 | 8881.6
4 | g) | Process description | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 71370 |  |  |  | 8564.4 | 79934.4
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
4 | h) | Plant drain Philosophy | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 7930 |  |  |  | 951.6 | 8881.6
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 7930 |  |  |  | 951.6 | 8881.6
4 | i) | Plant Operation and Control Philosophy | 1 | LS
5 | i) | Submission of Design and Documentation | 1 | LS | 7930 |  |  |  | 951.6 | 8881.6
5 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 23790 |  |  |  | 2854.8 | 26644.8
5 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 7930 |  |  |  | 951.6 | 8881.6
3 | 1.1.2 | Site Layout Plan, Bore hole location plan for entire plant, Civil & Mechanical General Arrangement drawings, Geotechnical survey,Topographical Survey, Electrical resistivity test report | 1 | LS
4 | 1.1.2.1 | Design Document | 1 | LS
5 | a) | Plant Layout | 1 | LS
6 | i) | Submission of Design and Documentation | 1 | LS | 46260 |  |  |  | 5551.2 | 51811.2
6 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 138780 |  |  |  | 16653.6 | 155433.6
6 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 46260 |  |  |  | 5551.2 | 51811.2
5 | b) | Bore Hole Location Plan | 1 | LS
6 | i) | Submission of Design and Documentation | 1 | LS | 46260 |  |  |  | 5551.2 | 51811.2
6 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 138780 |  |  |  | 16653.6 | 155433.6
6 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 46260 |  |  |  | 5551.2 | 51811.2
5 | c) | Geographical Survey | 1 | LS
6 | i) | Submission of Design and Documentation | 1 | LS | 30840 |  |  |  | 3700.8 | 34540.8
6 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 92520 |  |  |  | 11102.4 | 103622.4
6 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 30840 |  |  |  | 3700.8 | 34540.8
5 | d) | Electrical resitivity test report | 1 | LS
6 | i) | Submission of Design and Documentation | 1 | LS | 30840 |  |  |  | 3700.8 | 34540.8
6 | ii) | Approval on Design and Documentation in Code B | 1 | LS | 92520 |  |  |  | 11102.4 | 103622.4
6 | iii) | Approval on Design and Documentation in Code A | 1 | LS | 30840 |  |  |  | 3700.8 | 34540.8
|  | B.ELECTRICAL DOCUMENTATION | 1 | LS
3 | 1.1.3 | Single Line diagrams and Electrical drawings complete | 1 | LS
4 | a) | Single Line Diagram. | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 7200 |  |  |  | 864 | 8064
5 | ii) | Approval on Diagram in Code B | 1 | LS | 21600 |  |  |  | 2592 | 24192
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 7200 |  |  |  | 864 | 8064
|  | Electrical Drawings | 1 | LS
4 | b) | Electrical drawing of transformer yard with HT & LT panel rooms | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 4800 |  |  |  | 576 | 5376
5 | ii) | Approval on Diagram in Code B | 1 | LS | 14400 |  |  |  | 1728 | 16128
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 4800 |  |  |  | 576 | 5376
4 | c) | Electrical drawing of MCC room | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 2400 |  |  |  | 288 | 2688
5 | ii) | Approval on Diagram in Code B | 1 | LS | 7200 |  |  |  | 864 | 8064
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 2400 |  |  |  | 288 | 2688
4 | d) | Earhing layout for outdoor | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 2400 |  |  |  | 288 | 2688
5 | ii) | Approval on Diagram in Code B | 1 | LS | 7200 |  |  |  | 864 | 8064
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 2400 |  |  |  | 288 | 2688
4 | e) | Earthing layout for indoor | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 7200 |  |  |  | 864 | 8064
5 | ii) | Approval on Diagram in Code B | 1 | LS | 21600 |  |  |  | 2592 | 24192
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 7200 |  |  |  | 864 | 8064
4 | f) | Lighting layout for indoor | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 7200 |  |  |  | 864 | 8064
5 | ii) | Approval on Diagram in Code B | 1 | LS | 21600 |  |  |  | 2592 | 24192
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 7200 |  |  |  | 864 | 8064
4 | g) | Lighting layout for outdoor | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 4800 |  |  |  | 576 | 5376
5 | ii) | Approval on Diagram in Code B | 1 | LS | 14400 |  |  |  | 1728 | 16128
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 4800 |  |  |  | 576 | 5376
4 | h) | Cable routing layout for indoor | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 7200 |  |  |  | 864 | 8064
5 | ii) | Approval on Diagram in Code B | 1 | LS | 21600 |  |  |  | 2592 | 24192
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 7200 |  |  |  | 864 | 8064
4 | i) | Cable routing layout for outdoor | 1 | LS
5 | i) | Submission of Diagram | 1 | LS | 4800 |  |  |  | 576 | 5376
5 | ii) | Approval on Diagram in Code B | 1 | LS | 14400 |  |  |  | 1728 | 16128
5 | iii) | Approvalon Diagram in Code A | 1 | LS | 4800 |  |  |  | 576 | 5376
|  | C.INSTRUMENTATION DOCUMENTATION | 1 | LS
3 | 1.1.4 | Instrumentation, Control & Automation systems, Functional design specifications, System Architecture drawings complete | 1 | LS
4 | 1.1.4.1 | Submission of Functional design specification | 1 | LS | 50000 |  |  |  | 6000 | 56000
4 | 1.1.4.2 | Approval on Diagram in Code B | 1 | LS | 150000 |  |  |  | 18000 | 168000
4 | 1.1.4.3 | Approval on Diagram in Code A | 1 | LS | 50000 |  |  |  | 6000 | 56000
3 | 1.1.5 | Any other necessary document which Bidder feels necessary for project completion needs to be added including all essential Investingation, Model Study (if required) ,etc. required to complete the Works | 1 | LS
4 | 1.1.5.1 | Submission of Functional design specification | 1 | LS | 68000 |  |  |  | 8160 | 76160
4 | 1.1.5.2 | Approval on Diagram in Code B | 1 | LS | 204000 |  |  |  | 24480 | 228480
4 | 1.1.5.3 | Approval on Diagram in Code A | 1 | LS | 68000 |  |  |  | 8160 | 76160
Sub Total of 1.1 |  |  | 1 | LS
2 | 1.2 | Civil, Architectural & Structural Designs and Drawings | 1 | LS
|  | TSPS Works | 1 | LS
3 | 1.2.1 | Inlet manhole & chamber, Coarse Screen channels, Effluent chamber, Overflow chamber, Wetwell with superstructure, Valve & Flowmeter chambers, Thrust block and Anchor blocks etc. | 1 | LS
4 | 1.2.1.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 65000 |  |  |  | 7800 | 72800
4 | 1.2.1.2 | Approval on Design and Drawing in Code B | 1 | LS | 195000 |  |  |  | 23400 | 218400
4 | 1.2.1.3 | Approval on Design and Drawing in Code A | 1 | LS | 65000 |  |  |  | 7800 | 72800
|  | Inlet Works | 1 | LS
3 | 1.2.2 | Inlet Chamber, Fine Screen Channel, Screen Effluent/ Grit Basin Distribution Channel, chambers, RCC Staircase, etc. | 1 | LS
4 | 1.2.2.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.2.2.2 | Approval on Design and Drawing in Code B | 1 | LS | 180000 |  |  |  | 21600 | 201600
4 | 1.2.2.3 | Approval on Design and Drawing in Code A | 1 | LS | 60000 |  |  |  | 7200 | 67200
3 | 1.2.3 | Vortex Grit Basins & chamber, Grit Basin effluent channel, Grit Classifier arrangement,chambers, RCC Staircase, etc. | 1 | LS
4 | 1.2.3.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 41000 |  |  |  | 4920 | 45920
4 | 1.2.3.2 | Approval on Design and Drawing in Code B | 1 | LS | 123000 |  |  |  | 14760 | 137760
4 | 1.2.3.3 | Approval on Design and Drawing in Code A | 1 | LS | 41000 |  |  |  | 4920 | 45920
3 | 1.2.4 | Parshall Flume, drop chamber, connecting arrangement from Inlet works to Areation basin, RCC Staircase etc | 1 | LS
4 | 1.2.4.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 40000 |  |  |  | 4800 | 44800
4 | 1.2.4.2 | Approval on Design and Drawing in Code B | 1 | LS | 120000 |  |  |  | 14400 | 134400
4 | 1.2.4.3 | Approval on Design and Drawing in Code A | 1 | LS | 40000 |  |  |  | 4800 | 44800
|  | AERATION BASINS | 1 | LS
3 | 1.2.5 | Aeration Basin flow distribution channel, Anaerobic Zones, Anoxic Zones, Aerobic Zones, Aeration Basin Effluent Channel, MLR Feed, RAS inlet arrangement, Valve & flowmeter chamber, Overflow & Bypass chamber, RCC Staircase, etc. | 1 | LS
4 | 1.2.5.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 85000 |  |  |  | 10200 | 95200
4 | 1.2.5.2 | Approval on Design and Drawing in Code B | 1 | LS | 255000 |  |  |  | 30600 | 285600
4 | 1.2.5.3 | Approval on Design and Drawing in Code A | 1 | LS | 85000 |  |  |  | 10200 | 95200
|  | BLOWER BUILDING | 1 | LS
3 | 1.2.6 | Process Air Blower Building, Valve chamber, Supports for air piping,RCC Stair case etc. | 1 | LS
4 | 1.2.6.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 56000 |  |  |  | 6720 | 62720
4 | 1.2.6.2 | Approval on Design and Drawing in Code B | 1 | LS | 168000 |  |  |  | 20160 | 188160
4 | 1.2.6.3 | Approval on Design and Drawing in Code A | 1 | LS | 56000 |  |  |  | 6720 | 62720
|  | SECONDARY CLARIFIERS | 1 | LS
3 | 1.2.7 | Inlet arrangments from areation basin outlet, Secondary Clarifier Distribution boxes, Secondary Clarifiers, Scum collection pit, Desluding valve chamber, RCC Staircase etc. | 1 | LS
4 | 1.2.7.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS
4 | 1.2.7.2 | Approval on Design and Drawing in Code B | 1 | LS
4 | 1.2.7.3 | Approval on Design and Drawing in Code A | 1 | LS
3 | 1.2.8 | RAS pumping station including Valve & flowmeter chambers, RCC Staircase, etc. | 1 | LS
4 | 1.2.8.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS
4 | 1.2.8.2 | Approval on Design and Drawing in Code B | 1 | LS
4 | 1.2.8.3 | Approval on Design and Drawing in Code A | 1 | LS
|  | Chlorine Contact Tank | 1 | LS
3 | 1.2.9 | Chlorine Contact Tank, Inlet chamber, distribution chamber, Effluent Channel/pipe, flowmeter chamber, RCC Staircase, Outfall Structure, etc | 1 | LS
4 | 1.2.9.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 50000 |  |  |  | 6000 | 56000
4 | 1.2.9.2 | Approval on Design and Drawing in Code B | 1 | LS | 150000 |  |  |  | 18000 | 168000
4 | 1.2.9.3 | Approval on Design and Drawing in Code A | 1 | LS | 50000 |  |  |  | 6000 | 56000
3 | 1.2.10 | Chlorine and Alum building etc and any other chemicals required as per the Process design, etc. | 1 | LS
4 | 1.2.10.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 50000 |  |  |  | 6000 | 56000
4 | 1.2.10.2 | Approval on Design and Drawing in Code B | 1 | LS | 150000 |  |  |  | 18000 | 168000
4 | 1.2.10.3 | Approval on Design and Drawing in Code A | 1 | LS | 50000 |  |  |  | 6000 | 56000
3 | 1.2.11 | Plant water & Treated water storage sump / Pump Station and inlet flow arrangement, chamber etc. | 1 | LS
4 | 1.2.11.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 55000 |  |  |  | 6600 | 61600
4 | 1.2.11.2 | Approval on Design and Drawing in Code B | 1 | LS | 165000 |  |  |  | 19800 | 184800
4 | 1.2.11.3 | Approval on Design and Drawing in Code A | 1 | LS | 55000 |  |  |  | 6600 | 61600
|  | Disc Filter | 1 | LS
3 | 1.2.12 | Disc Filter Influent chamber, Disc Filter units and Disc Filter Effluent channel, Backwash water collection arrangement etc. | 1 | LS
4 | 1.2.12.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 35400 |  |  |  | 4248 | 39648
4 | 1.2.12.2 | Approval on Design and Drawing in Code B | 1 | LS | 106200 |  |  |  | 12744 | 118944
4 | 1.2.12.3 | Approval on Design and Drawing in Code A | 1 | LS | 35400 |  |  |  | 4248 | 39648
|  | SLUDGE DEWATERING | 1 | LS
3 | 1.2.13 | Sludge Dewatering Building including sludge storage, chambers etc. | 1 | LS
4 | 1.2.13.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 50000 |  |  |  | 6000 | 56000
4 | 1.2.13.2 | Approval on Design and Drawing in Code B | 1 | LS | 150000 |  |  |  | 18000 | 168000
4 | 1.2.13.3 | Approval on Design and Drawing in Code A | 1 | LS | 50000 |  |  |  | 6000 | 56000
3 | 1.2.14 | Dewatering Feed sump and Pumping Station, chambers etc. | 1 | LS
4 | 1.2.14.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 34000 |  |  |  | 4080 | 38080
4 | 1.2.14.2 | Approval on Design and Drawing in Code B | 1 | LS | 102000 |  |  |  | 12240 | 114240
4 | 1.2.14.3 | Approval on Design and Drawing in Code A | 1 | LS | 34000 |  |  |  | 4080 | 38080
3 | 1.2.15 | Scum Pit,Sump and Pump Station, Chamber etc. | 1 | LS
4 | 1.2.15.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 34000 |  |  |  | 4080 | 38080
4 | 1.2.15.2 | Approval on Design and Drawing in Code B | 1 | LS | 102000 |  |  |  | 12240 | 114240
4 | 1.2.15.3 | Approval on Design and Drawing in Code A | 1 | LS | 34000 |  |  |  | 4080 | 38080
3 | 1.2.16 | Plant Drain Sump and Pump Station, Chamber etc. | 1 | LS
4 | 1.2.16.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 32000 |  |  |  | 3840 | 35840
4 | 1.2.16.2 | Approval on Design and Drawing in Code B | 1 | LS | 96000 |  |  |  | 11520 | 107520
4 | 1.2.16.3 | Approval on Design and Drawing in Code A | 1 | LS | 32000 |  |  |  | 3840 | 35840
|  | SUBSTATION FOR STP & TSPS | 1 | LS
3 | 1.2.17 | Switch gear room, Electrical Sub station | 1 | LS
4 | 1.2.17.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.2.17.2 | Approval on Design and Drawing in Code B | 1 | LS | 90000 |  |  |  | 10800 | 100800
4 | 1.2.17.3 | Approval on Design and Drawing in Code A | 1 | LS | 30000 |  |  |  | 3600 | 33600
3 | 1.2.18 | Transformer yard | 1 | LS
4 | 1.2.18.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 26000 |  |  |  | 3120 | 29120
4 | 1.2.18.2 | Approval on Design and Drawing in Code B | 1 | LS | 78000 |  |  |  | 9360 | 87360
4 | 1.2.18.3 | Approval on Design and Drawing in Code A | 1 | LS | 26000 |  |  |  | 3120 | 29120
|  | UTILITY BUILDINGS | 1 | LS
3 | 1.2.19 | Plant D.G. Room | 1 | LS
4 | 1.2.19.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 24000 |  |  |  | 2880 | 26880
4 | 1.2.19.2 | Approval on Design and Drawing in Code B | 1 | LS | 72000 |  |  |  | 8640 | 80640
4 | 1.2.19.3 | Approval on Design and Drawing in Code A | 1 | LS | 24000 |  |  |  | 2880 | 26880
3 | 1.2.20 | Administration Cum Laboratory Building & SCADA Building (Two Floors) (For SCADA control room ,refer Particular ICA requirements) | 1 | LS
4 | 1.2.20.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 50000 |  |  |  | 6000 | 56000
4 | 1.2.20.2 | Approval on Design and Drawing in Code B | 1 | LS | 150000 |  |  |  | 18000 | 168000
4 | 1.2.20.3 | Approval on Design and Drawing in Code A | 1 | LS | 50000 |  |  |  | 6000 | 56000
3 | 1.2.21 | Guard Room (Security Room) | 1 | LS
4 | 1.2.21.1 | Submission of Architectural and Structural Design and Drawings | 1 | LS | 10000 |  |  |  | 1200 | 11200
4 | 1.2.21.2 | Approval on Design and Drawing in Code B | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.2.21.3 | Approval on Design and Drawing in Code A | 1 | LS | 10000 |  |  |  | 1200 | 11200
OTHER UTILITIES |  |  | 1 | LS
3 | 1.2.22 | Roads & drains , Internal roads and landscaping, Culverts, Name boards for units in kannada/ english | 1 | LS
4 | 1.2.22.1 | Submission of Drawings | 1 | LS | 20100 |  |  |  | 2412 | 22512
4 | 1.2.22.2 | Approval on Drawings in Code B | 1 | LS | 60300 |  |  |  | 7236 | 67536
4 | 1.2.22.3 | Approval on Drawings in Code A | 1 | LS | 20100 |  |  |  | 2412 | 22512
3 | 1.2.23 | Approach Road to STP, TSPS | 1 | LS
4 | 1.2.23.1 | Submission of Drawings | 1 | LS | 20000 |  |  |  | 2400 | 22400
|  |  | 1 | LS
|  | A.Civil Works | 1 | LS
4 | 1.2.23.2 | Approval on Drawings in Code B | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.2.23.3 | Approval on Drawings in Code A | 1 | LS | 20000 |  |  |  | 2400 | 22400
3 | 1.2.24 | Parking Shed, piles if required, gates, GP2, Grouting for machine | 1 | LS
4 | 1.2.24.1 | Submission of Drawings | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.2.24.2 | Approval on Drawings in Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.2.24.3 | Approval on Drawings in Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.2.25 | Compound Wall with gates, Chain link fencing | 1 | LS
4 | 1.2.25.1 | Submission of Drawings | 1 | LS | 20000 |  |  |  | 2400 | 22400
4 | 1.2.25.2 | Approval on Drawings in Code B | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.2.25.3 | Approval on Drawings in Code A | 1 | LS | 20000 |  |  |  | 2400 | 22400
3 | 1.2.26 | Ground Improvement Plan, Site grading | 1 | LS
4 | 1.2.26.1 | Submission of Drawings | 1 | LS | 20000 |  |  |  | 2400 | 22400
4 | 1.2.26.2 | Approval on Drawings in Code B | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.2.26.3 | Approval on Drawings in Code A | 1 | LS | 20000 |  |  |  | 2400 | 22400
3 | 1.2.27 | Nalla & flow diversion etc. | 1 | LS
4 | 1.2.27.1 | Submission of Drawings | 1 | LS | 10000 |  |  |  | 1200 | 11200
4 | 1.2.27.2 | Approval on Drawings in Code B | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.2.27.3 | Approval on Drawings in Code A | 1 | LS | 10000 |  |  |  | 1200 | 11200
3 | 1.2.28 | Gabion wall, Site retaining structure and pile foundation , electric cable trenches inside STP site. | 1 | LS
4 | 1.2.28.1 | Submission of Drawings | 1 | LS | 20000 |  |  |  | 2400 | 22400
4 | 1.2.28.2 | Approval on Drawings in Code B | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.2.28.3 | Approval on Drawings in Code A | 1 | LS | 20000 |  |  |  | 2400 | 22400
3 | 1.2.29 | Additional Backfill for entire Project including approach road (if required) | 1 | LS
4 | 1.2.29.1 | Submission of Drawings | 1 | LS
4 | 1.2.29.2 | Approval on Drawings in Code B | 1 | LS
4 | 1.2.29.3 | Approval on Drawings in Code A | 1 | LS
3 | 1.2.30 | Tree Plantation | 1 | LS
3 | 1.2.31 | Any other works which Bidder feels necessary for project completion needs to be added including all essential Investigation, etc. required to complete the Works under 1.2 | 1 | LS
Sub Total of 1.2 |  |  | 1 | LS
2 | 1.3 | Mechanical Design, Drawings,and Documentation as defined in Volume 2 of Bidding Document | 1 | LS
|  | TSPS | 1 | LS
3 | 1.3.1 | Inlet & Effluent chambers, Overflow chamber, Screen channels with necessary screening arrangements (Trash & Coarse screen), Conveyors, Screening collection arrangement, Sluice gates, weir gates and Inlet & Overflow piping with fittings and Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.1.1 | Submission of Drawing | 1 | LS | 35000 |  |  |  | 4200 | 39200
4 | 1.3.1.2 | Approval on Code B | 1 | LS | 105000 |  |  |  | 12600 | 117600
4 | 1.3.1.3 | Approval on Code A | 1 | LS | 35000 |  |  |  | 4200 | 39200
3 | 1.3.2 | Wet well with superstructure & Pumping system , Submersible pumps with suitable valves and piping arrangements and Hardware and all allied works complete | 1 | LS
4 | 1.3.2.1 | Submission of Drawing | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.3.2.2 | Approval on Code B | 1 | LS | 90000 |  |  |  | 10800 | 100800
4 | 1.3.2.3 | Approval on Code A | 1 | LS | 30000 |  |  |  | 3600 | 33600
3 | 1.3.3 | Material Handling system with suitable Cranes and hoist arrangements with Hardware and all allied works complete | 1 | LS
4 | 1.3.3.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.3.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.3.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.4 | Miscellaneous works such as flushing arrangements, dewatering and ventilation system including Hardware all allied works complete | 1 | LS
4 | 1.3.4.1 | Submission of Drawing | 1 | LS | 10000 |  |  |  | 1200 | 11200
4 | 1.3.4.2 | Approval on Code B | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.3.4.3 | Approval on Code A | 1 | LS | 10000 |  |  |  | 1200 | 11200
|  | STP | 1 | LS
3 | 1.3.5 | Inlet chamber and Fine Screen Channel, Overflow chamber, Screen Effluent/ Grit Basin Distribution Channel with Sluice gates, weir gates, Stop logs, Inlet & Overflow piping with fittings, flushing arrangement, including Hardware and all allied works complete | 1 | LS
4 | 1.3.5.1 | Submission of Drawing | 1 | LS | 16000 |  |  |  | 1920 | 17920
4 | 1.3.5.2 | Approval on Code B | 1 | LS | 48000 |  |  |  | 5760 | 53760
4 | 1.3.5.3 | Approval on Code A | 1 | LS | 16000 |  |  |  | 1920 | 17920
3 | 1.3.6 | Screen chamber with effluent channel, drain piping and Fine screening, Conveyors, Screening collection arrangement, flushing arrangement, including Hardware and all allied works complete | 1 | LS
4 | 1.3.6.1 | Submission of Drawing | 1 | LS | 14000 |  |  |  | 1680 | 15680
4 | 1.3.6.2 | Approval on Code B | 1 | LS | 42000 |  |  |  | 5040 | 47040
4 | 1.3.6.3 | Approval on Code A | 1 | LS | 14000 |  |  |  | 1680 | 15680
3 | 1.3.7 | Vortex Grit mechanism with grit classifier & washing mechanism, Conveyors, Grit collection arrangement, sluice gates, Stop logs, flushing arrangement, including Hardware and all allied works complete | 1 | LS
4 | 1.3.7.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.7.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.7.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.8 | Aeration Basin with Aeration arrangement with piping, Sluice gates and weir gates, Stop logs, flushing arrangement, including Hardware and all allied works complete | 1 | LS
4 | 1.3.8.1 | Submission of Drawing | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.3.8.2 | Approval on Code B | 1 | LS | 90000 |  |  |  | 10800 | 100800
4 | 1.3.8.3 | Approval on Code A | 1 | LS | 30000 |  |  |  | 3600 | 33600
3 | 1.3.9 | Anaerobic Zone Inlet arrangement including pipework, Submersible mixer arrangement and Material Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.9.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.9.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.9.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.10 | Anoxic zone Inlet arrangement including pipework, Submersible mixer arrangement and Material Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.10.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.10.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.10.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.11 | Deareation zone Inlet arrangement Inlet arrangement including pipework, Submersible mixer arrangement and Material Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.11.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.11.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.11.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.12 | Aeration Zone with MLR Pumpsets, Retrievable type Fine Bubble Diffuser Aeration system arrangement, Pipe grid, Drop legs, piping arrangements, Drain pumpsets, Electric hoist, sluice gates, flushing arrangement, Material Handling Equipment, piping and valves including Hardware and all allied works complete | 1 | LS
4 | 1.3.12.1 | Submission of Drawing | 1 | LS | 18000 |  |  |  | 2160 | 20160
4 | 1.3.12.2 | Approval on Code B | 1 | LS | 54000 |  |  |  | 6480 | 60480
4 | 1.3.12.3 | Approval on Code A | 1 | LS | 18000 |  |  |  | 2160 | 20160
3 | 1.3.13 | Process Air Blower Building with blowers, Air Coolers, EOT Crane, Service water & blower cooling arrangement, Piping and valves, Material Handling Equipment, Ventilation system, Hardware and all allied works complete | 1 | LS
4 | 1.3.1.31 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.1.32 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.1.33 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.14 | Alum solution preparation and dosing which includes minimum of preparation and dosing pumpsets to feed maximum average doses efficiently, agitators, mixing arrangement, flushing arrangement, Channel mounted mixer for alum mixing,Material Handling Equipment, Ventilation system, Hardware with piping and all allied works complete including bulk storage tank and containment structure in case of a spill. | 1 | LS
4 | 1.3.14.1 | Submission of Drawing | 1 | LS | 14600 |  |  |  | 1752 | 16352
4 | 1.3.14.2 | Approval on Code B | 1 | LS | 43800 |  |  |  | 5256 | 49056
4 | 1.3.14.3 | Approval on Code A | 1 | LS | 14600 |  |  |  | 1752 | 16352
3 | 1.3.15 | Inlet & outlet piping, Distribution Chamber for Secondary Clarifiers with Inlet & Outlet sluice gates, stoplogs, weir arrangement, flushing arrangement, piping and valves including Hardware and all allied works complete | 1 | LS
4 | 1.3.15.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.15.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.15.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.16 | Inlet & Outlet piping, Secondary Clarifiers mechanism, Bridge, scum collection with desludging arrangements, Material Handling Equipment, flushing arrangement, piping and valves including Hardware and all allied works complete | 1 | LS
4 | 1.3.16.1 | Submission of Drawing | 1 | LS | 13000 |  |  |  | 1560 | 14560
4 | 1.3.16.2 | Approval on Code B | 1 | LS | 39000 |  |  |  | 4680 | 43680
4 | 1.3.16.3 | Approval on Code A | 1 | LS | 13000 |  |  |  | 1560 | 14560
3 | 1.3.17 | Inlet & Outlet piping, Disc Filter Influent & Effluent chamber sluice gates, Weir gates, Stoplogs, Disc Filter units with chemical cleaning arrangements.Backwash water system and collection arrangement etc and all allied works complete. | 1 | LS
4 | 1.3.17.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.17.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.17.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.18 | Material pumping station general arrangement,Pumpsets, flushing arrangement, Material Handling Equipment, Ventilation system, Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 1.3.18.1 | Submission of Drawing | 1 | LS | 13000 |  |  |  | 1560 | 14560
4 | 1.3.18.2 | Approval on Code B | 1 | LS | 39000 |  |  |  | 4680 | 43680
4 | 1.3.18.3 | Approval on Code A | 1 | LS | 13000 |  |  |  | 1560 | 14560
3 | 1.3.19 | Chlorine & any other chemical dosing arrangement, spill containment bund, flushing arrangement, Material Handling Equipment, Ventilation system, Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.19.1 | Submission of Drawing | 1 | LS | 18000 |  |  |  | 2160 | 20160
4 | 1.3.19.2 | Approval on Code B | 1 | LS | 54000 |  |  |  | 6480 | 60480
4 | 1.3.19.3 | Approval on Code A | 1 | LS | 18000 |  |  |  | 2160 | 20160
3 | 1.3.20 | Inlet & Outlet piping, Chlorine Contact Tank & Outfall structure with sluice gates, weir gates, Stop logs, mixing arrangement, hardware with piping, valves and all allied works complete, Disk filters. | 1 | LS
4 | 1.3.20.1 | Submission of Drawing | 1 | LS | 20000 |  |  |  | 2400 | 22400
4 | 1.3.20.2 | Approval on Code B | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.3.20.3 | Approval on Code A | 1 | LS | 20000 |  |  |  | 2400 | 22400
3 | 1.3.21 | Dewatering feed pumping system, Submersible mixer arrangement, Sludge feed Pumpsets, flushing arrangement, Ventilation system, Material Handling Equipment and Hardware with piping, valves and all allied works complete | 1 | LS
4 | 1.3.21.1 | Submission of Drawing | 1 | LS | 26000 |  |  |  | 3120 | 29120
4 | 1.3.21.2 | Approval on Code B | 1 | LS | 78000 |  |  |  | 9360 | 87360
4 | 1.3.21.3 | Approval on Code A | 1 | LS | 26000 |  |  |  | 3120 | 29120
3 | 1.3.22 | Polyelectrolyte dosing systems for sludge dewatering, stirrer arrangement, feeding arrangement, Preparation & Storage tanks, Dosing Pumpsets, flushing arrangement, Material Handling Equipment, Ventilation system, Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.22.1 | Submission of Drawing | 1 | LS | 15000 |  |  |  | 1800 | 16800
4 | 1.3.22.2 | Approval on Code B | 1 | LS | 45000 |  |  |  | 5400 | 50400
4 | 1.3.22.3 | Approval on Code A | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.3.23 | Sludge dewatering units, sludge cake conveying system with cut gate arrangement and hopper & Collection system, Material Handling Equipment for sludge dewatering units, flushing arrangement, Ventilation system, Hardware with piping and all allied works complete | 1 | LS
4 | 1.3.23.1 | Submission of Drawing | 1 | LS | 18000 |  |  |  | 2160 | 20160
4 | 1.3.23.2 | Approval on Code B | 1 | LS | 54000 |  |  |  | 6480 | 60480
4 | 1.3.23.3 | Approval on Code A | 1 | LS | 18000 |  |  |  | 2160 | 20160
3 | 1.3.24 | Inlet & Outlet piping, Plant Drain Sump and Pump Station, Submersible pumpsets, Material Handling Equipment,, Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 1.3.24.1 | Submission of Drawing | 1 | LS | 12000 |  |  |  | 1440 | 13440
4 | 1.3.24.2 | Approval on Code B | 1 | LS | 36000 |  |  |  | 4320 | 40320
4 | 1.3.24.3 | Approval on Code A | 1 | LS | 12000 |  |  |  | 1440 | 13440
3 | 1.3.25 | Inlet & Outlet piping, Treated water storage Pump Station, Submersible pumpsets, Material Handling Equipment, Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 1.3.25.1 | Submission of Drawing | 1 | LS | 18000 |  |  |  | 2160 | 20160
4 | 1.3.25.2 | Approval on Code B | 1 | LS | 54000 |  |  |  | 6480 | 60480
4 | 1.3.25.3 | Approval on Code A | 1 | LS | 18000 |  |  |  | 2160 | 20160
3 | 1.3.26 | Inlet & Outlet piping, Plant water Pump Station, Submersible pumpsets, Material Handling Equipment, Sluice gates, Weir gates, Stop log gates,Hardware with piping, Valves, All Plant Piping works and all allied works complete | 1 | LS
4 | 1.3.26.1 | Submission of Drawing | 1 | LS | 18000 |  |  |  | 2160 | 20160
4 | 1.3.26.2 | Approval on Code B | 1 | LS | 54000 |  |  |  | 6480 | 60480
4 | 1.3.26.3 | Approval on Code A | 1 | LS | 18000 |  |  |  | 2160 | 20160
3 | 1.3.27 | Flushing arrangement for all chemical & Sludge Material Handling systems, Dewatering Pumps including piping and all allied works in all sludge & Chemical Material Handling pump houses complete | 1 | LS
4 | 1.3.27.1 | Submission of Drawing | 1 | LS | 18000 |  |  |  | 2160 | 20160
4 | 1.3.27.2 | Approval on Code B | 1 | LS | 54000 |  |  |  | 6480 | 60480
4 | 1.3.27.3 | Approval on Code A | 1 | LS | 18000 |  |  |  | 2160 | 20160
3 | 1.3.28 | Service water system including pumps with Hardware, piping, Valves and all allied works complete | 1 | LS
4 | 1.3.28.1 | Submission of Drawing | 1 | LS | 10000 |  |  |  | 1200 | 11200
4 | 1.3.28.2 | Approval on Code B | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.3.28.3 | Approval on Code A | 1 | LS | 10000 |  |  |  | 1200 | 11200
3 | 1.3.29 | Fire Fighting system for the whole plant (inclusive of fire alarm,fire detection,fire extinguishing system), Tools Kit, Air conditioning system for SCADA control room & Administration and Laboratory Building and all allied works complete. | 1 | LS
4 | 1.3.29.1 | Submission of Drawing | 1 | LS | 8000 |  |  |  | 960 | 8960
4 | 1.3.29.2 | Approval on Code B | 1 | LS | 24000 |  |  |  | 2880 | 26880
4 | 1.3.29.3 | Approval on Code A | 1 | LS | 8000 |  |  |  | 960 | 8960
3 | 1.3.30 | Any other works which Bidder feels necessary for project completion needs to be added including all essential Investigation, etc. required to complete the Works under 1.3 | 1 | LS
4 | 1.3.30.1 | Submission of Drawing | 1 | LS | 8000 |  |  |  | 960 | 8960
4 | 1.3.30.2 | Approval on Code B | 1 | LS | 24000 |  |  |  | 2880 | 26880
4 | 1.3.30.3 | Approval on Code A | 1 | LS | 8000 |  |  |  | 960 | 8960
Sub Total of 1.3 |  |  | 1 | LS
2 | 1.4 | Electrical Design, Drawings and Documents as defined in Volume 2 of Bidding Documents | 1 | LS
3 | 1.4.1 | Electrical System Design, Drawings & Documentation as per General Requirements of the Bid document for the followings : i) Single Line Diagram (HT & LT System) ii) Sizing calculations for 11kV Switchgear Panel, Transformers, DG Set, LT Panels (PCC/MCC), HT/LT Cables, Earthing etc. iii) Electrical Equipment Layout and GA Drawing iv) Cabling Layout for the Plant v) Lighting, Earthing and Lightning layout vi) Guaranteed Technical particulars (GTP) of all equipment vII) Any other necessary document which bidder's feels necessary for project completion needs to be added including all calculations etc. required to complete the Works. | 1 | LS
4 | 1.4.1.1 | Submission of Drawing | 1 | LS | 143628 |  |  |  | 17235.4 | 160863.4
4 | 1.4.1.2 | Approval on Code B | 1 | LS | 430884 |  |  |  | 51706.2 | 482590.2
4 | 1.4.1.3 | Approval on Code A | 1 | LS | 143628 |  |  |  | 17235.4 | 160863.4
|  | Sub Total of 1.4 | 1 | LS
2 | 1.5 | Instrumentation, Control, and Automation Design, Drawings and Documentation as defined in Volume 2 of Bidding Document | 1 | LS
3 | 1.5.1 | Instrumentation, Control, Automation inclusive of complete field instrumentation,Real time online water quality monitoring systems ,Auto samplers,PLC based SCADA system-Functional design specifications (FDS) for Instrumentation ,FDS for Control & Automation systems,all other equipment required as per specifications,FAT Reports,SAT reports,Interoperability test reports, and all allied works complete as required under the specifications. | 1 | LS
4 | 1.5.1.1 | Submission of Drawing | 1 | LS | 80000 |  |  |  | 9600 | 89600
4 | 1.5.1.2 | Approval on Code B | 1 | LS | 240000 |  |  |  | 28800 | 268800
4 | 1.5.1.3 | Approval on Code A | 1 | LS | 80000 |  |  |  | 9600 | 89600
3 | 1.5.2 | MIS system- ( MIS system shall provide a digital platform for monitoring the project status remotely for all STP's and ISPS under this contract, inclusive of online document management system. The MIS system shall enable real time project status monitoring and shall provide a real time project dashboard to BWSSB and Project Management Consultants ) | 1 | LS
4 | 1.5.2.1 | Scope finalization | 1 | LS | 39600 |  |  |  | 4752 | 44352
4 | 1.5.2.2 | Implementation | 1 | LS | 118800 |  |  |  | 14256 | 133056
4 | 1.5.2.3 | Integartion | 1 | LS | 39600 |  |  |  | 4752 | 44352
Sub Total of 1.5 |  |  | 1 | LS
2 | 1.6 | Tests on Completion of Design-Build as defined in Volume 2 of Bidding Document | 1 | LS
3 | 1.6.1 | For Effluent Quality | 1 | LS
4 | 1.6.1.1 | Submission of Document | 1 | LS | 60000 |  |  |  | 7200 | 67200
4 | 1.6.1.2 | Approval of document | 1 | LS | 90000 |  |  |  | 10800 | 100800
3 | 1.6.2 | For Sludge Quality | 1 | LS
4 | 1.6.2.1 | Submission of Document | 1 | LS | 36000 |  |  |  | 4320 | 40320
4 | 1.6.2.2 | Approval of document | 1 | LS | 90000 |  |  |  | 10800 | 100800
Sub Total of 1.6 |  |  | 1 | LS
|  |  | 1 | LS
2 | 1.7 | Tests prior to Contract Completion as defined in Volume 2 of Bidding Document | 1 | LS
3 | 1.7.1 | For Effluent Quality | 1 | LS
3 | 1.7.2 | For Sludge Quality | 1 | LS
Sub Total of 1.7 |  |  | 1 | LS
2 | 1.8 | As Built Drawings | 1 | LS
3 | 1.8.1 | Civil, Structural & Building Works and piping | 1 | LS
4 | 1.8.1.1 | Submission of Document | 1 | LS | 40000 |  |  |  | 4800 | 44800
4 | 1.8.1.2 | Approval of document | 1 | LS | 60000 |  |  |  | 7200 | 67200
3 | 1.8.2 | Mechanical systems | 1 | LS
4 | 1.8.2.1 | Submission of Document | 1 | LS | 30000 |  |  |  | 3600 | 33600
4 | 1.8.2.2 | Approval of document | 1 | LS | 45000 |  |  |  | 5400 | 50400
3 | 1.8.3 | Electrical systems | 1 | LS
4 | 1.8.3.1 | Submission of Document | 1 | LS | 14000 |  |  |  | 1680 | 15680
4 | 1.8.3.2 | Approval of document | 1 | LS | 21000 |  |  |  | 2520 | 23520
3 | 1.8.4 | Instrumentation systems & MIS System Hardware | 1 | LS
4 | 1.8.4.1 | Submission of Document | 1 | LS | 10000 |  |  |  | 1200 | 11200
4 | 1.8.4.2 | Approval of document | 1 | LS | 15000 |  |  |  | 1800 | 16800
3 | 1.8.5 | Control and Automation System | 1 | LS
4 | 1.8.5.1 | Submission of Document | 1 | LS | 10000 |  |  |  | 1200 | 11200
4 | 1.8.5.2 | Approval of document | 1 | LS | 15000 |  |  |  | 1800 | 16800
Sub Total of 1.8 |  |  | 1 | LS
2 | 1.9 | Other Documentation | 1 | LS
3 | 1.9.1 | Design Report of STP, ISPS & Networks | 1 | LS
4 | 1.9.1.1 | Submission of Report | 1 | LS | 16800 |  |  |  | 2016 | 18816
4 | 1.9.1.2 | Approval | 1 | LS | 25200 |  |  |  | 3024 | 28224
3 | 1.9.2 | Surge Analysis of Pumping Mains,SAT & FAT reports | 1 | LS
4 | 1.9.2.1 | Submission of Report | 1 | LS | 9200 |  |  |  | 1104 | 10304
4 | 1.9.2.2 | Approval | 1 | LS | 13800 |  |  |  | 1656 | 15456
3 | 1.9.3 | Concept of Civil Design Report | 1 | LS
4 | 1.9.3.1 | Submission of Report | 1 | LS | 4000 |  |  |  | 480 | 4480
4 | 1.9.3.2 | Approval | 1 | LS | 6000 |  |  |  | 720 | 6720
3 | 1.9.4 | Fault level calculations and Load flow studies & SCADA Manual | 1 | LS
4 | 1.9.4.1 | Submission of Report | 1 | LS | 4000 |  |  |  | 480 | 4480
4 | 1.9.4.2 | Approval | 1 | LS | 6000 |  |  |  | 720 | 6720
3 | 1.9.5 | Operation & Maintenance Manuals | 1 | LS
4 | 1.9.5.1 | Submission of Manuals | 1 | LS | 6000 |  |  |  | 720 | 6720
4 | 1.9.5.2 | Approval | 1 | LS | 9000 |  |  |  | 1080 | 10080
3 | 1.9.6 | Training Programme and Manuals | 1 | LS
4 | 1.9.6.1 | Submission of Manuals | 1 | LS | 4000 |  |  |  | 480 | 4480
4 | 1.9.6.2 | Approval | 1 | LS | 6000 |  |  |  | 720 | 6720
3 | 1.9.7 | Energy Optimization Plan | 1 | LS
4 | 1.9.7.1 | Submission of | 1 | LS | 4000 |  |  |  | 480 | 4480
4 | 1.9.7.2 | Approval | 1 | LS | 6000 |  |  |  | 720 | 6720
Sub Total of 1. 9
| 1.1 | Bidder shall list here details of additional items required
Sub Total 1.10
Total Schedule 1 (Sub total 1.1+ sub total 1.2+ sub total 1.3+ sub total 1.4+1.5+1.6+1.7+1.8+1.9+1.10) Carried to Schedule 1 - Grand Summary of DODDABETTAHALLI STP

## Schedule 2
7 MLD STP at Doddabettahalli
Schedule 2: Civil Works, Installations, Testing & Commissioning and Other Services
Level | Item No. | Description | Quantity | Unit | Price in INR | Duties | EX. Work | Local Transport | GST in INR | Total Price including GST in INR
2 | 2.1 | TSPS Works (Sewage Retaining Structure) | 1 | LS
3 | 2.1.1 | Inlet manhole & chamber, Screen channels, Effluent chamber, Overflow chamber, Wetwell with superstructure, Pump House, Valve & Flowmeter chambers, Thrust block and Anchor blocks, Epoxy painting etc. | 1 | LS
4 | 2.1.1.1 | Inlet chamber, screen channel, Effluent chamber & over flow chamber | 1 | LS
5 | 2.1.1.1.1 | Excavation | 1 | LS | 243852 |  |  |  | 29262.24 | 273114.24
5 | 2.1.1.1.2 | PCC | 1 | LS | 121926 |  |  |  | 14631.12 | 136557.12
5 | 2.1.1.1.3 | RCC Raft | 1 | LS | 975408 |  |  |  | 117048.96 | 1092456.96
5 | 2.1.1.1.4 | RCC walls | 1 | LS | 463318.8 |  |  |  | 55598.256 | 518917.056
5 | 2.1.1.1.5 | RCC beams, Slab/Walkway | 1 | LS | 243852 |  |  |  | 29262.24 | 273114.24
5 | 2.1.1.1.6 | Back Filling | 1 | LS | 24385.2 |  |  |  | 2926.224 | 27311.424
5 | 2.1.1.1.7 | Hydro Test | 1 | LS | 121926 |  |  |  | 14631.12 | 136557.12
5 | 2.1.1.1.8 | Finishing, Protective coating measures. | 1 | LS | 121926 |  |  |  | 14631.12 | 136557.12
5 | 2.1.1.1.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 121926 |  |  |  | 14631.12 | 136557.12
4 | 2.1.1.2 | Wet Well - Well shrinking | 1 | LS
5 | 2.1.1.2.1 | Excavation & levling of site | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
5 | 2.1.1.2.2 | Fabrication and instalation of MS Cutting edge as per the approved drawing | 1 | LS | 512089.2 |  |  |  | 61450.704 | 573539.904
|  | Sinking of RCC Well as per approved drawing | 1 | LS
5 | 2.1.1.2.3 | 0-2 meters depth | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
5 | 2.1.1.2.4 | 2-4 meters depth | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
5 | 2.1.1.2.5 | 4-5 meters depth | 1 | LS | 438933.6 |  |  |  | 52672.032 | 491605.632
5 | 2.1.1.2.6 | 5-6 meters depth | 1 | LS | 438933.6 |  |  |  | 52672.032 | 491605.632
5 | 2.1.1.2.7 | 6-7 meters depth | 1 | LS | 438933.6 |  |  |  | 52672.032 | 491605.632
5 | 2.1.1.2.8 | 7-8 meters depth | 1 | LS | 512089.2 |  |  |  | 61450.704 | 573539.904
5 | 2.1.1.2.9 | 8-9 meters depth | 1 | LS | 585244.8 |  |  |  | 70229.376 | 655474.176
5 | 2.1.1.2.10 | Soling with PCC piug concrete | 1 | LS | 731556 |  |  |  | 87786.72 | 819342.72
5 | 2.1.1.2.11 | RCC bottom Raft | 1 | LS | 731556 |  |  |  | 87786.72 | 819342.72
5 | 2.1.1.2.12 | RCC Partition wall | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
5 | 2.1.1.2.13 | RCC Roof with necessary beams, Slab/Walkway | 1 | LS | 731556 |  |  |  | 87786.72 | 819342.72
5 | 2.1.1.2.14 | Finishing, Protective coating measures. | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
5 | 2.1.1.2.15 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
4 | 2.1.1.3 | Pump House | 1 | LS
5 | 2.1.1.3.1 | Column above base slab upto roof level | 1 | LS | 182889 |  |  |  | 21946.68 | 204835.68
5 | 2.1.1.3.2 | Roof slab with beam | 1 | LS | 243852 |  |  |  | 29262.24 | 273114.24
5 | 2.1.1.3.3 | Block work | 1 | LS | 365778 |  |  |  | 43893.36 | 409671.36
5 | 2.1.1.3.4 | Plastering work | 1 | LS | 304815 |  |  |  | 36577.8 | 341392.8
5 | 2.1.1.3.5 | Finishing, Protective coating measures. | 1 | LS | 60963 |  |  |  | 7315.56 | 68278.56
5 | 2.1.1.3.6 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 60963 |  |  |  | 7315.56 | 68278.56
4 | 2.1.1.4 | RCC Valve chamber & Flow meter chamber | 1 | LS
5 | 2.1.1.4.1 | Excavation | 1 | LS | 121926 |  |  |  | 14631.12 | 136557.12
5 | 2.1.1.4.2 | PCC | 1 | LS | 60963 |  |  |  | 7315.56 | 68278.56
5 | 2.1.1.4.3 | RCC Raft | 1 | LS | 487704 |  |  |  | 58524.48 | 546228.48
5 | 2.1.1.4.4 | RCC walls | 1 | LS | 231659.4 |  |  |  | 27799.128 | 259458.528
5 | 2.1.1.4.5 | RCC beams, Slab/Walkway | 1 | LS | 121926 |  |  |  | 14631.12 | 136557.12
5 | 2.1.1.4.6 | Back Filling | 1 | LS | 12192.6 |  |  |  | 1463.112 | 13655.712
5 | 2.1.1.4.7 | Hydro Test | 1 | LS | 60963 |  |  |  | 7315.56 | 68278.56
5 | 2.1.1.4.8 | Finishing, Protective coating measures. | 1 | LS | 60963 |  |  |  | 7315.56 | 68278.56
5 | 2.1.1.4.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 60963 |  |  |  | 7315.56 | 68278.56
|  | Inlet Works | 1 | LS
3 | 2.1.2 | Inlet Chamber, Fine Screen Channel, Screen Effluent/ Grit Basin Distribution Channel, chambers,RCC Stair case etc. (Sewage Retaining Structure) | 1 | LS
4 | 2.1.2.1 | Excavation work for foundation / pile works | 1 | LS | 120030 |  |  |  | 14403.6 | 134433.6
4 | 2.1.2.2 | PCC | 1 | LS | 60015 |  |  |  | 7201.8 | 67216.8
4 | 2.1.2.3 | RCC Raft /Pile / Footings | 1 | LS | 480120 |  |  |  | 57614.4 | 537734.4
4 | 2.1.2.4 | RCC Walls | 1 | LS | 228057 |  |  |  | 27366.84 | 255423.84
4 | 2.1.2.5 | RCC Roof beams, Slab/Walkway | 1 | LS | 120030 |  |  |  | 14403.6 | 134433.6
4 | 2.1.2.6 | Back Filling | 1 | LS | 12003 |  |  |  | 1440.36 | 13443.36
4 | 2.1.2.7 | Hydro Test | 1 | LS | 60015 |  |  |  | 7201.8 | 67216.8
4 | 2.1.2.8 | Finishing, Protective coating measures. | 1 | LS | 60015 |  |  |  | 7201.8 | 67216.8
4 | 2.1.2.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 60015 |  |  |  | 7201.8 | 67216.8
3 | 2.1.3 | Vortex Grit Basins & chamber, Grit Basin effluent channel, Grit Classifier arrangement,chambers,RCC Stair case etc. (Sewage Retaining Structure) | 1 | LS
4 | 2.1.3.1 | Excavation work for foundation / pile works | 1 | LS | 77920 |  |  |  | 9350.4 | 87270.4
4 | 2.1.3.2 | PCC | 1 | LS | 38960 |  |  |  | 4675.2 | 43635.2
4 | 2.1.3.3 | RCC Raft /Footings /Pile | 1 | LS | 311680 |  |  |  | 37401.6 | 349081.6
4 | 2.1.3.4 | RCC Walls | 1 | LS | 148048 |  |  |  | 17765.76 | 165813.76
4 | 2.1.3.5 | RCC Roof beams, Slab/Walkway | 1 | LS | 77920 |  |  |  | 9350.4 | 87270.4
4 | 2.1.3.6 | Back Filling | 1 | LS | 7792 |  |  |  | 935.04 | 8727.04
4 | 2.1.3.7 | Hydro Test | 1 | LS | 38960 |  |  |  | 4675.2 | 43635.2
4 | 2.1.3.8 | Finishing, Protective coating measures. | 1 | LS | 38960 |  |  |  | 4675.2 | 43635.2
4 | 2.1.3.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 38960 |  |  |  | 4675.2 | 43635.2
3 | 2.1.4 | Parshall Flume, drop chamber, connecting arrangement from Inlet works to Aeration basin,RCC Stair case etc. (Sewage Retaining Structure) | 1 | LS
4 | 2.1.4.1 | Excavation work for foundation / pile works | 1 | LS | 85890 |  |  |  | 10306.8 | 96196.8
4 | 2.1.4.2 | PCC | 1 | LS | 42945 |  |  |  | 5153.4 | 48098.4
4 | 2.1.4.3 | RCC Raft /Footings /Pile | 1 | LS | 343560 |  |  |  | 41227.2 | 384787.2
4 | 2.1.4.4 | RCC Walls | 1 | LS | 163191 |  |  |  | 19582.92 | 182773.92
4 | 2.1.4.5 | RCC Roof beams, Slab/Walkway | 1 | LS | 85890 |  |  |  | 10306.8 | 96196.8
4 | 2.1.4.6 | Back Filling | 1 | LS | 8589 |  |  |  | 1030.68 | 9619.68
4 | 2.1.4.7 | Hydro Test | 1 | LS | 42945 |  |  |  | 5153.4 | 48098.4
4 | 2.1.4.8 | Finishing, Protective coating measures. | 1 | LS | 42945 |  |  |  | 5153.4 | 48098.4
4 | 2.1.4.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 42945 |  |  |  | 5153.4 | 48098.4
|  | AERATION BASINS (Sewage Retaining Structure) | 1 | LS
3 | 2.1.5 | Aeration Basin flow distribution channel, Anaerobic Zones, Anoxic Zones, Aeration Zones, Aeration Basin Effluent Channel, MLR Feed, RAS inlet arrangement, Valve & flowmeter chamber, Overflow & Bypass chamber,RCC Stair case etc. | 1 | LS
4 | 2.1.5.1 | SBR TANK | 1 | LS
5 | 2.1.5.1.1 | Excavation work for foundation / pile works | 1 | LS | 4378890 |  |  |  | 525466.8 | 4904356.8
5 | 2.1.5.1.2 | PCC with bottom solling | 1 | LS | 2189445 |  |  |  | 262733.4 | 2452178.4
5 | 2.1.5.1.3 | RCC Raft /Footings /Pile | 1 | LS | 17515560 |  |  |  | 2101867.2 | 19617427.2
5 | 2.1.5.1.4 | RCC walls & Columns | 1 | LS | 8319891 |  |  |  | 998386.92 | 9318277.92
5 | 2.1.5.1.5 | RCC beams & Walkway | 1 | LS | 4378890 |  |  |  | 525466.8 | 4904356.8
5 | 2.1.5.1.6 | Back Filling | 1 | LS | 437889 |  |  |  | 52546.68 | 490435.68
5 | 2.1.5.1.7 | Hydro Test | 1 | LS | 2189445 |  |  |  | 262733.4 | 2452178.4
5 | 2.1.5.1.8 | Finishing, Protective coating measures. | 1 | LS | 2189445 |  |  |  | 262733.4 | 2452178.4
5 | 2.1.5.1.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 2189445 |  |  |  | 262733.4 | 2452178.4
|  | BLOWER BUILDING | 1 | LS
3 | 2.1.6 | Process Air Blower Building, Valve chamber, Supports for air piping,RCC Stair case etc. | 1 | LS
4 | 2.1.6.1 | Excavation work for foundation / pile works | 1 | LS | 577530 |  |  |  | 69303.6 | 646833.6
4 | 2.1.6.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 288765 |  |  |  | 34651.8 | 323416.8
4 | 2.1.6.3 | RCC Raft /Footings /Pile | 1 | LS | 1443825 |  |  |  | 173259 | 1617084
4 | 2.1.6.4 | Column & Walls | 1 | LS | 1155060 |  |  |  | 138607.2 | 1293667.2
4 | 2.1.6.5 | RCC Roof Slab & Beams | 1 | LS | 1155060 |  |  |  | 138607.2 | 1293667.2
4 | 2.1.6.6 | Block work and Plastering | 1 | LS | 577530 |  |  |  | 69303.6 | 646833.6
4 | 2.1.6.7 | Finishing, Protective coating measures. | 1 | LS | 288765 |  |  |  | 34651.8 | 323416.8
4 | 2.1.6.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 288765 |  |  |  | 34651.8 | 323416.8
|  | SECONDARY CLARIFIERS (Sewage Retaining Structure) | 1 | LS
3 | 2.1.7 | Inlet arrangements from aeration basin outlet, Secondary Clarifier Distribution boxes, Secondary Clarifiers, Scum collection pit, Desludging valve chamber, RCC Stair case etc. any other items for necessary completion of works | 1 | LS
3 | 2.1.8 | RAS pumping station including Valve & flowmeter chambers,RCC Stair case etc. | 1 | LS
4 | 2.1.8.1 | WAS pump house (Inbuild of SBR tank) | 1 | LS
5 | 2.1.8.1.1 | Excavation work for foundation / pile works | 1 | LS | 163940 |  |  |  | 19672.8 | 183612.8
5 | 2.1.8.1.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 81970 |  |  |  | 9836.4 | 91806.4
5 | 2.1.8.1.3 | RCC Raft /Footings / piles works | 1 | LS | 655760 |  |  |  | 78691.2 | 734451.2
5 | 2.1.8.1.4 | RCC Walls | 1 | LS | 311486 |  |  |  | 37378.32 | 348864.32
5 | 2.1.8.1.5 | RCC Staircase | 1 | LS | 163940 |  |  |  | 19672.8 | 183612.8
5 | 2.1.8.1.7 | Back Filling | 1 | LS | 16394 |  |  |  | 1967.28 | 18361.28
5 | 2.1.8.1.8 | Hydro Test | 1 | LS | 81970 |  |  |  | 9836.4 | 91806.4
5 | 2.1.8.1.9 | Finishing, Protective coating measures. | 1 | LS | 81970 |  |  |  | 9836.4 | 91806.4
5 | 2.1.8.1.10 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 81970 |  |  |  | 9836.4 | 91806.4
|  | Chlorine Contact Tank (Sewage Retaining Structure) | 1 | LS
3 | 2.1.9 | Chlorine Contact Tank, Inlet chamber, distribution chamber, Effluent Channel/pipe, flowmeter chamber,RCC Stair case, Outfall Structure etc | 1 | LS
4 | 2.1.9.1 | Excavation work for foundation / pile works | 1 | LS | 685760 |  |  |  | 82291.2 | 768051.2
4 | 2.1.9.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 342880 |  |  |  | 41145.6 | 384025.6
4 | 2.1.9.3 | RCC Raft /Footings / piles works | 1 | LS | 2743040 |  |  |  | 329164.8 | 3072204.8
4 | 2.1.9.4 | RCC Walls | 1 | LS | 1302944 |  |  |  | 156353.28 | 1459297.28
4 | 2.1.9.5 | RCC partation wall | 1 | LS | 685760 |  |  |  | 82291.2 | 768051.2
4 | 2.1.9.6 | Back Filling | 1 | LS | 68576 |  |  |  | 8229.12 | 76805.12
4 | 2.1.9.7 | Hydro Test | 1 | LS | 342880 |  |  |  | 41145.6 | 384025.6
4 | 2.1.9.8 | Finishing, Protective coating measures. | 1 | LS | 342880 |  |  |  | 41145.6 | 384025.6
4 | 2.1.9.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 342880 |  |  |  | 41145.6 | 384025.6
3 | 2.1.10 | Chlorine and alum building etc and any other chemicals required as per process design etc | 1 | LS
4 | 2.1.10.1 | Chlorine building | 1 | LS
5 | 2.1.10.1.1 | Excavation work for foundation / pile works | 1 | LS | 423642 |  |  |  | 50837.04 | 474479.04
5 | 2.1.10.1.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 211821 |  |  |  | 25418.52 | 237239.52
5 | 2.1.10.1.3 | RCC Raft /Footings /Pile | 1 | LS | 1059105 |  |  |  | 127092.6 | 1186197.6
5 | 2.1.10.1.4 | Column & Walls | 1 | LS | 847284 |  |  |  | 101674.08 | 948958.08
5 | 2.1.10.1.5 | RCC Roof Slab & Beams | 1 | LS | 847284 |  |  |  | 101674.08 | 948958.08
5 | 2.1.10.1.6 | Block work and Plastering | 1 | LS | 423642 |  |  |  | 50837.04 | 474479.04
5 | 2.1.10.1.7 | Finishing, Protective coating measures. | 1 | LS | 211821 |  |  |  | 25418.52 | 237239.52
5 | 2.1.10.1.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 211821 |  |  |  | 25418.52 | 237239.52
4 | 2.1.10.2 | Alum building | 1 | LS
5 | 2.1.10.2.1 | Excavation work for foundation / pile works | 1 | LS | 282428 |  |  |  | 33891.36 | 316319.36
5 | 2.1.10.2.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 141214 |  |  |  | 16945.68 | 158159.68
5 | 2.1.10.2.3 | RCC Raft /Footings /Pile | 1 | LS | 706070 |  |  |  | 84728.4 | 790798.4
5 | 2.1.10.2.4 | Column & Walls | 1 | LS | 564856 |  |  |  | 67782.72 | 632638.72
5 | 2.1.10.2.5 | RCC Roof Slab & Beams | 1 | LS | 564856 |  |  |  | 67782.72 | 632638.72
5 | 2.1.10.2.6 | Block work and Plastering | 1 | LS | 282428 |  |  |  | 33891.36 | 316319.36
5 | 2.1.10.2.7 | Finishing, Protective coating measures. | 1 | LS | 141214 |  |  |  | 16945.68 | 158159.68
5 | 2.1.10.2.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 141214 |  |  |  | 16945.68 | 158159.68
3 | 2.1.11 | Plant water & Treated water storage sump / Pump Station and inlet flow arrangement, chamber etc. | 1 | LS
4 | 2.1.11.1 | Plant water & Treated water storage sump | 1 | LS
5 | 2.1.11.1.1 | Excavation work for foundation / pile works | 1 | LS | 149720 |  |  |  | 17966.4 | 167686.4
5 | 2.1.11.1.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
5 | 2.1.11.1.3 | RCC Raft /Footings / piles works | 1 | LS | 598880 |  |  |  | 71865.6 | 670745.6
5 | 2.1.11.1.4 | RCC Walls | 1 | LS | 284468 |  |  |  | 34136.16 | 318604.16
5 | 2.1.11.1.5 | RCC partation wall / roof lab / walk way | 1 | LS | 149720 |  |  |  | 17966.4 | 167686.4
5 | 2.1.11.1.6 | Back Filling | 1 | LS | 14972 |  |  |  | 1796.64 | 16768.64
5 | 2.1.11.1.7 | Hydro Test | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
5 | 2.1.11.1.8 | Finishing, Protective coating measures. | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
5 | 2.1.11.1.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
4 | 2.1.11.2 | Plant water & Treated water Pump Station (Sewage Retaining Structure) | 1 | LS
5 | 2.1.11.2.1 | RCC columns up to lintel beam | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
5 | 2.1.11.2.2 | RCC Columns from lintel beam to Roof Slab | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
5 | 2.1.11.2.3 | Lintel Beams | 1 | LS | 37430 |  |  |  | 4491.6 | 41921.6
5 | 2.1.11.2.4 | RCC Roof Beams & slabs | 1 | LS | 74860 |  |  |  | 8983.2 | 83843.2
5 | 2.1.11.2.5 | Block work | 1 | LS | 37430 |  |  |  | 4491.6 | 41921.6
5 | 2.1.11.2.6 | Plastering | 1 | LS | 37430 |  |  |  | 4491.6 | 41921.6
5 | 2.1.11.2.7 | Finishing, Protective coating measures. | 1 | LS | 18715 |  |  |  | 2245.8 | 20960.8
5 | 2.1.11.2.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 18715 |  |  |  | 2245.8 | 20960.8
|  | Disc Filter (Sewage Retaining Structure) | 1 | LS
3 | 2.1.12 | Disc Filter Influent chamber, Disc Filter units and Disc Filter Effluent channel, Backwash water collection arrangement etc. | 1 | LS
4 | 2.1.12.1 | Excavation work for foundation / pile works | 1 | LS | 190270 |  |  |  | 22832.4 | 213102.4
4 | 2.1.12.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 95135 |  |  |  | 11416.2 | 106551.2
4 | 2.1.12.3 | RCC Raft /Footings / piles works | 1 | LS | 761080 |  |  |  | 91329.6 | 852409.6
4 | 2.1.12.4 | RCC Walls | 1 | LS | 361513 |  |  |  | 43381.56 | 404894.56
4 | 2.1.12.5 | RCC Channel / walk way | 1 | LS | 190270 |  |  |  | 22832.4 | 213102.4
4 | 2.1.12.6 | Back Filling | 1 | LS | 19027 |  |  |  | 2283.24 | 21310.24
4 | 2.1.12.7 | Hydro Test | 1 | LS | 95135 |  |  |  | 11416.2 | 106551.2
4 | 2.1.12.8 | Finishing, Protective coating measures. | 1 | LS | 95135 |  |  |  | 11416.2 | 106551.2
4 | 2.1.12.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 95135 |  |  |  | 11416.2 | 106551.2
|  | SLUDGE DEWATERING | 1 | LS
3 | 2.1.13 | Sludge Dewatering Building including sludge storage, chambers etc. | 1 | LS
4 | 2.1.13.1 | Excavation work for foundation / pile works | 1 | LS | 522880 |  |  |  | 62745.6 | 585625.6
4 | 2.1.13.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 261440 |  |  |  | 31372.8 | 292812.8
4 | 2.1.13.3 | RCC Raft /Footings /Pile | 1 | LS | 1307200 |  |  |  | 156864 | 1464064
4 | 2.1.13.4 | Column & Walls | 1 | LS | 1045760 |  |  |  | 125491.2 | 1171251.2
4 | 2.1.13.5 | RCC Roof Slab & Beams | 1 | LS | 1045760 |  |  |  | 125491.2 | 1171251.2
4 | 2.1.13.6 | Block work and Plastering | 1 | LS | 522880 |  |  |  | 62745.6 | 585625.6
4 | 2.1.13.7 | Finishing, Protective coating measures. | 1 | LS | 261440 |  |  |  | 31372.8 | 292812.8
4 | 2.1.13.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 261440 |  |  |  | 31372.8 | 292812.8
3 | 2.1.14 | Dewatering Feed sump and Pumping Station, chambers etc. (Sewage Retaining Structure) | 1 | LS
4 | 2.1.14.1 | Dewatering Feed sump | 1 | LS
5 | 2.1.14.1.1 | Excavation work for foundation / pile works | 1 | LS | 160805 |  |  |  | 19296.6 | 180101.6
5 | 2.1.14.1.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 80402.5 |  |  |  | 9648.3 | 90050.8
5 | 2.1.14.1.3 | RCC Raft /Footings / piles works | 1 | LS | 643220 |  |  |  | 77186.4 | 720406.4
5 | 2.1.14.1.4 | RCC Walls | 1 | LS | 305529.5 |  |  |  | 36663.54 | 342193.04
5 | 2.1.14.1.5 | RCC partation wall / roof lsab / walk way/staircase | 1 | LS | 160805 |  |  |  | 19296.6 | 180101.6
5 | 2.1.14.1.6 | Hydro Test | 1 | LS | 16080.5 |  |  |  | 1929.66 | 18010.16
5 | 2.1.14.1.7 | Finishing, Protective coating measures. | 1 | LS | 80402.5 |  |  |  | 9648.3 | 90050.8
5 | 2.1.14.1.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 80402.5 |  |  |  | 9648.3 | 90050.8
4 | 2.1.14.2 | Pumping Station | 1 | LS
5 | 2.1.14.2.1 | Excavation work for foundation / pile works | 1 | LS | 160805 |  |  |  | 19296.6 | 180101.6
5 | 2.1.14.2.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 80402.5 |  |  |  | 9648.3 | 90050.8
5 | 2.1.14.2.3 | RCC Raft /Footings /Pile | 1 | LS | 402012.5 |  |  |  | 48241.5 | 450254
5 | 2.1.14.2.4 | Column & Walls | 1 | LS | 321610 |  |  |  | 38593.2 | 360203.2
5 | 2.1.14.2.5 | RCC Roof Slab & Beams | 1 | LS | 321610 |  |  |  | 38593.2 | 360203.2
5 | 2.1.14.2.6 | Block work and Plastering | 1 | LS | 160805 |  |  |  | 19296.6 | 180101.6
5 | 2.1.14.2.7 | Finishing, Protective coating measures. | 1 | LS | 80402.5 |  |  |  | 9648.3 | 90050.8
5 | 2.1.14.2.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 80402.5 |  |  |  | 9648.3 | 90050.8
3 | 2.1.15 | Scum Pit,Sump and Pump Station, Chamber etc. | 1 | LS
4 | 2.1.15.1 | Excavation work for foundation / pile works | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.3 | RCC Raft /Footings / piles works | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.4 | RCC Walls | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.5 | RCC columns | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.6 | Backfilling | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.7 | Hydro Test | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.8 | Finishing, Protective coating measures. | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.15.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 0 |  |  |  | 0 | 0
3 | 2.1.16 | Plant Drain Sump and Pump Station, Chamber etc. (Sewage Retaining Structure) | 1 | LS
4 | 2.1.16.1 | Excavation work for foundation / pile works | 1 | LS | 32460 |  |  |  | 3895.2 | 36355.2
4 | 2.1.16.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 16230 |  |  |  | 1947.6 | 18177.6
4 | 2.1.16.3 | RCC Raft /Footings / piles works | 1 | LS | 129840 |  |  |  | 15580.8 | 145420.8
4 | 2.1.16.4 | RCC Walls | 1 | LS | 61674 |  |  |  | 7400.88 | 69074.88
4 | 2.1.16.5 | RCC columns | 1 | LS | 32460 |  |  |  | 3895.2 | 36355.2
4 | 2.1.16.6 | Back Filling | 1 | LS | 3246 |  |  |  | 389.52 | 3635.52
4 | 2.1.16.7 | Hydro Test | 1 | LS | 16230 |  |  |  | 1947.6 | 18177.6
4 | 2.1.16.8 | Finishing, Protective coating measures. | 1 | LS | 16230 |  |  |  | 1947.6 | 18177.6
4 | 2.1.16.9 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 16230 |  |  |  | 1947.6 | 18177.6
|  | SUBSTATION FOR STP | 1 | LS
3 | 2.1.17 | Switch gear room, Electrical Sub station | 1 | LS
4 | 2.1.17.1 | Excavation work for foundation / pile works | 1 | LS | 365560 |  |  |  | 43867.2 | 409427.2
4 | 2.1.17.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 182780 |  |  |  | 21933.6 | 204713.6
4 | 2.1.17.3 | RCC Raft /Footings /Pile | 1 | LS | 913900 |  |  |  | 109668 | 1023568
4 | 2.1.17.4 | Column & Walls | 1 | LS | 731120 |  |  |  | 87734.4 | 818854.4
4 | 2.1.17.5 | RCC Roof Slab & Beams | 1 | LS | 731120 |  |  |  | 87734.4 | 818854.4
4 | 2.1.17.6 | Block work and Plastering | 1 | LS | 365560 |  |  |  | 43867.2 | 409427.2
4 | 2.1.17.7 | Finishing, Protective coating measures. | 1 | LS | 182780 |  |  |  | 21933.6 | 204713.6
4 | 2.1.17.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 182780 |  |  |  | 21933.6 | 204713.6
3 | 2.1.18 | Transformer yard | 1 | LS
4 | 2.1.18.1 | Earthwork for Foundation | 1 | LS | 177740 |  |  |  | 21328.8 | 199068.8
4 | 2.1.18.2 | PCC for yard | 1 | LS | 177740 |  |  |  | 21328.8 | 199068.8
4 | 2.1.18.3 | RCC sidewalls for cable trench, Earthing chambers & Transformer Foundation | 1 | LS | 177740 |  |  |  | 21328.8 | 199068.8
4 | 2.1.18.4 | Chain link fencing with angular supports including painting | 1 | LS | 177740 |  |  |  | 21328.8 | 199068.8
4 | 2.1.18.5 | Filling of 40mm and down sized jalli to the yard | 1 | LS | 88870 |  |  |  | 10664.4 | 99534.4
4 | 2.1.18.6 | Finishing, Protective coating measures. 1. Finching -3% 2. Gate- 2% | 1 | LS | 44435 |  |  |  | 5332.2 | 49767.2
4 | 2.1.18.7 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 44435 |  |  |  | 5332.2 | 49767.2
|  | UTILITY BUILDINGS | 1 | LS
3 | 2.1.19 | Plant D.G. Room | 1 | LS
4 | 2.1.19.1 | Excavation work for foundation / pile works | 1 | LS | 110250 |  |  |  | 13230 | 123480
4 | 2.1.19.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 55125 |  |  |  | 6615 | 61740
4 | 2.1.19.3 | RCC Raft /Footings /Pile | 1 | LS | 275625 |  |  |  | 33075 | 308700
4 | 2.1.19.4 | Column & Walls | 1 | LS | 220500 |  |  |  | 26460 | 246960
4 | 2.1.19.5 | RCC Roof Slab & Beams | 1 | LS | 220500 |  |  |  | 26460 | 246960
4 | 2.1.19.6 | Block work and Plastering | 1 | LS | 110250 |  |  |  | 13230 | 123480
4 | 2.1.19.7 | Finishing, Protective coating measures. | 1 | LS | 55125 |  |  |  | 6615 | 61740
4 | 2.1.19.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 55125 |  |  |  | 6615 | 61740
3 | 2.1.20 | Administration Cum Laboratory Building & SCADA building (Two Floors) (For SCADA control room ,refer Particular ICA requirements) | 1 | LS
4 | 2.1.20.1 | Excavation work for foundation / pile works | 1 | LS | 507770 |  |  |  | 60932.4 | 568702.4
4 | 2.1.20.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 253885 |  |  |  | 30466.2 | 284351.2
4 | 2.1.20.3 | RCC Raft /Footings /Pile | 1 | LS | 1269425 |  |  |  | 152331 | 1421756
4 | 2.1.20.4 | Column & Walls | 1 | LS | 1015540 |  |  |  | 121864.8 | 1137404.8
4 | 2.1.20.5 | RCC Roof Slab & Beams | 1 | LS | 1015540 |  |  |  | 121864.8 | 1137404.8
4 | 2.1.20.6 | Block work and Plastering | 1 | LS | 507770 |  |  |  | 60932.4 | 568702.4
4 | 2.1.20.7 | Finishing, Protective coating measures. | 1 | LS | 253885 |  |  |  | 30466.2 | 284351.2
4 | 2.1.20.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 253885 |  |  |  | 30466.2 | 284351.2
3 | 2.1.21 | Guard Room (Security Room) | 1 | LS
4 | 2.1.21.1 | Excavation work for foundation / pile works | 1 | LS | 45250 |  |  |  | 5430 | 50680
4 | 2.1.21.2 | PCC for Footings / floor / pile / plinth beam bottom | 1 | LS | 22625 |  |  |  | 2715 | 25340
4 | 2.1.21.3 | RCC Raft /Footings /Pile | 1 | LS | 113125 |  |  |  | 13575 | 126700
4 | 2.1.21.4 | Column & Walls | 1 | LS | 90500 |  |  |  | 10860 | 101360
4 | 2.1.21.5 | RCC Roof Slab & Beams | 1 | LS | 90500 |  |  |  | 10860 | 101360
4 | 2.1.21.6 | Block work and Plastering | 1 | LS | 45250 |  |  |  | 5430 | 50680
4 | 2.1.21.7 | Finishing, Protective coating measures. | 1 | LS | 22625 |  |  |  | 2715 | 25340
4 | 2.1.21.8 | After Successful testing trial run & Performance Guarantee test | 1 | LS | 22625 |  |  |  | 2715 | 25340
|  | OTHER UTILITIES | 1 | LS
3 | 2.1.22 | Roads & drains / Internal roads and landscaping | 1 | LS
4 | 2.1.22.1 | ROADS | 1 | LS
5 | 2.1.22.1.1 | Earth work excavation and formation of coarse grade granular sub base for roads | 1 | LS | 524544 |  |  |  | 62945.28 | 587489.28
5 | 2.1.22.1.2 | construction of wet mix macadam concrete mix for sub base on granular sub base | 1 | LS | 524544 |  |  |  | 62945.28 | 587489.28
5 | 2.1.22.1.3 | construction of bituminus macadam with 60/70 grade on prepared surface with coarse aggregade for base/ binding | 1 | LS | 786816 |  |  |  | 94417.92 | 881233.92
5 | 2.1.22.1.4 | construction of semi dense bituminus concrete with compacted with 5% bitumen 80/100 grade with MORTH for complete finishing of roads | 1 | LS | 786816 |  |  |  | 94417.92 | 881233.92
4 | 2.1.22.2 | DRAIN / Landscaping | 1 | LS
5 | 2.1.22.2.1 | Earth work excavation for drains | 1 | LS | 174848 |  |  |  | 20981.76 | 195829.76
5 | 2.1.22.2.2 | PCC & RCC for drain raft | 1 | LS | 349696 |  |  |  | 41963.52 | 391659.52
5 | 2.1.22.2.3 | RCC side walls | 1 | LS | 611968 |  |  |  | 73436.16 | 685404.16
5 | 2.1.22.2.4 | RCC Pipe for diversion work and other site misc works | 1 | LS | 611968 |  |  |  | 73436.16 | 685404.16
3 | 2.1.23 | Approach Road to STP, TSPS | 1 | LS
4 | 2.1.23.1 | Site Clearence including removing of vegetation | 1 | LS | 254640 |  |  |  | 30556.8 | 285196.8
4 | 2.1.23.2 | Filling of good earth and all other required works | 1 | LS | 1018560 |  |  |  | 122227.2 | 1140787.2
3 | 2.1.24 | Parking Shed | 1 | LS
4 | 2.1.24.1 | Earth work Excavation, Providing PCC | 1 | LS | 373760 |  |  |  | 44851.2 | 418611.2
4 | 2.1.24.2 | Supply of Materials and Fabrication | 1 | LS | 467200 |  |  |  | 56064 | 523264
4 | 2.1.24.3 | Erection, painting and finishing | 1 | LS | 93440 |  |  |  | 11212.8 | 104652.8
3 | 2.1.25 | Compound Wall with gates | 1 | LS
4 | 2.1.25.1 | Earth work excavation for column foundation | 1 | LS | 624360 |  |  |  | 74923.2 | 699283.2
4 | 2.1.25.2 | Piling for foundation | 1 | LS | 1248720 |  |  |  | 149846.4 | 1398566.4
4 | 2.1.25.3 | Providing sand and boulder filling, PCC,RCC column footing,columns and plinth beam. | 1 | LS | 1248720 |  |  |  | 149846.4 | 1398566.4
4 | 2.1.25.4 | Columns above ground level upto height of compund including fixing of angles for barbed wire fencing | 1 | LS | 1560900 |  |  |  | 187308 | 1748208
4 | 2.1.25.5 | Insertion of RC Precast Slab panels between columns | 1 | LS | 1248720 |  |  |  | 149846.4 | 1398566.4
4 | 2.1.25.6 | supply and fixing barbed wire fence, Fabrication and erection of MS Gate including painting. | 1 | LS | 312180 |  |  |  | 37461.6 | 349641.6
3 | 2.1.26 | Ground Improvement Plan, Site grading and Piling arrangement | 1 | LS
4 | 2.1.26.1 | Clearing of Bushed and cutting of trees | 1 | LS | 195955 |  |  |  | 23514.6 | 219469.6
4 | 2.1.26.2 | Embankment work and dewatering work | 1 | LS | 783820 |  |  |  | 94058.4 | 877878.4
4 | 2.1.26.3 | Filling of good earth / morum and formation | 1 | LS | 1371685 |  |  |  | 164602.2 | 1536287.2
4 | 2.1.26.4 | Piling arrangment | 1 | LS | 1567640 |  |  |  | 188116.8 | 1755756.8
3 | 2.1.27 | Nalla & flow diversion etc. | 1 | LS
4 | 2.1.27.1 | Earth work excavation and filling work | 1 | LS | 147360 |  |  |  | 17683.2 | 165043.2
4 | 2.1.27.2 | Formation of embankment on either side of Nalla | 1 | LS | 368400 |  |  |  | 44208 | 412608
4 | 2.1.27.3 | RCC pipe for diversion work and other site misc works | 1 | LS | 221040 |  |  |  | 26524.8 | 247564.8
3 | 2.1.28 | Gabion wall, Site retaining structure and pile foundation | 1 | LS
4 | 2.1.28.1 | Preperation of sub base /earthwork and filling | 1 | LS | 339080 |  |  |  | 40689.6 | 379769.6
4 | 2.1.28.2 | Placing of gabion side walls | 1 | LS | 0 |  |  |  | 0 | 0
4 | 2.1.28.3 | 1st layer | 1 | LS | 1525860 |  |  |  | 183103.2 | 1708963.2
4 | 2.1.28.4 | Final Layer | 1 | LS | 1525860 |  |  |  | 183103.2 | 1708963.2
3 | 2.1.29 | Additional Backfill for entire Project including approach road (if required) | 1 | LS
3 | 2.1.30 | Tree Plantation | 1 | LS
4 | 2.1.30.1 | Leveling of landscape area | 1 | LS | 135080 |  |  |  | 16209.6 | 151289.6
4 | 2.1.30.2 | Filling of red Earth and formation | 1 | LS | 202620 |  |  |  | 24314.4 | 226934.4
4 | 2.1.30.3 | Planting of grass and ornamental plants | 1 | LS | 337700 |  |  |  | 40524 | 378224
|  | The bidder shall list here details of any additional items (all area of the works) required for a complete installation | 1 | LS
| 2.1.31 |  | 1 | LS
| 2.1.32 |  | 1 | LS
| 2.1.33 |  | 1 | LS
Sub Total of 2.1 |  |  | 1 | LS
|  |  | 1 | LS
2 | 2.2 | Mechanical, Electrical Works and Instrumentation & Control Works | 1 | LS
|  | Complete Installation, testing and commissioning of Mechanical system as per the Bid specifications | 1 | LS
|  | TSPS | 1 | LS
3 | 2.2.1 | Inlet & Effluent chambers, Overflow chamber,Screen channels with necessary screening arrangements (Trash & Coarse screen), , Conveyors, Screening collection arrangement,Sluice gates, weir gates and Inlet & Overflow piping with fittings and Hardware with piping and all allied works complete | 1 | LS
4 | 2.2.1.1 | Screen | 1 | LS
5 | 2.2.1.1.1 | Successful Installation | 1 | LS | 283998.96 |  |  |  | 34079.92 | 318078.88
5 | 2.2.1.1.2 | Completion of testing. Trial run | 1 | LS | 81142.56 |  |  |  | 9737.12 | 90879.68
5 | 2.2.1.1.3 | Commissioing of equipment | 1 | LS | 40571.28 |  |  |  | 4868.56 | 45439.84
4 | 2.2.1.2 | Sluice gate | 1 | LS
5 | 2.2.1.2.1 | Successful Installation | 1 | LS | 35499.87 |  |  |  | 4259.99 | 39759.86
5 | 2.2.1.2.2 | Completion of testing. Trial run | 1 | LS | 10142.82 |  |  |  | 1217.14 | 11359.96
5 | 2.2.1.2.3 | Commissioing of equipment | 1 | LS | 5071.41 |  |  |  | 608.57 | 5679.98
4 | 2.2.1.3 | pipes, fittings | 1 | LS
5 | 2.2.1.3.1 | Successful Installation | 1 | LS | 35499.87 |  |  |  | 4259.99 | 39759.86
5 | 2.2.1.3.2 | Completion of testing. Trial run | 1 | LS | 10142.82 |  |  |  | 1217.14 | 11359.96
5 | 2.2.1.3.3 | Commissioing of equipment | 1 | LS | 5071.41 |  |  |  | 608.57 | 5679.98
3 | 2.2.2 | Wet well with superstructure & Pumping system with Submersible pumps with suitable valves and piping arrangements and Hardware and all allied works complete | 1 | LS
4 | 2.2.2.1 | Submersible pump | 1 | LS
5 | 2.2.2.1.1 | Successful Installation | 1 | LS | 70388.64 |  |  |  | 8447.04 | 78835.68
5 | 2.2.2.1.2 | Completion of testing. Trial run | 1 | LS | 20111.04 |  |  |  | 2413.44 | 22524.48
5 | 2.2.2.1.3 | Commissioing of equipment | 1 | LS | 10055.52 |  |  |  | 1206.72 | 11262.24
4 | 2.2.2.2 | Valves | 1 | LS
5 | 2.2.2.2.1 | Successful Installation | 1 | LS | 8798.58 |  |  |  | 1055.88 | 9854.46
5 | 2.2.2.2.2 | Completion of testing. Trial run | 1 | LS | 2513.88 |  |  |  | 301.68 | 2815.56
5 | 2.2.2.2.3 | Commissioing of equipment | 1 | LS | 1256.94 |  |  |  | 150.84 | 1407.78
4 | 2.2.2.3 | Pipes and Fittings | 1 | LS
5 | 2.2.2.3.1 | Successful Installation | 1 | LS | 8798.58 |  |  |  | 1055.88 | 9854.46
5 | 2.2.2.3.2 | Completion of testing. Trial run | 1 | LS | 2513.88 |  |  |  | 301.68 | 2815.56
5 | 2.2.2.3.3 | Commissioing of equipment | 1 | LS | 1256.94 |  |  |  | 150.84 | 1407.78
3 | 2.2.3 | Material handling system with suitable Cranes and hoist arrangements with Hardware and all allied works complete | 1 | LS
4 | 2.2.3.1 | Lifting arrangement | 1 | LS
5 | 2.2.3.1.1 | Successful Installation | 1 | LS | 31987.2 |  |  |  | 3838.8 | 35826
5 | 2.2.3.1.2 | Completion of testing. Trial run | 1 | LS | 9139.2 |  |  |  | 1096.8 | 10236
5 | 2.2.3.1.3 | Commissioing of equipment | 1 | LS | 4569.6 |  |  |  | 548.4 | 5118
3 | 2.2.4 | Miscellaneous works such as flushing arrangements,dewatering and ventilation system including Hardware all allied works complete | 1 | LS
4 | 2.2.4.1 | Dewatering pumps | 1 | LS
5 | 2.2.4.1.1 | Successful Installation | 1 | LS | 60671.8 |  |  |  | 7280.91 | 67952.71
5 | 2.2.4.1.2 | Completion of testing. Trial run | 1 | LS | 17334.8 |  |  |  | 2080.26 | 19415.06
5 | 2.2.4.1.3 | Commissioing of equipment | 1 | LS | 8667.4 |  |  |  | 1040.13 | 9707.53
4 | 2.2.4.2 | GI pipe and valves | 1 | LS
5 | 2.2.4.2.1 | Successful Installation | 1 | LS | 26002.2 |  |  |  | 3120.39 | 29122.59
5 | 2.2.4.2.2 | Completion of testing. Trial run | 1 | LS | 7429.2 |  |  |  | 891.54 | 8320.74
5 | 2.2.4.2.3 | Commissioing of equipment | 1 | LS | 3714.6 |  |  |  | 445.77 | 4160.37
3 | 2.2.5 | The bidder shall list here details of any additional items (all area of the works) required for a complete installation | 1 | LS
|  | STP | 1 | LS
3 | 2.2.6 | Inlet chamber and Fine Screen Channel, Overflow chamber, Screen Effluent/ Grit Basin Distribution Channel with Sluice gates, weir gates,Stop logs, and Inlet & Overflow piping with fittings, flushing arrangement, including Hardware all allied works complete | 1 | LS
4 | 2.2.6.1 | Sluice Gate | 1 | LS
5 | 2.2.6.1.1 | Successful Installation | 1 | LS | 82467.63 |  |  |  | 9896.67 | 92364.3
5 | 2.2.6.1.2 | Completion of testing. Trial run | 1 | LS | 23562.18 |  |  |  | 2827.62 | 26389.8
5 | 2.2.6.1.3 | Commissioing of equipment | 1 | LS | 11781.09 |  |  |  | 1413.81 | 13194.9
4 | 2.2.6.2 | Supply of Pipes and Fittings | 1 | LS
5 | 2.2.6.2.1 | Successful Installation | 1 | LS | 9163.07 |  |  |  | 1099.63 | 10262.7
5 | 2.2.6.2.2 | Completion of testing. Trial run | 1 | LS | 2618.02 |  |  |  | 314.18 | 2932.2
5 | 2.2.6.2.3 | Commissioing of equipment | 1 | LS | 1309.01 |  |  |  | 157.09 | 1466.1
3 | 2.2.7 | Screen chamber with effluent channel, Drain piping and Fine screening, Conveyors, Screening collection arrangement, flushing arrangement, inculding Hardware all allied works complete | 1 | LS
4 | 2.2.7.1 | Fine screen | 1 | LS
5 | 2.2.7.1.1 | Successful Installation | 1 | LS | 180542.88 |  |  |  | 21665.7 | 202208.58
5 | 2.2.7.1.2 | Completion of testing. Trial run | 1 | LS | 51583.68 |  |  |  | 6190.2 | 57773.88
5 | 2.2.7.1.3 | Commissioing of equipment | 1 | LS | 25791.84 |  |  |  | 3095.1 | 28886.94
4 | 2.2.7.2 | Conveyor | 1 | LS
5 | 2.2.7.2.1 | Successful Installation | 1 | LS | 10030.16 |  |  |  | 1203.65 | 11233.81
5 | 2.2.7.2.2 | Completion of testing. Trial run | 1 | LS | 2865.76 |  |  |  | 343.9 | 3209.66
5 | 2.2.7.2.3 | Commissioing of equipment | 1 | LS | 1432.88 |  |  |  | 171.95 | 1604.83
4 | 2.2.7.3 | Pipes and Fittings | 1 | LS
5 | 2.2.7.3.1 | Successful Installation | 1 | LS | 10030.16 |  |  |  | 1203.65 | 11233.81
5 | 2.2.7.3.2 | Completion of testing. Trial run | 1 | LS | 2865.76 |  |  |  | 343.9 | 3209.66
5 | 2.2.7.3.3 | Commissioing of equipment | 1 | LS | 1432.88 |  |  |  | 171.95 | 1604.83
3 | 2.2.8 | Vortex Grit mechanism with grit classifier & washing mechanism,Conveyors, Grit collection arrangement, sluice gates,Stop logs, flushing arrangement, including Hardware all allied works complete | 1 | LS
4 | 2.2.8.1 | Vortex grit mechanism | 1 | LS
5 | 2.2.8.1.1 | Successful Installation | 1 | LS | 399660.905 |  |  |  | 47959.38 | 447620.285
5 | 2.2.8.1.2 | Completion of testing. Trial run | 1 | LS | 114188.83 |  |  |  | 13702.68 | 127891.51
5 | 2.2.8.1.3 | Commissioing of equipment | 1 | LS | 57094.415 |  |  |  | 6851.34 | 63945.755
4 | 2.2.8.2 | Grit transfer pump | 1 | LS
5 | 2.2.8.2.1 | Successful Installation | 1 | LS | 23509.465 |  |  |  | 2821.14 | 26330.605
5 | 2.2.8.2.2 | Completion of testing. Trial run | 1 | LS | 6716.99 |  |  |  | 806.04 | 7523.03
5 | 2.2.8.2.3 | Commissioing of equipment | 1 | LS | 3358.495 |  |  |  | 403.02 | 3761.515
4 | 2.2.8.3 | Washer mechanism | 1 | LS
5 | 2.2.8.3.1 | Successful Installation | 1 | LS | 23509.465 |  |  |  | 2821.14 | 26330.605
5 | 2.2.8.3.2 | Completion of testing. Trial run | 1 | LS | 6716.99 |  |  |  | 806.04 | 7523.03
5 | 2.2.8.3.3 | Commissioing of equipment | 1 | LS | 3358.495 |  |  |  | 403.02 | 3761.515
4 | 2.2.8.4 | Sluice gates | 1 | LS
5 | 2.2.8.4.1 | Successful Installation | 1 | LS | 23509.465 |  |  |  | 2821.14 | 26330.605
5 | 2.2.8.4.2 | Completion of testing. Trial run | 1 | LS | 6716.99 |  |  |  | 806.04 | 7523.03
5 | 2.2.8.4.3 | Commissioing of equipment | 1 | LS | 3358.495 |  |  |  | 403.02 | 3761.515
3 | 2.2.9 | Aeration Basin with Aeration arrangement with piping, Sluice gates and weir gates, Stop logs, flushing arrangement, including Hardware all allied works complete | 1 | LS
4 | 2.2.9.1 | Sluice gates for SBR Basin | 1 | LS
5 | 2.2.9.1.1 | Successful Installation | 1 | LS | 59047.38 |  |  |  | 7086.24 | 66133.62
5 | 2.2.9.1.2 | Completion of testing. Trial run | 1 | LS | 16870.68 |  |  |  | 2024.64 | 18895.32
5 | 2.2.9.1.3 | Commissioing of equipment | 1 | LS | 8435.34 |  |  |  | 1012.32 | 9447.66
4 | 2.2.9.2 | Pipes and fittings | 1 | LS
5 | 2.2.9.2.1 | Successful Installation | 1 | LS | 6560.82 |  |  |  | 787.36 | 7348.18
5 | 2.2.9.2.2 | Completion of testing. Trial run | 1 | LS | 1874.52 |  |  |  | 224.96 | 2099.48
5 | 2.2.9.2.3 | Commissioing of equipment | 1 | LS | 937.26 |  |  |  | 112.48 | 1049.74
3 | 2.2.10 | Anaerobic Zone Inlet arrangement including pipework,Submersible mixer arrangement,and Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
3 | 2.2.11 | Anoxic zone Inlet arrangement including pipework,Submersible mixer arrangement,and Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
3 | 2.2.12 | Deareation Zone Inlet arrangement including pipework,Submersible mixer arrangement,and Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
3 | 2.2.13 | Aeration Zone with MLR Pumpsets, Retrievable type Fine Bubble Diffuser Aeration system arrangement, Pipe grid, Drop legs,piping arrangements,Drain pumpsets, Lifting arrangements, sluice gates, flushing arrangement,Handling Equipment,piping and valves including Hardware all allied works complete | 1 | LS
4 | 2.2.13.1 | Decanter for SBR Technology | 1 | LS
5 | 2.2.13.1.1 | Successful Installation | 1 | LS | 1334334.4 |  |  |  | 160120.24 | 1494454.64
5 | 2.2.13.1.2 | Completion of testing. Trial run | 1 | LS | 381238.4 |  |  |  | 45748.64 | 426987.04
5 | 2.2.13.1.3 | Commissioing of equipment | 1 | LS | 190619.2 |  |  |  | 22874.32 | 213493.52
4 | 2.2.13.2 | Fine bubble diffusers for SBR Technology | 1 | LS
5 | 2.2.13.2.1 | Successful Installation | 1 | LS | 166791.8 |  |  |  | 20015.03 | 186806.83
5 | 2.2.13.2.2 | Completion of testing. Trial run | 1 | LS | 47654.8 |  |  |  | 5718.58 | 53373.38
5 | 2.2.13.2.3 | Commissioing of equipment | 1 | LS | 23827.4 |  |  |  | 2859.29 | 26686.69
4 | 2.2.13.3 | Pipe grid and fittings for SBR Technology | 1 | LS
5 | 2.2.13.3.1 | Successful Installation | 1 | LS | 83395.9 |  |  |  | 10007.515 | 93403.415
5 | 2.2.13.3.2 | Completion of testing. Trial run | 1 | LS | 23827.4 |  |  |  | 2859.29 | 26686.69
5 | 2.2.13.3.3 | Commissioing of equipment | 1 | LS | 11913.7 |  |  |  | 1429.645 | 13343.345
4 | 2.2.13.4 | WAS pumps | 1 | LS
5 | 2.2.13.4.1 | Successful Installation | 1 | LS | 83395.9 |  |  |  | 10007.515 | 93403.415
5 | 2.2.13.4.2 | Completion of testing. Trial run | 1 | LS | 23827.4 |  |  |  | 2859.29 | 26686.69
5 | 2.2.13.4.3 | Commissioing of equipment | 1 | LS | 11913.7 |  |  |  | 1429.645 | 13343.345
3 | 2.2.14 | Process Air Blower Building with blowers, Air Coolers,EOT Crane, Service water & blower cooling arrangement, Piping and valves, Handling Equipment,Ventilation system, Hardware and all allied works complete | 1 | LS
4 | 2.2.14.1 | Air blowers | 1 | LS
5 | 2.2.14.1.1 | Successful Installation | 1 | LS | 221884.11 |  |  |  | 26626.32 | 248510.43
5 | 2.2.14.1.2 | Completion of testing. Trial run | 1 | LS | 63395.46 |  |  |  | 7607.52 | 71002.98
5 | 2.2.14.1.3 | Commissioing of equipment | 1 | LS | 31697.73 |  |  |  | 3803.76 | 35501.49
4 | 2.2.14.2 | Lifting arrangement | 1 | LS
5 | 2.2.14.2.1 | Successful Installation | 1 | LS | 24653.79 |  |  |  | 2958.48 | 27612.27
5 | 2.2.14.2.2 | Completion of testing. Trial run | 1 | LS | 7043.94 |  |  |  | 845.28 | 7889.22
5 | 2.2.14.2.3 | Commissioing of equipment | 1 | LS | 3521.97 |  |  |  | 422.64 | 3944.61
3 | 2.2.15 | Alum solution Preparation and dosing which includes minimum of preparation and dosing pumpsets, agitators, mixing arrangement, flushing arrangement,Channel mounted mixer for alum mixing, material Handling Equipment,Ventilation system, Hardware with piping and all allied works complete | 1 | LS
4 | 2.2.15.1 | Alum dosing pumps | 1 | LS
5 | 2.2.15.1.1 | Successful Installation | 1 | LS | 30699.27 |  |  |  | 3683.925 | 34383.195
5 | 2.2.15.1.2 | Completion of testing. Trial run | 1 | LS | 8771.22 |  |  |  | 1052.55 | 9823.77
5 | 2.2.15.1.3 | Commissioing of equipment | 1 | LS | 4385.61 |  |  |  | 526.275 | 4911.885
4 | 2.2.15.2 | Agitator | 1 | LS
5 | 2.2.15.2.1 | Successful Installation | 1 | LS | 10233.09 |  |  |  | 1227.975 | 11461.065
5 | 2.2.15.2.2 | Completion of testing. Trial run | 1 | LS | 2923.74 |  |  |  | 350.85 | 3274.59
5 | 2.2.15.2.3 | Commissioing of equipment | 1 | LS | 1461.87 |  |  |  | 175.425 | 1637.295
4 | 2.2.15.3 | Alum dosing tanks | 1 | LS
5 | 2.2.15.3.1 | Successful Installation | 1 | LS | 27288.24 |  |  |  | 3274.6 | 30562.84
5 | 2.2.15.3.2 | Completion of testing. Trial run | 1 | LS | 7796.64 |  |  |  | 935.6 | 8732.24
5 | 2.2.15.3.3 | Commissioing of equipment | 1 | LS | 3898.32 |  |  |  | 467.8 | 4366.12
3 | 2.2.16 | Inlet & outlet piping, Distribution Chamber for Secondary Clarifiers with Inlet & Outlet sluice gates,stoplogs,weir arrangement,flushing arrangement, piping and valves including Hardware all allied works complete | 1 | LS
3 | 2.2.17 | Inlet & Outlet piping,Secondary Clarifiers mechanism, scum collection with desludging arrangements,Handling Equipment,flushing arrangement, piping and valves including Hardware all allied works complete | 1 | LS
3 | 2.2.18 | Inlet & Outlet piping,Disc Filter Influent & Effluent chamber sluice gates,Weir gates, Stoplogs,Disc Filter units with Chemical Cleaning Arrangement, Backwash water system and collection arrangement etc. | 1 | LS
4 | 2.2.18.1 | Disc filter | 1 | LS
5 | 2.2.18.1.1 | Successful Installation | 1 | LS | 459534.6 |  |  |  | 55144.53 | 514679.13
5 | 2.2.18.1.2 | Completion of testing. Trial run | 1 | LS | 131295.6 |  |  |  | 15755.58 | 147051.18
5 | 2.2.18.1.3 | Commissioing of equipment | 1 | LS | 65647.8 |  |  |  | 7877.79 | 73525.59
4 | 2.2.18.2 | Gates | 1 | LS
5 | 2.2.18.2.1 | Successful Installation | 1 | LS | 25529.7 |  |  |  | 3063.585 | 28593.285
5 | 2.2.18.2.2 | Completion of testing. Trial run | 1 | LS | 7294.2 |  |  |  | 875.31 | 8169.51
5 | 2.2.18.2.3 | Commissioing of equipment | 1 | LS | 3647.1 |  |  |  | 437.655 | 4084.755
4 | 2.2.18.3 | Backwash Pumps for filter | 1 | LS
5 | 2.2.18.3.1 | Successful Installation | 1 | LS | 25529.7 |  |  |  | 3063.585 | 28593.285
5 | 2.2.18.3.2 | Completion of testing. Trial run | 1 | LS | 7294.2 |  |  |  | 875.31 | 8169.51
5 | 2.2.18.3.3 | Commissioing of equipment | 1 | LS | 3647.1 |  |  |  | 437.655 | 4084.755
3 | 2.2.19 | Material pumping station general arrangement,Pumpsets, flushing arrangement, Handling Equipment,,Ventilation system,Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 2.2.19.1 | Exhaust fan | 1 | LS
5 | 2.2.19.1.1 | Successful Installation | 1 | LS | 84991.2 |  |  |  | 10199 | 95190.2
5 | 2.2.19.1.2 | Completion of testing. Trial run | 1 | LS | 24283.2 |  |  |  | 2914 | 27197.2
5 | 2.2.19.1.3 | Commissioing of equipment | 1 | LS | 12141.6 |  |  |  | 1457 | 13598.6
3 | 2.2.20 | Chlorine & any chemical dosing arrangement, flushing arrangement, spill containment bund, Handling Equipment,Ventilation system,Hardware with piping and all allied works complete | 1 | LS
4 | 2.2.20.1 | Chlorination system | 1 | LS
5 | 2.2.20.1.1 | Successful Installation | 1 | LS | 228135.6 |  |  |  | 27376.72 | 255512.32
5 | 2.2.20.1.2 | Completion of testing. Trial run | 1 | LS | 65181.6 |  |  |  | 7821.92 | 73003.52
5 | 2.2.20.1.3 | Commissioing of equipment | 1 | LS | 32590.8 |  |  |  | 3910.96 | 36501.76
4 | 2.2.20.2 | Lifting arrangement, | 1 | LS
5 | 2.2.20.2.1 | Successful Installation | 1 | LS | 28516.95 |  |  |  | 3422.09 | 31939.04
5 | 2.2.20.2.2 | Completion of testing. Trial run | 1 | LS | 8147.7 |  |  |  | 977.74 | 9125.44
5 | 2.2.20.2.3 | Commissioing of equipment | 1 | LS | 4073.85 |  |  |  | 488.87 | 4562.72
4 | 2.2.20.3 | Chlorine tonner | 1 | LS
5 | 2.2.20.3.1 | Successful Installation | 1 | LS | 28516.95 |  |  |  | 3422.09 | 31939.04
5 | 2.2.20.3.2 | Completion of testing. Trial run | 1 | LS | 8147.7 |  |  |  | 977.74 | 9125.44
5 | 2.2.20.3.3 | Commissioing of equipment | 1 | LS | 4073.85 |  |  |  | 488.87 | 4562.72
3 | 2.2.21 | Inlet & Outlet piping,Chlorine Contact Tank & Outfall structure with sluice gates,weir gates,Stop log Gates, mixing arrangement, hardware with piping, valves and all allied works complete | 1 | LS
4 | 2.2.21.1 | Sluice Gates | 1 | LS
5 | 2.2.21.1.1 | Successful Installation | 1 | LS | 40749.66 |  |  |  | 4890.06 | 45639.72
5 | 2.2.21.1.2 | Completion of testing. Trial run | 1 | LS | 11642.76 |  |  |  | 1397.16 | 13039.92
5 | 2.2.21.1.3 | Commissioing of equipment | 1 | LS | 5821.38 |  |  |  | 698.58 | 6519.96
4 | 2.2.21.2 | Pipes and Valves | 1 | LS
5 | 2.2.21.2.1 | Successful Installation | 1 | LS | 4527.74 |  |  |  | 543.34 | 5071.08
5 | 2.2.21.2.2 | Completion of testing. Trial run | 1 | LS | 1293.64 |  |  |  | 155.24 | 1448.88
5 | 2.2.21.2.3 | Commissioing of equipment | 1 | LS | 646.82 |  |  |  | 77.62 | 724.44
3 | 2.2.22 | Dewatering feed pumping system- Submersible mixer arrangement, Sludge feed Pumpsets, flushing arrangement,Ventilation system,Handling Equipment and Hardware with piping, valves and all allied works complete | 1 | LS
4 | 2.2.22.1 | Centrifuge feed pumps | 1 | LS
5 | 2.2.22.1.1 | Successful Installation | 1 | LS | 20868.12 |  |  |  | 2504.18 | 23372.3
5 | 2.2.22.1.2 | Completion of testing. Trial run | 1 | LS | 5962.32 |  |  |  | 715.48 | 6677.8
5 | 2.2.22.1.3 | Commissioing of equipment | 1 | LS | 2981.16 |  |  |  | 357.74 | 3338.9
4 | 2.2.22.2 | Dewatering unit- Centrifuge | 1 | LS
5 | 2.2.22.2.1 | Successful Installation | 1 | LS | 73038.42 |  |  |  | 8764.63 | 81803.05
5 | 2.2.22.2.2 | Completion of testing. Trial run | 1 | LS | 20868.12 |  |  |  | 2504.18 | 23372.3
5 | 2.2.22.2.3 | Commissioing of equipment | 1 | LS | 10434.06 |  |  |  | 1252.09 | 11686.15
4 | 2.2.22.3 | Supply of lifting arrangement | 1 | LS
5 | 2.2.22.3.1 | Successful Installation | 1 | LS | 5217.03 |  |  |  | 626.045 | 5843.075
5 | 2.2.22.3.2 | Completion of testing. Trial run | 1 | LS | 1490.58 |  |  |  | 178.87 | 1669.45
5 | 2.2.22.3.3 | Commissioing of equipment | 1 | LS | 745.29 |  |  |  | 89.435 | 834.725
4 | 2.2.22.4 | Pipes and Valves | 1 | LS
5 | 2.2.22.4.1 | Successful Installation | 1 | LS | 5217.03 |  |  |  | 626.045 | 5843.075
5 | 2.2.22.4.2 | Completion of testing. Trial run | 1 | LS | 1490.58 |  |  |  | 178.87 | 1669.45
5 | 2.2.22.4.3 | Commissioing of equipment | 1 | LS | 745.29 |  |  |  | 89.435 | 834.725
3 | 2.2.23 | Polyelectrolyte dosing systems for sludge thicking units-Stirrer arrangement, feeding arrangement, Preparation & Storage tanks ,Dosing Pumpsets,flushing arrangement,Handling Equipment,Ventilation system, Hardware with piping and all allied works complete | 1 | LS
4 | 2.2.23.1 | Auto- Polymer System | 1 | LS
5 | 2.2.23.1.1 | Successful Installation | 1 | LS | 129241.98 |  |  |  | 15509.34 | 144751.32
5 | 2.2.23.1.2 | Completion of testing. Trial run | 1 | LS | 36926.28 |  |  |  | 4431.24 | 41357.52
5 | 2.2.23.1.3 | Commissioing of equipment | 1 | LS | 18463.14 |  |  |  | 2215.62 | 20678.76
4 | 2.2.23.2 | Pipes and valves | 1 | LS
5 | 2.2.23.2.1 | Successful Installation | 1 | LS | 14360.22 |  |  |  | 1723.26 | 16083.48
5 | 2.2.23.2.2 | Completion of testing. Trial run | 1 | LS | 4102.92 |  |  |  | 492.36 | 4595.28
5 | 2.2.23.2.3 | Commissioing of equipment | 1 | LS | 2051.46 |  |  |  | 246.18 | 2297.64
3 | 2.2.24 | Dewatering units, sludge cake conveying system with cut gate arrangement and hopper & Collection system, Handling Equipment for Sludge handling systems, flushing arrangement,Ventilation system, Hardware with piping and all allied works complete | 1 | LS
4 | 2.2.24.1 | Sudge thickener mechanism | 1 | LS
5 | 2.2.24.1.1 | Successful Installation | 1 | LS | 232057.735 |  |  |  | 27847.19 | 259904.925
5 | 2.2.24.1.2 | Completion of testing. Trial run | 1 | LS | 66302.21 |  |  |  | 7956.34 | 74258.55
5 | 2.2.24.1.3 | Commissioing of equipment | 1 | LS | 33151.105 |  |  |  | 3978.17 | 37129.275
4 | 2.2.24.2 | Mixers for thickened sludge sump | 1 | LS
5 | 2.2.24.2.1 | Successful Installation | 1 | LS | 27300.91 |  |  |  | 3276.14 | 30577.05
5 | 2.2.24.2.2 | Completion of testing. Trial run | 1 | LS | 7800.26 |  |  |  | 936.04 | 8736.3
5 | 2.2.24.2.3 | Commissioing of equipment | 1 | LS | 3900.13 |  |  |  | 468.02 | 4368.15
4 | 2.2.24.3 | Pipes and valves | 1 | LS
5 | 2.2.24.3.1 | Successful Installation | 1 | LS | 13650.455 |  |  |  | 1638.07 | 15288.525
5 | 2.2.24.3.2 | Completion of testing. Trial run | 1 | LS | 3900.13 |  |  |  | 468.02 | 4368.15
5 | 2.2.24.3.3 | Commissioing of equipment | 1 | LS | 1950.065 |  |  |  | 234.01 | 2184.075
3 | 2.2.25 | Inlet & Outlet piping,Plant Drain Sump and Pump Station,Submersible pumpsets,Handling Equipment,Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 2.2.25.1 | Submersible pumps | 1 | LS
5 | 2.2.25.1.1 | Successful Installation | 1 | LS | 34725.04 |  |  |  | 4166.96 | 38892
5 | 2.2.25.1.2 | Completion of testing. Trial run | 1 | LS | 9921.44 |  |  |  | 1190.56 | 11112
5 | 2.2.25.1.3 | Commissioing of equipment | 1 | LS | 4960.72 |  |  |  | 595.28 | 5556
4 | 2.2.25.2 | Lifting arrangement | 1 | LS
5 | 2.2.25.2.1 | Successful Installation | 1 | LS | 4340.63 |  |  |  | 520.87 | 4861.5
5 | 2.2.25.2.2 | Completion of testing. Trial run | 1 | LS | 1240.18 |  |  |  | 148.82 | 1389
5 | 2.2.25.2.3 | Commissioing of equipment | 1 | LS | 620.09 |  |  |  | 74.41 | 694.5
4 | 2.2.25.3 | Piping and valves | 1 | LS
5 | 2.2.25.3.1 | Successful Installation | 1 | LS | 4340.63 |  |  |  | 520.87 | 4861.5
5 | 2.2.25.3.2 | Completion of testing. Trial run | 1 | LS | 1240.18 |  |  |  | 148.82 | 1389
5 | 2.2.25.3.3 | Commissioing of equipment | 1 | LS | 620.09 |  |  |  | 74.41 | 694.5
3 | 2.2.26 | Inlet & Outlet piping, Treated water storage Pump Station,Submersible pumpsets,Handling Equipment,Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 2.2.26.1 | Submersible pumps | 1 | LS
5 | 2.2.26.1.1 | Successful Installation | 1 | LS | 55903.68 |  |  |  | 6708.8 | 62612.48
5 | 2.2.26.1.2 | Completion of testing. Trial run | 1 | LS | 15972.48 |  |  |  | 1916.8 | 17889.28
5 | 2.2.26.1.3 | Commissioing of equipment | 1 | LS | 7986.24 |  |  |  | 958.4 | 8944.64
4 | 2.2.26.2 | Lifting arrangement | 1 | LS
5 | 2.2.26.2.1 | Successful Installation | 1 | LS | 6987.96 |  |  |  | 838.6 | 7826.56
5 | 2.2.26.2.2 | Completion of testing. Trial run | 1 | LS | 1996.56 |  |  |  | 239.6 | 2236.16
5 | 2.2.26.2.3 | Commissioing of equipment | 1 | LS | 998.28 |  |  |  | 119.8 | 1118.08
4 | 2.2.26.3 | Piping and valves | 1 | LS
5 | 2.2.26.3.1 | Successful Installation | 1 | LS | 6987.96 |  |  |  | 838.6 | 7826.56
5 | 2.2.26.3.2 | Completion of testing. Trial run | 1 | LS | 1996.56 |  |  |  | 239.6 | 2236.16
5 | 2.2.26.3.3 | Commissioing of equipment | 1 | LS | 998.28 |  |  |  | 119.8 | 1118.08
3 | 2.2.27 | Inlet & Outlet piping,Plant water Pump Station,Submersible pumpsets,Handling Equipment, Sluice gates, Weir gates, Stop logs,Hardware with piping, Valves and all allied works complete | 1 | LS
4 | 2.2.27.1 | Submersible pumps | 1 | LS
5 | 2.2.27.1.1 | Successful Installation | 1 | LS | 33587.68 |  |  |  | 4030.88 | 37618.56
5 | 2.2.27.1.2 | Completion of testing. Trial run | 1 | LS | 9596.48 |  |  |  | 1151.68 | 10748.16
5 | 2.2.27.1.3 | Commissioing of equipment | 1 | LS | 4798.24 |  |  |  | 575.84 | 5374.08
4 | 2.2.27.2 | Lifting arrangement | 1 | LS
5 | 2.2.27.2.1 | Successful Installation | 1 | LS | 4198.46 |  |  |  | 503.86 | 4702.32
5 | 2.2.27.2.2 | Completion of testing. Trial run | 1 | LS | 1199.56 |  |  |  | 143.96 | 1343.52
5 | 2.2.27.2.3 | Commissioing of equipment | 1 | LS | 599.78 |  |  |  | 71.98 | 671.76
4 | 2.2.27.3 | Piping and valves | 1 | LS
5 | 2.2.27.3.1 | Successful Installation | 1 | LS | 4198.46 |  |  |  | 503.86 | 4702.32
5 | 2.2.27.3.2 | Completion of testing. Trial run | 1 | LS | 1199.56 |  |  |  | 143.96 | 1343.52
5 | 2.2.27.3.3 | Commissioing of equipment | 1 | LS | 599.78 |  |  |  | 71.98 | 671.76
3 | 2.2.28 | Flushing arrangement for all chemical & Sludge handling system, Dewatering Pumps including piping and all allied works in all sludge & Chemical handling pump houses complete | 1 | LS
4 | 2.2.28.1 | GI pipe and valves | 1 | LS
5 | 2.2.28.1.1 | Successful Installation | 1 | LS | 86674 |  |  |  | 10401.3 | 97075.3
5 | 2.2.28.1.2 | Completion of testing. Trial run | 1 | LS | 24764 |  |  |  | 2971.8 | 27735.8
5 | 2.2.28.1.3 | Commissioing of equipment | 1 | LS | 12382 |  |  |  | 1485.9 | 13867.9
3 | 2.2.29 | Service water system including pumps with Hardware,piping,Valves and all allied works complete | 1 | LS
4 | 2.2.29.1 | Submersible pump | 1 | LS
5 | 2.2.29.1.1 | Successful Installation | 1 | LS | 22410.64 |  |  |  | 2689.68 | 25100.32
5 | 2.2.29.1.2 | Completion of testing. Trial run | 1 | LS | 6403.04 |  |  |  | 768.48 | 7171.52
5 | 2.2.29.1.3 | Commissioing of equipment | 1 | LS | 3201.52 |  |  |  | 384.24 | 3585.76
4 | 2.2.29.2 | GI Piping and valves | 1 | LS
5 | 2.2.29.2.1 | Successful Installation | 1 | LS | 5602.66 |  |  |  | 672.42 | 6275.08
5 | 2.2.29.2.2 | Completion of testing. Trial run | 1 | LS | 1600.76 |  |  |  | 192.12 | 1792.88
5 | 2.2.29.2.3 | Commissioing of equipment | 1 | LS | 800.38 |  |  |  | 96.06 | 896.44
3 | 2.2.30 | Fire Fighting system for the entire STP (inclusive of fire alarm,fire detection,fire extinguishing system and integration with plan SCADA system for monitoring), Tools Kit, Air conditioning system for SCADA control room & Administration and Laboratory Building and all allied works complete. | 1 | LS
4 | 2.2.30.1 | Fire extinguishers | 1 | LS
5 | 2.2.30.1.1 | Successful Installation | 1 | LS | 23091.25 |  |  |  | 2770.95 | 25862.2
5 | 2.2.30.1.2 | Completion of testing. Trial run | 1 | LS | 6597.5 |  |  |  | 791.7 | 7389.2
5 | 2.2.30.1.3 | Commissioing of equipment | 1 | LS | 3298.75 |  |  |  | 395.85 | 3694.6
4 | 2.2.30.2 | Fire sand bucket | 1 | LS
5 | 2.2.30.2.1 | Successful Installation | 1 | LS | 23091.25 |  |  |  | 2770.95 | 25862.2
5 | 2.2.30.2.2 | Completion of testing. Trial run | 1 | LS | 6597.5 |  |  |  | 791.7 | 7389.2
5 | 2.2.30.2.3 | Commissioing of equipment | 1 | LS | 3298.75 |  |  |  | 395.85 | 3694.6
3 | 2.2.31 | Carrying out the SOTE test in presence of Client/ client representative Engineer at original manufacturer site for selected diffuser membranes from supplied lot with test results, and calculation sheet, photo and provide all of test results with necessary document including its data and photo and the its test results | 1 | LS
3 | 2.2.32 | The bidder shall list here details of any additional items (all areas of the works) required for a complete installation | 1 | LS
| 2.2.33 |  | 1 | LS
| 2.2.34 |  | 1 | LS
| 2.2.35 |  | 1 | LS
Sub Total of 2.2 |  |  | 1 | LS
|  |  | 1 | LS
2 | 2.3 | Electrical Systems for TSPS & STP | 1 | LS
|  | Complete Installation, testing and commissioning of Electrical system as per the Bid specifications | 1 | LS
3 | 2.3.1 | Installation, testing and commissioning of 11kV underground Cables, Termination Kits at following locations as per scope, specification and drawings. | 1 | LS
4 | 2.3.1.1 | 11kV Outdoor cable termination at Tariff Metering Unit / BESCOM | 1 | LS
5 | 2.3.1.1.1 | Successful Installation | 1 | LS | 1750.7 |  |  |  | 210.7 | 1961.4
5 | 2.3.1.1.2 | Completion of testing. Trial run | 1 | LS | 500.2 |  |  |  | 60.2 | 560.4
5 | 2.3.1.1.3 | Commissioing of equipment | 1 | LS | 250.1 |  |  |  | 30.1 | 280.2
4 | 2.3.1.2 | 11kV Indoor cable terminations at incomer and outgoings of 11kV Metal Enclosed Switchboard of Sewage Treatment Plant | 1 | LS
5 | 2.3.1.2.1 | Successful Installation | 1 | LS | 2406.6 |  |  |  | 289.1 | 2695.7
5 | 2.3.1.2.2 | Completion of testing. Trial run | 1 | LS | 687.6 |  |  |  | 82.6 | 770.2
5 | 2.3.1.2.3 | Commissioing of equipment | 1 | LS | 343.8 |  |  |  | 41.3 | 385.1
4 | 2.3.1.3 | 11kV Outdoor cable terminations at primary side of 11kV / 0.433 kV Transformers of Sewage Treatment Plant | 1 | LS
5 | 2.3.1.3.1 | Successful Installation | 1 | LS | 1969.1 |  |  |  | 236.6 | 2205.7
5 | 2.3.1.3.2 | Completion of testing. Trial run | 1 | LS | 562.6 |  |  |  | 67.6 | 630.2
5 | 2.3.1.3.3 | Commissioing of equipment | 1 | LS | 281.3 |  |  |  | 33.8 | 315.1
4 | 2.3.1.4 | 11kV XLPE Cable from Metering Unit to incomer of 11kV Metal Enclosed Switchboard of Sewage Treatment Plant | 1 | LS
5 | 2.3.1.4.1 | Successful Installation | 1 | LS | 8750.7 |  |  |  | 1050.7 | 9801.4
5 | 2.3.1.4.2 | Completion of testing. Trial run | 1 | LS | 2500.2 |  |  |  | 300.2 | 2800.4
5 | 2.3.1.4.3 | Commissioing of equipment | 1 | LS | 1250.1 |  |  |  | 150.1 | 1400.2
4 | 2.3.1.5 | 11kV XLPE Cables from 11kV Metal Enclosed Switchboard to Primary cable end boxes of 11kV/0.433kV Transformers of Sewage Treatment Plant | 1 | LS
5 | 2.3.1.5.1 | Successful Installation | 1 | LS | 6563.2 |  |  |  | 788.2 | 7351.4
5 | 2.3.1.5.2 | Completion of testing. Trial run | 1 | LS | 1875.2 |  |  |  | 225.2 | 2100.4
5 | 2.3.1.5.3 | Commissioing of equipment | 1 | LS | 937.6 |  |  |  | 112.6 | 1050.2
4 | 2.3.1.6 | 11kV XLPE Cable from existing Metering Unit to Proposed 11kV Metal Enclosed Switchboard if applicable | 1 | LS
5 | 2.3.1.6.1 | Successful Installation | 1 | LS
5 | 2.3.1.6.2 | Completion of testing. Trial run | 1 | LS
5 | 2.3.1.6.3 | Commissioing of equipment | 1 | LS
4 | 2.3.1.7 | 11kV XLPE Cable from Proposed 11kV Metal Enclosed Switchboard to 11kV Metal Enclosed Switchboard at Existing Sewage Treatment Plant if applicable | 1 | LS
5 | 2.3.1.7.1 | Successful Installation | 1 | LS
5 | 2.3.1.7.2 | Completion of testing. Trial run | 1 | LS
5 | 2.3.1.7.3 | Commissioing of equipment | 1 | LS
4 | 2.3.1.8 | 11kV Cable Straight through joints | 1 | LS
5 | 2.3.1.8.1 | Successful Installation | 1 | LS | 438.2 |  |  |  | 53.2 | 491.4
5 | 2.3.1.8.2 | Completion of testing. Trial run | 1 | LS | 125.2 |  |  |  | 15.2 | 140.4
5 | 2.3.1.8.3 | Commissioing of equipment | 1 | LS | 62.6 |  |  |  | 7.6 | 70.2
3 | 2.3.2 | Complete Installation, testing and commissioning of Electrical equipments at Sewage Treatment Plant Substation Building & Process Air Blower Building as per scope, specification and drawings. | 1 | LS
4 | 2.3.2.1 | 11kV Metal Enclosed Switchboard with VCBs | 1 | LS
5 | 2.3.2.1.1 | Successful Installation | 1 | LS | 44297.4 |  |  |  | 5315.8 | 49613.2
5 | 2.3.2.1.2 | Completion of testing. Trial run | 1 | LS | 12656.4 |  |  |  | 1518.8 | 14175.2
5 | 2.3.2.1.3 | Commissioing of equipment | 1 | LS | 6328.2 |  |  |  | 759.4 | 7087.6
4 | 2.3.2.2 | Diesel Generator Set complete with AMF Control Panel | 1 | LS
5 | 2.3.2.2.1 | Successful Installation | 1 | LS | 216563.9 |  |  |  | 25988.2 | 242552.1
5 | 2.3.2.2.2 | Completion of testing. Trial run | 1 | LS | 61875.4 |  |  |  | 7425.2 | 69300.6
5 | 2.3.2.2.3 | Commissioing of equipment | 1 | LS | 30937.7 |  |  |  | 3712.6 | 34650.3
4 | 2.3.2.3 | 11kV / 0.433kV Transformers with OLTC | 1 | LS
5 | 2.3.2.3.1 | Successful Installation | 1 | LS | 73829 |  |  |  | 8859.9 | 82688.9
5 | 2.3.2.3.2 | Completion of testing. Trial run | 1 | LS | 21094 |  |  |  | 2531.4 | 23625.4
5 | 2.3.2.3.3 | Commissioing of equipment | 1 | LS | 10547 |  |  |  | 1265.7 | 11812.7
4 | 2.3.2.4 | LT Non Segregated Aluminium Bus ducts with necessary supporting structure | 1 | LS
5 | 2.3.2.4.1 | Successful Installation | 1 | LS | 44297.4 |  |  |  | 5315.8 | 49613.2
5 | 2.3.2.4.2 | Completion of testing. Trial run | 1 | LS | 12656.4 |  |  |  | 1518.8 | 14175.2
5 | 2.3.2.4.3 | Commissioing of equipment | 1 | LS | 6328.2 |  |  |  | 759.4 | 7087.6
4 | 2.3.2.5 | 415V Switchgear PCC | 1 | LS
5 | 2.3.2.5.1 | Successful Installation | 1 | LS | 88594.8 |  |  |  | 10631.6 | 99226.4
5 | 2.3.2.5.2 | Completion of testing. Trial run | 1 | LS | 25312.8 |  |  |  | 3037.6 | 28350.4
5 | 2.3.2.5.3 | Commissioing of equipment | 1 | LS | 12656.4 |  |  |  | 1518.8 | 14175.2
4 | 2.3.2.6 | 415V Capacitor banks with Automatic Power Factor Correction Relay | 1 | LS
5 | 2.3.2.6.1 | Successful Installation | 1 | LS | 14765.8 |  |  |  | 1772.4 | 16538.2
5 | 2.3.2.6.2 | Completion of testing. Trial run | 1 | LS | 4218.8 |  |  |  | 506.4 | 4725.2
5 | 2.3.2.6.3 | Commissioing of equipment | 1 | LS | 2109.4 |  |  |  | 253.2 | 2362.6
4 | 2.3.2.7 | 110V D.C Battery Bank, Battery Charger with D.C Distribution Board | 1 | LS
5 | 2.3.2.7.1 | Successful Installation | 1 | LS | 9844.1 |  |  |  | 1181.6 | 11025.7
5 | 2.3.2.7.2 | Completion of testing. Trial run | 1 | LS | 2812.6 |  |  |  | 337.6 | 3150.2
5 | 2.3.2.7.3 | Commissioing of equipment | 1 | LS | 1406.3 |  |  |  | 168.8 | 1575.1
3 | 2.3.3 | Complete Installation, testing and commissioning of Motor Control Centres, Distribution boards etc at various locations in TSPS & Sewage Treatment plant with following major equipment, items as per scope, specification and drawings. | 1 | LS
4 | 2.3.3.1 | TSPS MCC | 1 | LS
5 | 2.3.3.1.1 | Successful Installation | 1 | LS | 30625.7 |  |  |  | 3675.7 | 34301.4
5 | 2.3.3.1.2 | Completion of testing. Trial run | 1 | LS | 8750.2 |  |  |  | 1050.2 | 9800.4
5 | 2.3.3.1.3 | Commissioing of equipment | 1 | LS | 4375.1 |  |  |  | 525.1 | 4900.2
4 | 2.3.3.2 | Process Air Blower MCC | 1 | LS
5 | 2.3.3.2.1 | Successful Installation | 1 | LS | 26250.7 |  |  |  | 3150.7 | 29401.4
5 | 2.3.3.2.2 | Completion of testing. Trial run | 1 | LS | 7500.2 |  |  |  | 900.2 | 8400.4
5 | 2.3.3.2.3 | Commissioing of equipment | 1 | LS | 3750.1 |  |  |  | 450.1 | 4200.2
4 | 2.3.3.3 | Headworks MCC | 1 | LS
5 | 2.3.3.3.1 | Successful Installation | 1 | LS | 21875.7 |  |  |  | 2625.7 | 24501.4
5 | 2.3.3.3.2 | Completion of testing. Trial run | 1 | LS | 6250.2 |  |  |  | 750.2 | 7000.4
5 | 2.3.3.3.3 | Commissioing of equipment | 1 | LS | 3125.1 |  |  |  | 375.1 | 3500.2
4 | 2.3.3.4 | Centrifuge MCC | 1 | LS
5 | 2.3.3.4.1 | Successful Installation | 1 | LS | 24063.2 |  |  |  | 2888.2 | 26951.4
5 | 2.3.3.4.2 | Completion of testing. Trial run | 1 | LS | 6875.2 |  |  |  | 825.2 | 7700.4
5 | 2.3.3.4.3 | Commissioing of equipment | 1 | LS | 3437.6 |  |  |  | 412.6 | 3850.2
4 | 2.3.3.5 | RAS MCC | 1 | LS
5 | 2.3.3.5.1 | WAS MCC | 1 | LS
6 | 2.3.3.5.1.1 | Successful Installation | 1 | LS | 19688.2 |  |  |  | 2363.2 | 22051.4
6 | 2.3.3.5.1.2 | Completion of testing. Trial run | 1 | LS | 5625.2 |  |  |  | 675.2 | 6300.4
6 | 2.3.3.5.1.3 | Commissioing of equipment | 1 | LS | 2812.6 |  |  |  | 337.6 | 3150.2
4 | 2.3.3.6 | Chlorine MCC | 1 | LS
5 | 2.3.3.6.1 | Successful Installation | 1 | LS | 17500.7 |  |  |  | 2100.7 | 19601.4
5 | 2.3.3.6.2 | Completion of testing. Trial run | 1 | LS | 5000.2 |  |  |  | 600.2 | 5600.4
5 | 2.3.3.6.3 | Commissioing of equipment | 1 | LS | 2500.1 |  |  |  | 300.1 | 2800.2
4 | 2.3.3.7 | Main Lighting DB | 1 | LS
5 | 2.3.3.7.1 | Successful Installation | 1 | LS | 6563.2 |  |  |  | 788.2 | 7351.4
5 | 2.3.3.7.2 | Completion of testing. Trial run | 1 | LS | 1875.2 |  |  |  | 225.2 | 2100.4
5 | 2.3.3.7.3 | Commissioing of equipment | 1 | LS | 937.6 |  |  |  | 112.6 | 1050.2
4 | 2.3.3.8 | Variable Frequency Drives MCC | 1 | LS
5 | 2.3.3.8.1 | Successful Installation | 1 | LS | 65625.7 |  |  |  | 7875.7 | 73501.4
5 | 2.3.3.8.2 | Completion of testing. Trial run | 1 | LS | 18750.2 |  |  |  | 2250.2 | 21000.4
5 | 2.3.3.8.3 | Commissioing of equipment | 1 | LS | 9375.1 |  |  |  | 1125.1 | 10500.2
4 | 2.3.3.9 | Local Push Button Stations | 1 | LS
5 | 2.3.3.9.1 | Successful Installation | 1 | LS | 4375.7 |  |  |  | 525.7 | 4901.4
5 | 2.3.3.9.2 | Completion of testing. Trial run | 1 | LS | 1250.2 |  |  |  | 150.2 | 1400.4
5 | 2.3.3.9.3 | Commissioing of equipment | 1 | LS | 625.1 |  |  |  | 75.1 | 700.2
4 | 2.3.3.10 | Miscellaneous works-Distribution Board | 1 | LS
5 | 2.3.3.10.1 | Successful Installation | 1 | LS | 2188.2 |  |  |  | 263.2 | 2451.4
5 | 2.3.3.10.2 | Completion of testing. Trial run | 1 | LS | 625.2 |  |  |  | 75.2 | 700.4
5 | 2.3.3.10.3 | Commissioing of equipment | 1 | LS | 312.6 |  |  |  | 37.6 | 350.2
3 | 2.3.4 | Complete Installation, testing and commissioning of Lighting System at TSPS & Sewage Treatment Plant with following major equipment, items as per scope, specification and drawings. | 1 | LS
4 | 2.3.4.1 | Lighting Fixtures | 1 | LS
5 | 2.3.4.1.1 | Successful Installation | 1 | LS | 11484.9 |  |  |  | 1378.3 | 12863.2
5 | 2.3.4.1.2 | Completion of testing. Trial run | 1 | LS | 3281.4 |  |  |  | 393.8 | 3675.2
5 | 2.3.4.1.3 | Commissioing of equipment | 1 | LS | 1640.7 |  |  |  | 196.9 | 1837.6
4 | 2.3.4.2 | Lighting panels | 1 | LS
5 | 2.3.4.2.1 | Successful Installation | 1 | LS | 6563.2 |  |  |  | 788.2 | 7351.4
5 | 2.3.4.2.2 | Completion of testing. Trial run | 1 | LS | 1875.2 |  |  |  | 225.2 | 2100.4
5 | 2.3.4.2.3 | Commissioing of equipment | 1 | LS | 937.6 |  |  |  | 112.6 | 1050.2
4 | 2.3.4.3 | Switchboards, Receptacles, Power Plug & Sockets, Switches, Ceiling fans with regulators etc | 1 | LS
5 | 2.3.4.3.1 | Successful Installation | 1 | LS | 4922.4 |  |  |  | 590.8 | 5513.2
5 | 2.3.4.3.2 | Completion of testing. Trial run | 1 | LS | 1406.4 |  |  |  | 168.8 | 1575.2
5 | 2.3.4.3.3 | Commissioing of equipment | 1 | LS | 703.2 |  |  |  | 84.4 | 787.6
4 | 2.3.4.4 | Point wiring with conduits, wires, supports etc for Lighting fixtures, Receptacles, Ceiling fans etc | 1 | LS
5 | 2.3.4.4.1 | Successful Installation | 1 | LS | 5469.1 |  |  |  | 656.6 | 6125.7
5 | 2.3.4.4.2 | Completion of testing. Trial run | 1 | LS | 1562.6 |  |  |  | 187.6 | 1750.2
5 | 2.3.4.4.3 | Commissioing of equipment | 1 | LS | 781.3 |  |  |  | 93.8 | 875.1
4 | 2.3.4.5 | Street Lighting and Area Lighting poles with Junction boxes and Over hang | 1 | LS
5 | 2.3.4.5.1 | Successful Installation | 1 | LS | 26250.7 |  |  |  | 3150.7 | 29401.4
5 | 2.3.4.5.2 | Completion of testing. Trial run | 1 | LS | 7500.2 |  |  |  | 900.2 | 8400.4
5 | 2.3.4.5.3 | Commissioing of equipment | 1 | LS | 3750.1 |  |  |  | 450.1 | 4200.2
3 | 2.3.5 | Complete Installation, testing and commissioning of L.T Cabling System, HT/LT Cable Carrier System at TSPS & Sewage Treatment Plant with following major components as per scope, specification and drawings. | 1 | LS
4 | 2.3.5.1 | L.T cables | 1 | LS
5 | 2.3.5.1.1 | Successful Installation | 1 | LS | 71094.8 |  |  |  | 8531.6 | 79626.4
5 | 2.3.5.1.2 | Completion of testing. Trial run | 1 | LS | 20312.8 |  |  |  | 2437.6 | 22750.4
5 | 2.3.5.1.3 | Commissioing of equipment | 1 | LS | 10156.4 |  |  |  | 1218.8 | 11375.2
4 | 2.3.5.2 | L.T Cable termination with glands and lugs | 1 | LS
5 | 2.3.5.2.1 | Successful Installation | 1 | LS | 15313.2 |  |  |  | 1838.2 | 17151.4
5 | 2.3.5.2.2 | Completion of testing. Trial run | 1 | LS | 4375.2 |  |  |  | 525.2 | 4900.4
5 | 2.3.5.2.3 | Commissioing of equipment | 1 | LS | 2187.6 |  |  |  | 262.6 | 2450.2
4 | 2.3.5.3 | Cable trays on supports for both LT and HT Cables | 1 | LS
5 | 2.3.5.3.1 | Successful Installation | 1 | LS | 17500.7 |  |  |  | 2100.7 | 19601.4
5 | 2.3.5.3.2 | Completion of testing. Trial run | 1 | LS | 5000.2 |  |  |  | 600.2 | 5600.4
5 | 2.3.5.3.3 | Commissioing of equipment | 1 | LS | 2500.1 |  |  |  | 300.1 | 2800.2
4 | 2.3.5.4 | Hume Pipe | 1 | LS
5 | 2.3.5.4.1 | Successful Installation | 1 | LS | 5469.1 |  |  |  | 656.6 | 6125.7
5 | 2.3.5.4.2 | Completion of testing. Trial run | 1 | LS | 1562.6 |  |  |  | 187.6 | 1750.2
5 | 2.3.5.4.3 | Commissioing of equipment | 1 | LS | 781.3 |  |  |  | 93.8 | 875.1
3 | 2.3.6 | Installation, testing and commissioning of Earthing & Lighting Protection System at TSPS & Sewage Treatment Plant with following major components as per scope, specification and drawings. | 1 | LS
4 | 2.3.6.1 | Earthing Conductor for outdoor main grid | 1 | LS
5 | 2.3.6.1.1 | Successful Installation | 1 | LS | 4922.4 |  |  |  | 590.8 | 5513.2
5 | 2.3.6.1.2 | Completion of testing. Trial run | 1 | LS | 1406.4 |  |  |  | 168.8 | 1575.2
5 | 2.3.6.1.3 | Commissioing of equipment | 1 | LS | 703.2 |  |  |  | 84.4 | 787.6
4 | 2.3.6.2 | Earthing Conductor for indoor main grid | 1 | LS
5 | 2.3.6.2.1 | Successful Installation | 1 | LS | 8203.3 |  |  |  | 984.9 | 9188.2
5 | 2.3.6.2.2 | Completion of testing. Trial run | 1 | LS | 2343.8 |  |  |  | 281.4 | 2625.2
5 | 2.3.6.2.3 | Commissioing of equipment | 1 | LS | 1171.9 |  |  |  | 140.7 | 1312.6
4 | 2.3.6.3 | Earthing Conductors for outdoor equipments and Junction Boxes | 1 | LS
5 | 2.3.6.3.1 | Successful Installation | 1 | LS | 5250.7 |  |  |  | 630.7 | 5881.4
5 | 2.3.6.3.2 | Completion of testing. Trial run | 1 | LS | 1500.2 |  |  |  | 180.2 | 1680.4
5 | 2.3.6.3.3 | Commissioing of equipment | 1 | LS | 750.1 |  |  |  | 90.1 | 840.2
4 | 2.3.6.4 | Lightning Protection system with Arrestors and Down Conductors | 1 | LS
5 | 2.3.6.4.1 | Successful Installation | 1 | LS | 3281.6 |  |  |  | 394.1 | 3675.7
5 | 2.3.6.4.2 | Completion of testing. Trial run | 1 | LS | 937.6 |  |  |  | 112.6 | 1050.2
5 | 2.3.6.4.3 | Commissioing of equipment | 1 | LS | 468.8 |  |  |  | 56.3 | 525.1
4 | 2.3.6.5 | Earthing Conductor for indoor equipments | 1 | LS
5 | 2.3.6.5.1 | Successful Installation | 1 | LS | 4594.1 |  |  |  | 551.6 | 5145.7
5 | 2.3.6.5.2 | Completion of testing. Trial run | 1 | LS | 1312.6 |  |  |  | 157.6 | 1470.2
5 | 2.3.6.5.3 | Commissioing of equipment | 1 | LS | 656.3 |  |  |  | 78.8 | 735.1
4 | 2.3.6.6 | Treated Earth pits | 1 | LS
5 | 2.3.6.6.1 | Successful Installation | 1 | LS | 6563.2 |  |  |  | 788.2 | 7351.4
5 | 2.3.6.6.2 | Completion of testing. Trial run | 1 | LS | 1875.2 |  |  |  | 225.2 | 2100.4
5 | 2.3.6.6.3 | Commissioing of equipment | 1 | LS | 937.6 |  |  |  | 112.6 | 1050.2
3 | 2.3.7 | Complete Installation, testing and commissioning of safety procedures with Signage for Electrical Equipments at TSPS & Sewage Treatment Plant as per scope, specification and drawings. | 1 | LS
3 | 2.3.8 | The bidder shall list here details of any additional items required for a complete installation | 1 | LS
| 2.3.8.1 |  | 1 | LS
| 2.3.8.2 |  | 1 | LS
| 2.3.8.3 |  | 1 | LS
Sub Total of 2.3 |  |  | 1 | LS
|  |  | 1 | LS
2 | 2.4 | Instrumentation, Control & Automation Systems | 1 | LS
3 | a | Complete Installation, testing and commissioning of Instrumentation system as per Equipment listed in Price Schedule 3A&3B and all other required Equipments as per Tender specifications | 1 | LS
4 | i) | Successful Installation | 1 | LS | 49219.1 |  |  |  | 5906.6 | 55125.7
4 | ii) | Completion of testing. Trial run | 1 | LS | 14062.6 |  |  |  | 1687.6 | 15750.2
4 | iii) | Commissioing of equipment | 1 | LS | 7031.3 |  |  |  | 843.8 | 7875.1
3 | b | Complete Installation, testing and commissioning of control and Automation system as per Equipment listed in Price Schedule 3A&3B and all other required Equipments as per Tender specifications | 1 | LS
4 | i) | Successful Installation | 1 | LS | 41016.5 |  |  |  | 4922.4 | 45938.9
4 | ii) | Completion of testing. Trial run | 1 | LS | 11719 |  |  |  | 1406.4 | 13125.4
4 | iii) | Commissioing of equipment | 1 | LS | 5859.5 |  |  |  | 703.2 | 6562.7
|  | Testing Requirements of all ICA system | 1 | LS
3 | c | Factory acceptance tests(FAT) for all instrumentation,control and automation system, as required under specifications | 1 | LS
4 | i) | Successful Installation | 1 | LS | 32813.2 |  |  |  | 3938.2 | 36751.4
4 | ii) | Completion of testing. Trial run | 1 | LS | 9375.2 |  |  |  | 1125.2 | 10500.4
4 | iii) | Commissioing of equipment | 1 | LS | 4687.6 |  |  |  | 562.6 | 5250.2
3 | d | Site acceptance tests(SAT)- for all instrumentation,control and automation system in combination and co-ordination with process,mechanical(individual vendor supplied systems) and electrical system's SAT test's ,inclusive of interoperability tests,Integration with ISPS,CP-24 and MIS-2 SCADA as required under specifications | 1 | LS
4 | i) | Successful Installation | 1 | LS | 41016.5 |  |  |  | 4922.4 | 45938.9
4 | ii) | Completion of testing. Trial run | 1 | LS | 11719 |  |  |  | 1406.4 | 13125.4
4 | iii) | Commissioing of equipment | 1 | LS | 5859.5 |  |  |  | 703.2 | 6562.7
3 | e | The Bidder shall list here details of any additional items (all areas of the Works) required for complete installation | 1 | LS
3 | 2.4.1 | The Bidder shall list here details of any additional items required for a complete installation | 1 | LS
| 2.4.1.1 |  | 1 | LS
| 2.4.1.2 |  | 1 | LS
| 2.4.1.3 |  | 1 | LS
| 2.4.1.4 |  | 1 | LS
| 2.4.1.5 |  | 1 | LS
Sub Total of 2.4 |  |  | 1 | LS
|  |  | 1 | LS
2 | 2.5 | General Mechanical Systems | 1 | LS
3 | 2.5.1 | Building Services including domestic water systems The bidder shall list here details of any additional items required for a complete installation | 1 | LS
| 2.5.2 |  | 1 | LS
Sub Total of 2.5 |  |  | 1 | LS
|  |  | 1 | LS
2 | 2.6 | Integrated Testing and Commissioning of the Entire System - TSPS, STP | 1 | LS
Sub Total of 2.6 |  |  | 1 | LS
Total of Schedule 2 (Sub Total 2.1+Sub Total 2.2+Sub Total 2.3+Sub Total 2.4+Sub Total 2.5+Sub Total 2.6) Carried to Schedule 2 - Grand Summary of DODDABETTAHALLI STP |  |  | 1 | LS
Note:All quantities in lumpsum |  |  | 1 | LS
|  |  | 1 | LS

## Schedule 3
7 MLD STP at Doddabettahalli
Schedule 3B: Plant and Equipment, Supplied from Within Employer’s Country for STPs
Level | Item No. | Description | Quantity | Unit | Price in INR | Duties | Ex. Work | Local Transport as per contract | GST in INR | Total Price including GST in INR
Mechanical, Electrical Works and Instrumentation ,Control & Automation Works
2 | 3.1 | Process Plant (except Electrical, Instrumentation ,Control & Automation systems) To provide the following systems for | 1 | LS
3 | 3.1.1 | TSPS | 1 | LS
4 | 3.1.1.1 | Inlet & Effluent chambers, Overflow chamber,Screen channels with necessary screening arrangements (Trash & Coarse screen), , Conveyors, Screening collection arrangement,Sluice gates, weir gates and Inlet & Overflow piping with fittings and Hardware with piping and all allied works complete | 1 | LS
5 | 3.1.1.1.1 | Supply of screens, Sluice gate and Pipes | 1 | LS | 7810279.2 |  |  | 351463.2 | 937233.6 | 9098976
5 | 3.1.1.1.2 | Supply of Fittings & other accessories to complete the work | 1 | LS | 1952569.8 |  |  | 87865.8 | 234308.4 | 2274744
4 | 3.1.1.2 | Wet well with superstructure & Pumping system, Submersible pumps with suitable valves and piping arrangements and Hardware and all allied works complete | 1 | LS
5 | 3.1.1.2.1 | Supply of Submersible Pumps, valves and Pipes | 1 | LS | 2258227.2 |  |  | 127722.4 | 270987.2 | 2656936.8
5 | 3.1.1.2.2 | Supply of Fittings & other accessories to complete the work | 1 | LS | 564556.8 |  |  | 31930.6 | 67746.8 | 664234.2
4 | 3.1.1.3 | Material handling system with suitable Cranes and hoist arrangements with Hardware and all allied works complete | 1 | LS
5 | 3.1.1.3.1 | Supply of Lifting arrangement along with allied components to complete the work | 1 | LS | 788800 |  |  | 35496 | 94656 | 918952
4 | 3.1.1.4 | Miscellaneous works such as flushing arrangements, dewatering and ventilation system including Hardware all allied works complete | 1 | LS
5 | 3.1.1.4.1 | Supply of dewatering pumps | 1 | LS | 309778 |  |  | 12770.8 | 37173.5 | 359722.3
5 | 3.1.1.4.2 | Supply of GI pipe and valves along with allied components to complete the work | 1 | LS | 132762 |  |  | 5473.2 | 15931.5 | 154166.7
|  | STP | 1 | LS
4 | 3.1.1.5 | Inlet chamber and Fine Screen Channel, Overflow chamber, Screen Effluent/ Grit Basin Distribution Channel with Sluice gates, weir gates,Stop logs, and Inlet & Overflow piping with fittings, flushing arrangement, including Hardware all allied works complete | 1 | LS
5 | 3.1.1.5.1 | Supply of Sluice Gates | 1 | LS | 2502028.8 |  |  | 112440.6 | 300243.6 | 2914713
5 | 3.1.1.5.2 | Supply of Pipes and Fittings along with allied components to complete the work | 1 | LS | 278003.2 |  |  | 12493.4 | 33360.4 | 323857
4 | 3.1.1.6 | Screen chamber with effluent channel, Drain pumiping and Fine screening, Conveyors, Screening collection arrangement, flushing arrangement,including Hardware all allied works complete | 1 | LS
5 | 3.1.1.6.1 | Supply of Fine screen,conveyor & Pipes | 1 | LS | 3891112.8 |  |  | 159482.4 | 466933.6 | 4517528.8
5 | 3.1.1.6.2 | Supply of Fittings & other accessories to complete the work | 1 | LS | 972778.2 |  |  | 39870.6 | 116733.4 | 1129382.2
4 | 3.1.1.7 | Vortex Grit mechanism with grit classifier & washing mechanism,Conveyors, Grit collection arrangement, sluice gates,Stop logs, flushing arrangement, including Hardware all allied works complete | 1 | LS
5 | 3.1.1.7.1 | Supply of Vortex grit mechanism | 1 | LS | 9709151.35 |  |  | 436911.9 | 1165098.4 | 11311161.65
5 | 3.1.1.7.2 | Supply of Grit transfer pump | 1 | LS | 571126.55 |  |  | 25700.7 | 68535.2 | 665362.45
5 | 3.1.1.7.3 | Supply of Washer mechanism | 1 | LS | 571126.55 |  |  | 25700.7 | 68535.2 | 665362.45
5 | 3.1.1.7.4 | Supply of gates along with allied components to complete the work | 1 | LS | 571126.55 |  |  | 25700.7 | 68535.2 | 665362.45
4 | 3.1.1.8 | Aeration Basin with Aeration arrangement with piping, Sluice gates and weir gates,Stop logs, flushing arrangement, including Hardware all allied works complete | 1 | LS
5 | 3.1.1.8.1 | Supply of Sluice gates for SBR Basin | 1 | LS | 1146011.4 |  |  | 51570.9 | 137521.8 | 1335104.1
5 | 3.1.1.8.2 | Supply of Pipes and Fittings along with allied components to complete the work | 1 | LS | 127334.6 |  |  | 5730.1 | 15280.2 | 148344.9
4 | 3.1.1.9 | Anaerobic Zone Inlet arrangement including pipework,Submersible mixer arrangement,and Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
4 | 3.1.1.10 | Anoxic zone Inlet arrangement Inlet arrangement including pipework,Submersible mixer arrangement,and Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete | 1 | LS
4 | 3.1.1.11 | Deareation zone Inlet arrangement Inlet arrangement including pipework,Submersible mixer arrangement,and Handling Equipment, flushing arrangement, Hardware with piping and all allied works complete. | 1 | LS
4 | 3.1.1.12 | Aeration Zone with MLR Pumpsets, Retrievable type Fine Bubble Diffuser Aeration system arrangement, Pipe grid, Drop legs,piping arrangements,Drain pumpsets, Electric hoist, sluice gates, flushing arrangement,Handling Equipment,piping and valves including Hardware all allied works complete | 1 | LS
5 | 3.1.1.12.1 | Supply of Decanter for SBR Technology | 1 | LS | 32681750.4 |  |  | 1559546.4 | 3921810.4 | 38163107.2
5 | 3.1.1.12.2 | Supply of fine bubble diffusers for SBR technology | 1 | LS | 4085218.8 |  |  | 194943.3 | 490226.3 | 4770388.4
5 | 3.1.1.12.3 | Supply of pipe grid and fittings, WAS pumps for SBR Technology and all other equipments required for SBR technology | 1 | LS | 4085218.8 |  |  | 194943.3 | 490226.3 | 4770388.4
4 | 3.1.1.13 | Process Air Blower Building with blowers, Air Coolers,EOT Crane, Service water & blower cooling arrangement, Piping and valves,Handling Equipment,Ventilation system, Hardware and all allied works complete | 1 | LS
5 | 3.1.1.13.1 | Supply of Air blowers | 1 | LS | 4679991 |  |  | 342288.9 | 561599.1 | 5583879
5 | 3.1.1.13.2 | Supply of Lifting arrangement along with allied components to complete the work | 1 | LS | 519999 |  |  | 38032.1 | 62399.9 | 620431
4 | 3.1.1.14 | Alum solution Preparation and dosing which includes minimum of preparation and dosing pumpsets, agitators, mixing arrangement, flushing arrangement,Channel mounted mixer for alum mixing, Handling Equipment, Ventilation system, Hardware with piping and all allied works complete | 1 | LS
5 | 3.1.1.14.1 | Supply of Alum dosing pumps | 1 | LS | 862873.2 |  |  | 38077.65 | 103545 | 1004495.85
5 | 3.1.1.14.2 | Supply of Agitators | 1 | LS | 287624.4 |  |  | 12692.55 | 34515 | 334831.95
5 | 3.1.1.14.3 | Supply of Alum dosing Tanks along with allied components to complete the work | 1 | LS | 766998.4 |  |  | 33846.8 | 92040 | 892885.2
4 | 3.1.1.15 | Inlet & Outlet piping, distribution chamber for secondary clarifiers with Inlet & outlet Sluice gates, stoplogs, weir arrangement, flushing arrangement, piping and valves including hardware all allied works complete | 1 | LS
4 | 3.1.1.16 | Inlet & Outlet piping, secondary clarifier mechanism, scum collection with desluding arrangements, handling equipment, Flushing arrangement, piping and valves including hardware all allied works complete | 1 | LS
4 | 3.1.1.20 | Inlet & outlet piping, disc filter influent & Effluent chamber sluice gares, Weir gates, stoplogs, disc filter unit, backwash water system and collection arrangement etc., | 1 | LS
5 | 3.1.1.20.1 | Supply of Disc filter | 1 | LS | 12008844 |  |  | 538895.7 | 1441062 | 13988801.7
5 | 3.1.1.20.2 | Supply of gates and Backwash pumps for filter along with allied components to complete the work | 1 | LS | 1334316 |  |  | 59877.3 | 160118 | 1554311.3
4 | 3.1.1.17 | Material pumping station general arrangement,Pumpsets, Spill Containment Bund flushing arrangement,Material Handling Equipment,fire fighting system for complete STP (inclusive of fire alarm, fire detection, fire extinguishing system and integration with plan SCADA system for monitoring),Ventilation system,Hardware with piping, Valves and all allied works complete | 1 | LS
5 | 3.1.1.17.1 | Supply of fire extinguishers | 1 | LS | 614495.5 |  |  | 34431.25 | 73739.5 | 722666.25
5 | 3.1.1.17.2 | Supply of fire sand bucket | 1 | LS | 614495.5 |  |  | 34431.25 | 73739.5 | 722666.25
5 | 3.1.1.17.3 | Supply of exhaust fan along with allied components to complete the work | 1 | LS | 1228991 |  |  | 68862.5 | 147479 | 1445332.5
4 | 3.1.1.19 | Chlorine & any chemical dosing arrangement, flushing arrangement, Handling Equipment,Ventilation system, Hardware with piping and all allied works complete | 1 | LS
5 | 3.1.1.19.1 | Supply of Chlorination system | 1 | LS | 5361300.8 |  |  | 240591.2 | 643356.8 | 6245248.8
5 | 3.1.1.19.2 | Supply of liftinig arrangement and Chlorine tonner along with allied components to complete the work | 1 | LS | 1340325.2 |  |  | 60147.8 | 160839.2 | 1561312.2
4 | 3.1.1.18 | Inlet & Outlet piping,Chlorine Contact Tank & Outfall structure with sluice gates,weir gates,Stop logs, mixing arrangement, hardware with piping, valves and all allied works complete | 1 | LS
5 | 3.1.1.18.1 | Supply of Sluice Gates | 1 | LS | 539757.9 |  |  | 24289.2 | 64771.2 | 628818.3
5 | 3.1.1.18.2 | Supply of Pipes and Valves along with allied components to complete the work | 1 | LS | 59973.1 |  |  | 2698.8 | 7196.8 | 69868.7
4 | 3.1.1.21 | Sludge dewatering Unit- Submersiible mixer arrangement, sludge feed pumpsets, flushing arrangement ventilation system, handling equipments and hardware with piping, valves and all allied works complete | 1 | LS
5 | 3.1.1.21.1 | Supply of centrifuge feed pumps | 1 | LS | 516274.8 |  |  | 23132.2 | 61953 | 601360
5 | 3.1.1.21.2 | Supply of Dewatering unit- Centrifuge | 1 | LS | 1806961.8 |  |  | 80962.7 | 216835.5 | 2104760
5 | 3.1.1.21.3 | Supply of lifting arrangements and pipes and valves along with allied components to complete the work | 1 | LS | 258137.4 |  |  | 11566.1 | 30976.5 | 300680
4 | 3.1.1.22 | Poly elelctrolyte dosing system for thickness strirrer arrangement, sludge feed pumpsets, flushing arrangement, ventilation system, handling equipment, Ventilation | 1 | LS
5 | 3.1.1.22.1 | Supply of Auto- Polymer System | 1 | LS | 3039563.7 |  |  | 136329.3 | 364748.4 | 3540641.4
5 | 3.1.1.22.2 | Supply of pipes and valves along with allied components to complete the work | 1 | LS | 337729.3 |  |  | 15147.7 | 40527.6 | 393404.6
4 | 3.1.1.23 | Sludge thickening unit, sludge cake conveying system with cut gate arrangement and hopper & collection system , handling equipment for dewatering unit, flushing arrangement, ventilation system, hardware with piping and allied works complete | 1 | LS
5 | 3.1.1.23.1 | Supply of Sudge thickener mechanism | 1 | LS | 6066646.2 |  |  | 272548.8 | 727998.3 | 7067193.3
5 | 3.1.1.23.2 | Supply of Mixers for thickened sludge sump, pipes and valves along with allied components to complete the work | 1 | LS | 674071.8 |  |  | 30283.2 | 80888.7 | 785243.7
4 | 3.1.1.24 | Inlet & Outlet piping,Plant drain sump & Pump Station, Submersible pumpsets,Handling Equipment, Hardware with piping, Valves and all allied works complete | 1 | LS
5 | 3.1.1.24.1 | Supply of submersible pump | 1 | LS | 856305.6 |  |  | 38533.6 | 102756.8 | 997596
5 | 3.1.1.24.2 | Supply of lifting arrangements, pipes, valves along with allied components to complete the work | 1 | LS | 214076.4 |  |  | 9633.4 | 25689.2 | 249399
4 | 3.1.1.25 | Inlet & Outlet piping, Treated water storage Pump Station, Submersible pumpsets,Handling Equipment, Hardware with piping, Valves and all allied works complete | 1 | LS
5 | 3.1.1.25.1 | Supply of submersible pump | 1 | LS | 1378565.6 |  |  | 62036 | 165428 | 1606029.6
5 | 3.1.1.25.2 | Supply of lifting arrangements, pipes, valves along with allied components to complete the work | 1 | LS | 344641.4 |  |  | 15509 | 41357 | 401507.4
4 | 3.1.1.26 | Inlet & Outlet piping,Plant water Pump Station,Submersible pumpsets,Handling Equipment, Sluice gates, Weir gates, Stop log gates, Hardware with piping, Valves and all allied works complete | 1 | LS
5 | 3.1.1.26.1 | Supply of submersible pump | 1 | LS | 828261.6 |  |  | 37272.8 | 99392 | 964926.4
5 | 3.1.1.26.2 | Supply of lifting arrangements, pipes, valves along with allied components to complete the work | 1 | LS | 207065.4 |  |  | 9318.2 | 24848 | 241231.6
4 | 3.1.1.27 | Flushing arrangement for all chemical & Sludge handling system, Dewatering Pumps including piping and all allied works in all sludge & Chemical handling pump houses complete | 1 | LS
5 | 3.1.1.27.1 | Supply of GI pipe and valves along with allied components to complete the work | 1 | LS | 2014356 |  |  | 87306 | 241723 | 2343385
4 | 3.1.1.28 | The bidder shall list here details of any additional items (all areas of the works) required for a complete installation | 1 | LS
| 3.1.1.29 |  | 1 | LS
| 3.1.1.30 |  | 1 | LS
| 3.1.1.31 |  | 1 | LS
| 3.1.1.32 |  | 1 | LS
|  | Sub Total of 3.1 | 1 | LS
|  |  | 1 | LS
2 | 3.2 | Electrical Systems | 1 | LS
3 | 3.2.1 | Supply of of 11kV underground Cables, Termination Kits at following locations as per scope, specification and drawings. | 1 | LS
4 | 3.2.1.1 | 11kV Outdoor cable termination at Tariff Metering Unit / BESCOM | 1 | LS | 31627 |  |  | 720 | 3797 | 36144
4 | 3.2.1.2 | 11kV Indoor cable terminations at incomer and outgoings of 11kV Metal Enclosed Switchboard of Sewage Treatment Plant | 1 | LS | 43485 |  |  | 989 | 5219 | 49693
4 | 3.2.1.3 | 11kV Outdoor cable terminations at primary side of 11kV / 0.433 kV Transformers of Sewage Treatment Plant | 1 | LS | 35579 |  |  | 810 | 4270 | 40659
4 | 3.2.1.4 | 11kV XLPE Cable from Metering Unit to incomer of 11kV Metal Enclosed Switchboard of Sewage Treatment Plant | 1 | LS | 158127 |  |  | 3595 | 18977 | 180699
4 | 3.2.1.5 | 11kV XLPE Cables from 11kV Metal Enclosed Switchboard to Primary cable end boxes of 11kV/0.433kV Transformers of Sewage Treatment Plant | 1 | LS | 118595 |  |  | 2696 | 14233 | 135524
4 | 3.2.1.6 | 11kV XLPE Cable from existing Metering Unit to Proposed 11kV Metal Enclosed Switchboard if applicable | 1 | LS
4 | 3.2.1.7 | 11kV XLPE Cable from Proposed 11kV Metal Enclosed Switchboard to 11kV Metal Enclosed Switchboard at Existing Sewage Treatment Plant if applicable | 1 | LS
4 | 3.2.1.8 | 11kV Cable Straight through joints | 1 | LS | 7908 |  |  | 181 | 950 | 9039
3 | 3.2.2 | Supply of Electrical equipments at Sewage Treatment Plant Substation Building & Process Air Blower Building as per scope, specification and drawings. | 1 | LS
4 | 3.2.2.1 | 11kV Metal Enclosed Switchboard | 1 | LS | 800514 |  |  | 18195 | 96062 | 914771
4 | 3.2.2.2 | Diesel Generator Set complete with AMF Control Panel | 1 | LS | 3913620 |  |  | 88947 | 469635 | 4472202
4 | 3.2.2.3 | 11kV / 0.433kV Transformers with OLTC | 1 | LS | 1334189 |  |  | 30324 | 160103 | 1524616
4 | 3.2.2.4 | LT Non Segregated Aluminium Bus ducts with necessary supporting structure | 1 | LS | 800514 |  |  | 18195 | 96062 | 914771
4 | 3.2.2.5 | 415V Switchgear PCC | 1 | LS | 1601027 |  |  | 36388 | 192124 | 1829539
4 | 3.2.2.6 | 415V Capacitor banks with Automatic Power Factor Correction Relay | 1 | LS | 266838 |  |  | 6066 | 32021 | 304925
4 | 3.2.2.7 | 110V D.C Battery Bank, Battery Charger with D.C Distribution Board | 1 | LS | 177893 |  |  | 4044 | 21348 | 203285
3 | 3.2.3 | Supply of Motor Control Centers , Distribution boards etc of Motor Control Centres, Distribution boards etc at various locations in TSPS & Sewage Treatment plant with following major equipment, items as per scope, specification and drawings. | 1 | LS
4 | 3.2.3.1 | TSPS MCC | 1 | LS | 581114 |  |  | 13208 | 69734 | 664056
4 | 3.2.3.2 | Process Air Blower MCC | 1 | LS | 498098 |  |  | 11321 | 59773 | 569192
4 | 3.2.3.3 | Headworks MCC | 1 | LS | 415081 |  |  | 9435 | 49810 | 474326
4 | 3.2.3.4 | Centrifuge MCC | 1 | LS | 456590 |  |  | 10378 | 54792 | 521760
4 | 3.2.3.5 | RAS MCC | 1 | LS
5 | 3.2.3.5.1 | WAS MCC for SBR Technology | 1 | LS | 373573 |  |  | 8491 | 44830 | 426894
4 | 3.2.3.6 | Chlorine MCC | 1 | LS | 332065 |  |  | 7548 | 39849 | 379462
4 | 3.2.3.7 | Main Lighting DB | 1 | LS | 124525 |  |  | 2831 | 14944 | 142300
4 | 3.2.3.8 | Variable Frequency Drives MCC | 1 | LS | 1245243 |  |  | 28302 | 149430 | 1422975
4 | 2.3.3.9 | Local Push Button Stations | 1 | LS | 83017 |  |  | 1888 | 9963 | 94868
4 | 3.2.3.10 | Miscellaneous works-Distribution Board | 1 | LS | 41509 |  |  | 945 | 4982 | 47436
3 | 3.2.4 | Supply of Lighting System at TSPS & Sewage Treatment Plant with following major equipment, items as per scope, specification and drawings. | 1 | LS
4 | 3.2.4.1 | Lighting Fixtures | 1 | LS | 332065 |  |  | 7548 | 39849 | 379462
4 | 3.2.4.2 | Lighting panels | 1 | LS | 189753 |  |  | 4314 | 22772 | 216839
4 | 3.2.4.3 | Switchboards, Receptacles, Power Plug & Sockets, Switches, Ceiling fans with regulators etc | 1 | LS | 142314 |  |  | 3235 | 17079 | 162628
4 | 3.2.4.4 | Point wiring with conduits, wires, supports etc for Lighting fixtures, Receptacles, Ceiling fans etc | 1 | LS | 158127 |  |  | 3595 | 18977 | 180699
4 | 3.2.4.5 | Street Lighting and Area Lighting poles with Junction boxes and Over hang | 1 | LS | 759006 |  |  | 17252 | 91082 | 867340
3 | 3.2.5 | Supply of L.T Cabling System, HT/LT Cable Carrier System of L.T Cabling System, HT/LT Cable Carrier System at TSPS & Sewage Treatment Plant with following major components as per scope, specification and drawings. | 1 | LS
4 | 3.2.5.1 | L.T cables | 1 | LS | 2698026 |  |  | 61320 | 323765 | 3083111
4 | 3.2.5.2 | L.T Cable termination with glands and lugs | 1 | LS | 581114 |  |  | 13208 | 69734 | 664056
4 | 3.2.5.3 | Cable trays on supports for both LT and HT Cables | 1 | LS | 664130 |  |  | 15095 | 79697 | 758922
4 | 3.2.5.4 | Hume Pipe | 1 | LS | 207541 |  |  | 4718 | 24906 | 237165
3 | 3.2.6 | Supply of Earthing & Lightning Protection System of Earthing & Lighting Protection System at TSPS & Sewage Treatment Plant with following major components as per scope, specification and drawings. | 1 | LS
4 | 3.2.6.1 | Earthing Conductor for outdoor main grid | 1 | LS | 88947 |  |  | 2022 | 10675 | 101644
4 | 3.2.6.2 | Earthing Conductor for indoor main grid | 1 | LS | 148245 |  |  | 3370 | 17790 | 169405
4 | 3.2.6.3 | Earthing Conductors for outdoor equipments and Junction Boxes | 1 | LS | 94877 |  |  | 2158 | 11387 | 108422
4 | 3.2.6.4 | Lightning Protection system with Arrestors and Down Conductors | 1 | LS | 59298 |  |  | 1348 | 7117 | 67763
4 | 3.2.6.5 | Earthing Conductor for indoor equipments | 1 | LS | 83017 |  |  | 1888 | 9963 | 94868
4 | 3.2.6.6 | Treated Earth pits | 1 | LS | 118595 |  |  | 2696 | 14233 | 135524
3 | 3.2.7 | Complete Installation, testing and commissioning of safety procedures with Signage for Electrical Equipments at TSPS & Sewage Treatment Plant as per scope, specification and drawings. | 1 | LS
4 | 3.2.7.1 | Supply of Signage board | 1 | LS | 230000 |  |  |  | 27600 | 257600
3 | 3.2.8 | The bidder shall list here details of any additional items required for a complete installation | 1 | LS
| 3.2.8.1 |  | 1 | LS
| 3.2.8.2 |  | 1 | LS
| 3.2.8.3 |  | 1 | LS
|  | Sub Total of 3.2 | 1 | LS
|  |  | 1 | LS
2 | 3.3 | Instrumentation, Control & Automation Systems | 1 | LS
3 | 3.3.1 | Supply of the following Instrumentation Systems as per Technical Specifications. | 1 | LS
4 | 3.3.1.1 | Supplying of Ultrasonic open channel flow measurement with Transmitter's along with required accessaries and fittings for open channel flow measurement for the complete STP. The flow meter shall be Interfaced with PLC based scada control system .Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 1179208 |  |  | 23585 | 141506 | 1344299
4 | 3.3.1.2 | Supplying of Air Flow Measuring System (Thermal mass flowmeter cum transmitter's at individual and common discharge of each air blowers's), Air pressure Measuring System with transmitter (at individual and common discharge of each air blowers's) & Temperature Measuring System with transmitter (at individual and common discharge of each air blowers's) along with the required accessories & fittings for the complete STP.Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 393070 |  |  | 7862 | 47169 | 448101
4 | 3.3.1.3 | Supplying of Electromagnetic Flowmeter's with Indicating Transmitter's with totalizer (full bore type) with flange Ends, rates shall be inclusive of mating flanges with necessary fasteners and gaskets, for the complete STP. The flow meter shall be Interfaced with PLC based scada control system .Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 1572277 |  |  | 31446 | 188674 | 1792397
4 | 3.3.1.4 | Supplying of Ultrasonic Level Transmitter's with indicators & alarms as required including all required Mounting accessories for the complete STP. and Interfacing with PLC based scada control system.Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant.Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 471683 |  |  | 9435 | 56603 | 537721
4 | 3.3.1.5 | Supplying of Differential Level Ultrasonic Sensor's & Transmitter's with indicators & alarms as required including all required Mounting accessories for the complete STP. and Interfacing with PLC based scada control system.Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 550297 |  |  | 11007 | 66037 | 627341
4 | 3.3.1.6 | Supplying of Conductivity type Level Switches (back up to level transmitter), High Level & Low Level sensing -( with 4 point contact) with necessary instrumentation cabling,glands with suitable stub and flange and bolting arrangement for hook-up, for the complete STP and also Interfacing with PLC based scada control system .Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 235842 |  |  | 4718 | 28302 | 268862
4 | 3.3.1.7 | Supplying of Float type Level Gauges with necessary instrumentation cabling,glands with suitable stub and flange and bolting arrangement for hook-up,for the complete STP and also Interfacing with PLC based scada control system.Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 78614 |  |  | 1574 | 9435 | 89623
4 | 3.3.1.8 | Supplying of Pressure Transmitter's with necessary instrumentation cabling,manifold,glands and conduit with suitable stub and flange and bolting arrangement for hook-up, for the complete STP. and also Interfacing with PLC based scada control system .Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 393070 |  |  | 7862 | 47169 | 448101
4 | 3.3.1.9 | Supplying of Pressure Switches on the pump discharge with necessary instrumentation cabling, glands and conduit with suitable stub and flange and bolting arrangement for hook-up, Pressure switch and also Interfacing with PLC based scada control system .Refer clause 13.30 Minimum I/O Requirements for Auto mode Control operation of the Plant | 1 | LS | 314456 |  |  | 6290 | 37735 | 358481
4 | 3.3.1.10 | Supplying of glycerine filled stainless steel pressure gauges of 150 mm Dia. Dail suitable on top of Air vessel with nipple, snubber for vibration resistance and necessary length of SS tubing suitable for mounting , including isolating valve for maintenance etc.,complete with all lead and lifts etc, for the complete STP | 1 | LS | 78614 |  |  | 1574 | 9435 | 89623
4 | 3.3.1.11 | Supplying of Field instruments IP-65 enclosures for complete field instrumentation | 1 | LS | 157228 |  |  | 3146 | 18869 | 179243
4 | 3.3.1.12 | Supplying of Field Junction boxes | 1 | LS | 235842 |  |  | 4718 | 28302 | 268862
4 | 3.3.1.13 | Supplying of Surge protection Devices for all the instruments | 1 | LS | 786139 |  |  | 15723 | 94337 | 896199
4 | 3.3.1.14 | Supply of on-line UPS system for complete ICA equipment inclusive of wireless communication equipment,CCTV systems,field instrumentation ,control and Automation system with 120 mins backup on full load. | 1 | LS | 628911 |  |  | 12579 | 75470 | 716960
4 | 3.3.1.15 | Supplying of 24V DC power supply system with SMF batteries & battery charger with DC distribution board with all accessories complete | 1 | LS | 196535 |  |  | 3931 | 23585 | 224051
4 | 3.3.1.16 | Supplying of Air conditioning system for control room with all accessories complete as required under specifications | 1 | LS | 78614 |  |  | 1574 | 9435 | 89623
4 | 3.3.1.17 | Supplying of Temperature-Measuring System with required Accessories & fittings | 1 | LS | 117921 |  |  | 2359 | 14151 | 134431
4 | 3.3.1.18 | Instrumentation Earthing system for complete STP | 1 | LS | 196535 |  |  | 3931 | 23585 | 224051
4 | 3.3.1.19 | Suppliying of Weight Indicator cum Transmitter with required accessaries & fittings | 1 | LS | 39307 |  |  | 787 | 4718 | 44812
4 | 3.3.1.20 | Supplying of sludge blanket level transmitters for the complete STP including all required Mounting accessories. and Interfacing with PLC based scada control system. | 1 | LS | 157228 |  |  | 3146 | 18869 | 179243
3 | 3.3.2 | Supply of Online Analytical Instruments as per Technical Specifications. | 1 | LS
4 | 3.3.2.1 | Dissolved Oxygen Analyzer + Accessories + fittings | 1 | LS | 361625 |  |  | 7234 | 43396 | 412255
4 | 3.3.2.2 | ORP Analyzer's+ Accessories + fittings | 1 | LS | 157228 |  |  | 3146 | 18869 | 179243
4 | 3.3.2.3 | p H Analyzer+ Accessories + fittings | 1 | LS | 141506 |  |  | 2831 | 16981 | 161318
4 | 3.3.2.4 | Conductivity Analzyer+ Accessories + fittings | 1 | LS | 235842 |  |  | 4718 | 28302 | 268862
4 | 3.3.2.5 | Residual Chlorine Analyzer+ Accessories +fittings | 1 | LS | 283011 |  |  | 5661 | 33962 | 322634
4 | 3.3.2.6 | MLSS Analyzer-+ Accessories+ Fittings | 1 | LS | 393070 |  |  | 7862 | 47169 | 448101
3 | 3.3.3 | Supply of Online Real Time Multi Parameters Continuous Monitoring System for Influent and Treated Sewage Parameters & AutoSamplers | 1 | LS | [5 empty] | 0
4 | 3.3.3.1 | All weather refrigerated Auto sampler's as per specifications | 1 | LS | 336917 |  |  | 6739 | 40431 | 384087
4 | 3.3.3.2 | Real time Multi Parameters Continuous Monitoring System for Influent and Treated Sewage Parameters at Inlet & outlet of STP to measure the following parameters (BOD,COD,TSS,COLOR,p H, Ammonical Nitrogen,Dissolved Oxygen & Temperature) and communication modules to transmit the data to SCADA system,CPCB and KSPCB data centers as and when required. | 1 | LS | 1347666 |  |  | 26954 | 161720 | 1536340
3 | 3.3.4 | Supply of the Instrumentation Cables/cable trays as per Technical Specification | 1 | LS
4 | 3.3.4.1 | Suppying of Instrumentation & Control Cables and Power Cables, OFC, Glands & Lugs, cable conduits ,etc as required to complete the entire Instrumentation,control and automation system ,required as per specifications | 1 | LS | 1302743 |  |  | 26056 | 156330 | 1485129
4 | 3.3.4.2 | Supplying and installation of hot dip GI perforated cable tray's with cover along with required angle supports, with coupler plates, Anchor bolts and nuts etc complete and the tray should be fitted on the wall / ceiling etc. complete for all instrumentation cables | 1 | LS | 943366 |  |  | 18869 | 113205 | 1075440
3 | 3.3.5 | Any other item & accessories not specified above but required to complete the work as per bid specifications. Note: 1. Contractor shall list down all equipment with breakup of item, quantity and include the total price of these items. 2. Items not listed and required for completing the job shall be done by contractor without any additional payment. | 1 | LS
3 | 3.3.6 | Control & Automation System | 1 | LS
4 | 3.3.6.1 | Supplying of redundant PLC (Hot standby PLC system), I/O Modules (critical inputs shall be on dual I/O's) ,redundant managed ethernet switches,RIO 's with 16"color touch screen HMI, Redundant power supply , Spares as indicated in the specifications,etc..with all required accessories ,required hardware & software complete with licensing,any other hardware & software to meet the requirements as per specifications | 1 | LS | 3517407 |  |  | 70349 | 422090 | 4009846
4 | 3.3.6.2 | Supplying of PLC &16" HMI programming software for all PLC and HMI equipment | 1 | LS | 781646 |  |  | 15634 | 93799 | 891079
4 | 3.3.6.3 | Supplying of redundant SCADA server software(SCADA is on dual redundant server) | 1 | LS | 521098 |  |  | 10423 | 62533 | 594054
4 | 3.3.6.4 | Supplying of Historian software | 1 | LS | 325686 |  |  | 6515 | 39083 | 371284
4 | 3.3.6.5 | Supplying of SCADA Server stations with 32" LED monitor sysytem, loaded with latest authorised windows server operating system, latest MS Office professional , licensed latest & proven PLC programming software ,licensed SCADA software,centralized server monitored Anti virus software,required licensed network monitoring software,licensed firewall software,etc... with all accessories complete to meet the requirements as per specifications | 1 | LS | 325686 |  |  | 6515 | 39083 | 371284
4 | 3.3.6.6 | Supplying of SCADA operator stations,engineering stations,Historian Stations & CCTV stations with with 32" LED monitor systems, loaded with latest authorised windows operating system, latest MS Office professional ,licensed SCADA software,licensed client Anti virus software,required licensed network monitoring software,etc.. all accessories complete to meet the requirements as per specifications | 1 | LS | 195412 |  |  | 3909 | 23450 | 222771
4 | 3.3.6.7 | Supplying of multifunction Printers-A3 size servers with all accessories complete and networked with SCADA system | 1 | LS | 130275 |  |  | 2606 | 15634 | 148515
4 | 3.3.6.8 | Supplying of Industrial Laptop 16" screen loaded with authorised windows operating system,MS Office,and PLC & HMI programming software,SCADA software with all accessories complete | 1 | LS | 260549 |  |  | 5212 | 31267 | 297028
4 | 3.3.6.9 | Supplying of LED screens, 55" in array of 2x3 (total 6 monitors) networked with SCADA & CCTV servers to display the SCADA screens, CCTV feeds, with all accessories complete in real time. | 1 | LS | 325686 |  |  | 6515 | 39083 | 371284
4 | 3.3.6.10 | Supplying of SCADA System industrial consoles for housing the complete SCADA system with all accessories complete as per specifications | 1 | LS | 130275 |  |  | 2606 | 15634 | 148515
3 | 3.3.7 | Communication Interface Equipment | 1 | LS
4 | 3.3.7.1 | Interoperability test in co-ordination with CP-024 & MIS-2 SCADA Contract @ Shimsha Bhavan to achieve complete data integration between sewerage contracts and centralized SCADA centers to meet the requirements as per specifications | 1 | LS | 911921 |  |  | 18239 | 109431 | 1039591
4 | 3.3.7.2 | Supplying of redundant GPRS Communication modules with redundant SIM cards,redundant power supply units with all required accessories to communicate & receive data from ISPS,CP-024 & MIS-2 SCADA Contract @ Shimsha Bhavan for bulk data transfer for monitoring and control. | 1 | LS | 660357 |  |  | 13208 | 79244 | 752809
3 | 3.3.8 | Monitoring Requirements | 1 | LS | [5 empty] | 0
4 | 3.3.8.1 | Supplying of CCTV IR water proof cameras suitable for upto 100ft.with IR Dome camera, 360 degrees view,control key board, DVR, Hard Disk, cables, UPT transreceivers ,complete with all required accessories,software and hardware required,CCTV server station loaded with CCTV software with latest windows OS with minimum 1 TB hard drive,licensed anti virus,etc,32"LED monitors connected via LAN to SCADA servers,mounting poles,fixtures,etc.. (Close Circuit Television System to be installed to cover all areas of the facilities,inclusive of high speed internet bandwidth as required to monitor the CCTV feed remotely and via web based broswers.CCTV feeds shall be monitored from SCADA control room ) | 1 | LS | 606451 |  |  | 12130 | 72775 | 691356
4 | 3.3.8.2 | Supplying of Management Information Software (MIS) inclusive of online document management system,seperate dashboard for each work site,implementation,Annual licensing subscription for entire duration of the contract period,five number of user licenses,cloud storage,daily support with 99.99% SLA agreement,24x7 help desk,fully secured hosting cloud server shall be based in India and shall be reputed with SLA agreement for 99.99 availability,security of data with data encryption and certification,allied softwares, Implementation & Maintenance of MIS Software throughtout the duration of the contract period inclusive of daily updation and complete integration with main MIS software as required per specifications. | 1 | LS | 404300 |  |  | 8087 | 48517 | 460904
4 | 3.3.8.3 | Any other item & accessories not specified above but required to complete the work. Note: 1. Contractor shall list down all equipment with breakup of item, quantity and include the total price of these items. 2. Items not listed and required for completing the job shall be done by contractor without any additional payment. | 1 | LS
3 | 3.3.9 | The Bidder shall list here details of any additional items required for a complete installation | 1 | LS
| 3.3.9.1 |  | 1 | LS
| 3.3.9.2 |  | 1 | LS
| 3.3.9.3 |  | 1 | LS
|  | Sub Total of 3.3 | 1 | LS
|  |  | 1 | LS
2 | 3.4 | General Mechanical Systems | 1 | LS
3 | 3.4.1 | Building Services including domestic water systems The bidder shall list here details of any additional items required for a complete installation | 1 | LS
| 3.4.2 |  | 1 | LS
| 3.4.3 |  | 1 | LS
Sub Total of 3.4
|  | Total of Schedule 3A (Sub Total 3.1+Sub Total 3.2+Sub Total 3.3+Sub Total 3.4) Carried to Schedule 3 - Grand Summary of DODDABETTAHALLI STP | [7 empty] | 192931039
Note:All quantities in lumpsum

## Schedule 4
7 MLD at Doddabettahalli
Schedule 4: Requirement of Office of the Engineer
Level | Item No. | Description | Quantity | Unit | Price in INR | Duties | Ex. Work | Local Transport | GST in INR | Total Price including GST in INR
2 | 4.1 | The following equipment, furniture and furnishings for each Proposed STP under the contract shall include:
Office furniture shall be of Godrej or Featherlite
3 | 4.1.1 | Conference table 10'-0" x 5'-0" with 6 chairs - 1 set complete | 1 | No | 50000 |  |  |  | 6000 | 56000
3 | 4.1.2 | 5' x 3' table with both side drawers (1 on each side) - 1 set complete | 1 | No | 10000 |  |  |  | 1200 | 11200
3 | 4.1.3 | 4' x 2 ½' table with both side drawers (3 on each side) - 1 set complete | 1 | No | 20000 |  |  |  | 2400 | 22400
3 | 4.1.4 | Executive Chairs (approved make) excluding chairs for Computer and Conference -1 set complete | 1 | No | 20000 |  |  |  | 2400 | 22400
3 | 4.1.5 | Steel cupboards (Storewel type or similar approved) - 2 sets | 1 | No | 30000 |  |  |  | 3600 | 33600
3 | 4.1.6 | Oscillating or wall mounted fan 400 mm dia - 3 Nos. | 1 | No | 7500 |  |  |  | 900 | 8400
3 | 4.1.7 | Computer Table and Chair - 1 set | 1 | No | 8000 |  |  |  | 960 | 8960
3 | 4.1.8 | Personal Computer - with following Features, plus UPS: - 3.0 MHz processor, ATX cabinet, 256 KB external cache, 3GB RAM, ITB HDD, DVD Drive/RW, 32'' LED flat panel colour monitor, 8USB 2.0 ports, with at least 2 of these in the front, Standard 101/102 keyboard,Optical Mouse and Mouse Pad (two sets), Pre-loaded with licensed Windows OS(Latest), Comphrensive Security and Management features such as antivirus, antispyware, and firewall, additional software - MS Office (latest version), Autocad latest version All the necessary consumables including paper, CDs,Printer catridges etc.- 1 set Complete. | 1 | SET | 100000 |  |  |  | 12000 | 112000
3 | 4.1.9 | Telephone line with STD Facility and high speed broadband internet- 1 set complete | 1 | No | 8000 |  |  |  | 960 | 8960
3 | 4.1.10 | Fire Extinguisher – CO2 type (3 Kg) with other accessories- 4 sets complete | 1 | No | 12000 |  |  |  | 1440 | 13440
3 | 4.1.11 | Supply, Installation, testing and commissioning of Lighting System covering Lighting Distribution board, Switchboards, Switch sockets, Power Plug & Sockets, Luminaries, Ceiling Fans, Cables, Conduits, wires, earthing etc. for the Site Office complete as per Specification- 1 set | 1 | JOB | 35000 |  |  |  | 4200 | 39200
Total to be Carried to Schedule 4, Grand Summary of Doddabettahalli STP

## Schedule 5
0
Schedule 5:Laboratory Equipments
Level | Item No. | Description | Quantity | Unit | Price in INR | Duties | Ex. Work | Local Transport | GST in INR | Total price including GST in INR
2 | 5.1 | Laboratory Equipments under the contract shall include:
3 | 5.1.1 | Comparator test set for residual chlorine or Chloro Scope | 1 | No | 10448 |  |  |  | 1254 | 11702
3 | 5.1.2 | Multi Parameter (pH and Conductivity Meter) | 1 | No | 59441 |  |  |  | 7133 | 66574
3 | 5.1.3 | Mains operated pH Meter completed with one calomel electrode and glass electrode | 1 | No | 42510 |  |  |  | 5102 | 47612
3 | 5.1.4 | Turbidimeter - Bench Model (Nephelometric Type) | 1 | No | 157070 |  |  |  | 18849 | 175919
3 | 5.1.5 | Turbidimeter - Hand held (Portable) | 1 | No | 63116 |  |  |  | 7574 | 70690
3 | 5.1.6 | Spectrophotometer | 1 | No | 92657 |  |  |  | 11119 | 103776
3 | 5.1.7 | Water bath with 6 to 8 concentric holes and discs, electrically heated | 1 | No | 23539 |  |  |  | 2825 | 26364
3 | 5.1.8 | Soxhlet extraction unit | 1 | No | 25866 |  |  |  | 3104 | 28970
3 | 5.1.9 | Kjeldahl digestion unit | 1 | No | 106346 |  |  |  | 12762 | 119108
3 | 5.1.10 | Hot Plates | 10 | No | 2269580 |  |  |  | 27235 | 2296815
3 | 5.1.11 | Distilled Water Plant | 1 | No | 15779 |  |  |  | 1894 | 17673
3 | 5.1.12 | Deminerailiser | 1 | No | 25218 |  |  |  | 3027 | 28245
3 | 5.1.13 | Refrigerator (320 lts Capacity) double door | 1 | No | 32783 |  |  |  | 3934 | 36717
3 | 5.1.14 | B.O.D Incubator | 1 | No | 75599 |  |  |  | 9072 | 84671
3 | 5.1.15 | Muffle furnace | 1 | No | 49607 |  |  |  | 5953 | 55560
3 | 5.1.16 | Electric Oven | 1 | No | 34945 |  |  |  | 4194 | 39139
3 | 5.1.17 | Magnetic stirrer | 1 | No | 6017 |  |  |  | 722 | 6739
3 | 5.1.18 | Monopan balance with digital display | 1 | No | 32639 |  |  |  | 3917 | 36556
3 | 5.1.19 | Jar-Test apparatus with RPM controller and simultaneous addition of Chemicals in all jars | 1 | No | 46041 |  |  |  | 5525 | 51566
3 | 5.1.20 | Centrifuge | 1 | No | 11089 |  |  |  | 1331 | 12420
3 | 5.1.21 | Gas Cylinder if gas supply is not available | 1 | No | 18013 |  |  |  | 2162 | 20175
3 | 5.1.22 | Fume cupboard/hood | 2 | No | 337194 |  |  |  | 20232 | 357426
3 | 5.1.23 | Filed Test kit for Cations and anions | 2 | No | 389070 |  |  |  | 23345 | 412415
3 | 5.1.24 | Depth Sampler | 2 | No | 54470 |  |  |  | 3269 | 57739
3 | 5.1.25 | Online Total organic carbon analytical analyser | 1 | No | 50363 |  |  |  | 6044 | 56407
3 | 5.1.26 | Sieve shaker with standard sieves and Two pan balance weight upto 200 gm samples | 1 | No | 47337 |  |  |  | 5681 | 53018
3 | 5.1.27 | Weigh Balance Max. 10 Kg | 1 | No | 23705 |  |  |  | 2845 | 26550
3 | 5.1.28 | Durham tubes and Imhoff cones | 1 | No | 10015 |  |  |  | 1202 | 11217
3 | 5.1.29 | D.O Meter | 1 | No | 57497 |  |  |  | 6900 | 64397
3 | 5.1.30 | LIMS Software & PC based system as per specifications | 1 | No | 120000 |  |  |  | 14400 | 134400
3 | 5.1.31 | Specified Gravity meter | 1 | No | 90000 |  |  |  | 10800 | 100800
3 | 5.1.32 | Consumables - disposable & Reusable type | 1 | No | 210000 |  |  |  | 25200 | 235200
2 | 5.2 | Equipment Needed for Bacteriological Examination
3 | 5.2.1 | Hot air Oven | 1 | No | 34945 |  |  |  | 4194 | 39139
3 | 5.2.2 | Autoclave | 1 | No | 33071 |  |  |  | 3969 | 37040
3 | 5.2.3 | Incubator 37 deg C or 44 deg C | 1 | No | 75599 |  |  |  | 9072 | 84671
3 | 5.2.4 | Binocular microscope | 1 | No | 19814 |  |  |  | 2378 | 22192
3 | 5.2.5 | Digital pH Meter | 1 | No | 45032 |  |  |  | 5404 | 50436
3 | 5.2.6 | Pipette Box SS | 10 | No | 147710 |  |  |  | 1773 | 149483
3 | 5.2.7 | Wooden/Aluminum Racks | 5 | No | 280995 |  |  |  | 6744 | 287739
3 | 5.2.8 | Wire Baskets | 10 | No | 32430 |  |  |  | 390 | 32820
3 | 5.2.9 | Cotton/Aluminum foils | 10 | No | 43230 |  |  |  | 519 | 43749
3 | 5.2.10 | Burners with Pilot Lamp | 3 | No | 11544 |  |  |  | 462 | 12006
3 | 5.2.11 | Suction Flask 1 ltr Cap | 2 | No | 10378 |  |  |  | 623 | 11001
3 | 5.2.12 | Suction Pump | 1 | No | 7350 |  |  |  | 882 | 8232
3 | 5.2.13 | Sampling Bottles | 10 | No | 44310 |  |  |  | 532 | 44842
3 | 5.2.14 | Measuring Cylinders | 3 | No | 35667 |  |  |  | 1427 | 37094
3 | 5.2.15 | Vaccum pump | 1 | No | 20895 |  |  |  | 2508 | 23403
2 | 5.3 | Bacteriological Media
3 | 5.3.1 | M. Endo Broth 9dehyrated) | 1 | No | 1761 |  |  |  | 212 | 1973
3 | 5.3.2 | Lactose or Lauryl Tryptose Broth | 1 | No | 3920 |  |  |  | 471 | 4391
3 | 5.3.3 | Mac Conkey broth | 1 | No | 3267 |  |  |  | 392 | 3659
3 | 5.3.4 | Brilliant Green Bile Lactose Broth | 1 | No | 1665 |  |  |  | 200 | 1865
3 | 5.3.5 | Total Plate Count Agar | 1 | No | 1373 |  |  |  | 165 | 1538
3 | 5.3.6 | Peptone/Triyptone water | 1 | No | 5880 |  |  |  | 706 | 6586
3 | 5.3.7 | Laminar Air flow Chamber | 1 | No | 23441 |  |  |  | 2813 | 26254
The Bidder shall list here any additional lab. Equipment
| 5.3.8 |  |  | No
| 5.3.9 |  |  | No
| 5.3.10 |  |  | No
| 5.3.11 |  |  | No
No
Total to be Carried to Schedule 5, Grand Summary of Doddabettahalli STP

## Schedule 6
0
Schedule 6: Operation and Maintenance
Level | Item No. | Description | Quantity | Unit | Price in INR | Duties | Ex. Work | Local Transport | GST in INR | Total price including GST in INR
2 | 6.1 | First Year of O&M
3 | 6.1.1 | Manpower + | 1 | Per year | 2873108 |  |  |  | 344773 | 3217881
3 | 6.1.2 | Chemical Usage
4 | 6.1.2.1 | Chlorine ++ | 8.9 | Tonne per year for 7 mld | 97900 |  |  |  | 11748 | 109648
4 | 6.1.2.2 | Poly Electrolyte ++ | 1.11 | Tonne per year for 7 mld | 299700 |  |  |  | 35964 | 335664
4 | 6.1.2.3 | Alum++ | 0 | Tonne per year for 7 mld
4 | 6.1.2.4 | Laboratory Chemicals | 1 | Ls | 405794 |  |  |  | 48696 | 454490
4 | 6.1.2.5 | Laboratory Consumables | 1 | Ls | 270529 |  |  |  | 32464 | 302993
4 | 6.1.2.6 | Any maintenance parts and maintenance consumables | 1 | Ls | 985597 |  |  |  | 118272 | 1103869
3 | 6.1.3 | Trouble shooting and preventive maintenance Network Operating Charges | 1 | Ls | 456763 |  |  |  | 54812 | 511575
3 | 6.1.4 | Transportation and Disposal of Sludge | 1 | Ls | 1210111 |  |  |  | 145214 | 1355325
3 | 6.1.5 | Insurance | 1 | Ls | 208375 |  |  |  | 25005 | 233380
3 | 6.1.6 | The Bidder shall list here any additional items required for O &M
6.1.6.1
6.1.6.2
6.1.6.3
|  | Sub Total of 6.1 for First Year O & M |  |  | 6807870 |  |  |  | 816939 | 7624825
|  | Total for Seven Years O & M (Based on First Year O&M) | 7 | Per Year | 47655090 |  |  |  | 5718573 | 53373775
| Total to be Carried to Schedule 6, Grand Summary of Doddabettahalli STP |  |  |  | 47655090 |  |  |  | 5718573 | 53373775