## Sheet1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
General 915 days 31-07-17 31-01-20 | [6 empty] | General | 31-07-2017 | 31-01-2020
1 Site Establishment & Mobilisation of Contractors 244 days 31-07-17 31-03-18 | [7 empty] | Site Establishment & Mobilisation of Contractors | 31-07-2017 | 31-03-2018
2 General 24 days 31-07-17 23-08-17 | [8 empty] | General | 31-07-2017 | 23-08-2017
3 Notice of commence Work 1 day 31-07-17 31-07-17 | [9 empty] | Notice of commence Work | 31-07-2017 | 31-07-2017
4 Submission of Organisation Chart 1 day 14-08-17 14-08-17 | [9 empty] | Submission of Organisation Chart | 14-08-2017 | 31-07-2017
5 Mobilisation of Contractor Representative 1 day 14-08-17 14-08-17 | [9 empty] | Mobilisation of Contractor Representative | 14-08-2017 | 14-08-2017
6 Mobilisation of Project Manager 1 day 23-08-17 23-08-17 | [9 empty] | Mobilisation of Project Manage | 23-08-2017 | 23-08-2017
7 Handing Over of Site 1 day 10-08-17 10-08-17 | [8 empty] | Handing Over of Site | 2017-10-08 | 2017-10-08
8 Sewage Treatment Plant at Hebbal 1 day 10-08-17 10-08-17 | [9 empty] | Sewage Treatment Plant at Hebba | 2017-10-08 | 2017-10-08
9 Soil Investigation / Soil Survey 141 days 13-08-17 31-12-17 | [8 empty] | Soil Investigation / Soil Survey | 13-08-2017 | 31-12-2017
10 Mobilisation and De-mobilisation of Topographic | [9 empty] | Mobilisation and De-mobilisation of Topographic Survey Team | 13-08-2017 | 31-10-2017
Survey Team
80 days 13-08-17 31-10-17
11 Approval of Topographic Survey 91 days 01-09-17 30-11-17 | [9 empty] | Approval of Topographic Survey | 2017-01-09 | 30-11-2017
12 Mobilisation and De-mobilisation of Geo technical | [9 empty] | Mobilisation and De-mobilisation of Geo technical Survey Team | 2017-06-09 | 25-09-2017
Survey Team | [9 empty] | Approval of Preliminary Bore Hole Layout | 2017-06-09 | 31-12-2017
20 days 06-09-17 25-09-17
13 Approval of Preliminary Bore Hole Layout 117 days 06-09-17 31-12-17
14 Approval of Geo Technical Report 117 days 06-09-17 31-12-17 | [9 empty] | Approval of Geo Technical Report | 2017-06-09 | 31-12-2017
15 Statuory Clearance 184 days 16-08-17 15-02-18 | [8 empty] | Statuory Clearance | 16-08-2017 | 15-02-2018
16 Clearance for Removal of Trees / Sludge Drying | [9 empty] | Clearance for Removal of Trees / Sludge Drying Beds / Shifting of RCC Pipes | 16-08-2017 | 15-01-2018
Beds / Shifting of RCC Pipes
153 days 16-08-17 15-01-18
17 Completion of Tree Cutting work, Breaking Sludge | [9 empty] | Completion of Tree Cutting work, Breaking Sludge Drying Bed and Site Leveling / Shifting of RCC Pipes | 18-09-2017 | 15-02-2018
Drying Bed and Site Leveling / Shifting of RCC
Pipes
151 days 18-09-17 15-02-18
18 Site Establishment 152 days 20-08-17 18-01-18 | [8 empty] | Site Establishment | 20-08-2017 | 18-01-2018
19 Establishment of Site Office 30 days 20-08-17 18-09-17 | [9 empty] | Establishment of Site Office | 20-08-2017 | 18-09-2017
20 Establishment of Construction - Power & Water 60 days 01-09-17 30-10-17 | [9 empty] | Establishment of Construction - Power & Water | 2017-01-09 | 30-10-2017
21 Establishment of Testing Lab 60 days 01-10-17 29-11-17 | [9 empty] | Establishment of Testing Lab | 2017-01-10 | 29/11/2017
22 Establishment of Employer's Office 60 days 20-11-17 18-01-18 | [9 empty] | Establishment of Employer's Office | 20-11-2017 | 18-01-2018
23 Establishment of Storage Yard 20 days 01-11-17 20-11-17 | [9 empty] | Establishment of Storage Yard | 2017-01-11 | 20/11/2017
24 Establishment of Other temporary Structures 60 days 01-10-17 29-11-17 | [9 empty] | Establishment of Other temporary Structures | 2017-01-10 | 29/11/2017
25 Finalisation of Contract 232 days 12-08-17 31-03-18 | [8 empty] | Finalisation of Contract | 2017-12-08 | 31/03/2018
26 Finalisation for Civil Work 32 days 12-08-17 12-09-17 | [9 empty] | Finalisation for Civil Work | 2017-12-08 | 2017-12-09
27 Finalisation for Mechanical Work 30 days 01-02-18 02-03-18 | [9 empty] | Finalisation for Mechanical Work | 2018-01-02 | 2018-02-03
28 Finalisation for Piping Work 31 days 01-02-18 03-03-18 | [9 empty] | Finalisation for Piping Work | 2018-01-02 | 2018-03-03
29 Finalisation for Electrical Work 31 days 01-03-18 31-03-18 | [9 empty] | Finalisation for Electrical Work | 2018-01-03 | 31/3/2018
30 Finalisation for Instrumentation Work 31 days 01-03-18 31-03-18 | [9 empty] | Finalisation for Intrumanteation Work | 2018-01-03 | 31/3/2018
31 Construction 508 days 18-09-17 07-02-19 | [7 empty] | Construction | 18/9/2017 | 2019-07-02
32 Mobilisation 508 days 18-09-17 07-02-19 | [8 empty] | Mobilization | 18/9/2017 | 2019-07-02
33 Mobilisation for Civil 6 days 18-09-17 23-09-17 | [9 empty] | Mobilization for civil | 18/09/2017 | 30/10/2018
34 Mobilisation for Mechanical 30 days 01-10-18 30-10-18 | [9 empty] | Mobilization for Electrical | 2019-01-01 | 2019-07-01
35 Mobilisation for Piping 7 days 01-10-18 07-10-18 | [9 empty] | Mobilization for Mechanical | 2018-01-10 | 30/10/2018
36 Mobilisation for Electrical 7 days 01-01-19 07-01-19 | [9 empty] | Mobilization for Piping | 2018-01-10 | 2018-07-10
37 Mobilisation for Instrumentation 7 days 01-02-19 07-02-19 | [9 empty] | Mobilization for Instrumentation | 2019-01-02 | 2019-07-02
38 Employer's Office 101 days 20-09-17 29-12-17 | [8 empty] | Employer's Office | 20/09/2017 | 29/12/2017
39 Preparation and Submission to Client 15 days 20-09-17 04-10-17 | [9 empty] | Preparation and Submission to Client | 20/09/2017 | 2017-04-10
40 Engineer's Comments on 1st submission 26 days 05-10-17 30-10-17 | [9 empty] | Engineer's Comments on 1st submission | 2017-05-10 | 30/10/2017
41 Resubmission for Code-B Approval 10 days 01-11-17 10-11-17 | [9 empty] | Resubmission for Code-B Approval | 2017-01-11 | 2017-10-11
42 Approval in Code-B 10 days 10-11-17 19-11-17 | [9 empty] | Approval in Code-B | 2017-10-11 | 19/11/2017
43 Resubmission for Code-A approval 20 days 20-11-17 09-12-17 | [9 empty] | Resubmission for Code-A approval | 20/11/2017 | 2017-09-12
44 Engineers review and Code-A approval 20 days 10-12-17 29-12-17 | [9 empty] | Engineers review and Code-A approval | 2017-10-12 | 29/12/2017
Civil Works 60 days 20-11-17 18-01-18 | [8 empty] | Civil works | 20/11/2017 | 18/01/2018
49 Completion of excavation 6 days 20-11-17 25-11-17 | [9 empty] | Completion of excavation | 20/11/2017 | 25/11/2017
50 Completion of RCC work upto Plinth for Blower | [9 empty] | Completion of RCC work upto Plinth for Blower Room | 22/11/2017 | 2017-10-12
Room
10 days 22-11-17 01-12-17
51 Grade Slab 10 days 01-12-17 10-12-17 | [9 empty] | Grade Slab | 2017-01-12 | 2017-10-12
52 Completion of RCC work Upto Top Slab 8 days 06-12-17 13-12-17 | [9 empty] | Completion of RCC work Upto Top Slab | 2017-06-12 | 31/12/2017
53 Completion of Top Slab 22 days 10-12-17 31-12-17 | [9 empty] | Completion of Top Slab | 2017-10-12 | 31/12/2017
54 Completion of Block Masonary 5 days 01-01-18 05-01-18 | [9 empty] | Completion of Block Masonary | 2018-01-01 | 2018-05-01
55 Completion of Finishing works 13 days 06-01-18 18-01-18 | [9 empty] | Completion of Finishing works | 2018-06-01 | 18/01/2018
56 TSPS & STP 802 days 20-09-17 30-11-19 | [7 empty] | TSPS & STP | 20/09/2017 | 30/11/2019 |  |  |  |  | 15/06/2018 | 2021-01-12
57 Basic Engineering Documentation 655 days 20-09-17 06-07-19 | [8 empty] | Basic Engineering Documentation | 20/09/2017 | 30/11/2019 |  |  |  | 15/06/2018 | 15/02/2020
58 PFD and Mass Balance 509 days 20-09-17 10-02-19 | [9 empty] | PFD and Mass Balance | 20/09/2017 | 2019-10-02 |  |  | 15/06/2018 | 15/12/2019
59 Preparation and Submission to Client 13 days 20-09-17 02-10-17
60 Engineer's Comments on 1st submission 15 days 04-10-17 18-10-17
61 Resubmission for Code-B Approval 6 days 19-10-17 24-10-17
62 Engineers review and Code-B approval 16 days 25-10-17 09-11-17
63 Resubmission for Code-A approval 15 days 01-01-19 15-01-19
64 Engineers review and Code-A approval 26 days 16-01-19 10-02-19
65 Hydraulic Calculation 458 days 10-11-17 10-02-19 | [9 empty] | Hydraulic Calculation | 2017-10-11 | 24/11/2017 |  |  | 20/08/2018 | 2019-01-11
66 Preparation and Submission to Client 15 days 10-11-17 24-11-17
67 Engineer's Comments on 1st submission 15 days 25-11-17 09-12-17
68 Resubmission for Code-B Approval 10 days 10-12-17 19-12-17
69 Engineers review and Code-B approval 31 days 20-12-17 19-01-18
70 Resubmission for Code-A approval 15 days 01-01-19 15-01-19
71 Engineers review and Code-A approval 26 days 16-01-19 10-02-19
72 Process Design Report 509 days 20-09-17 10-02-19 | [9 empty] | rocess Design Report | 20/09/2017 | 2019-10-02
73 Preparation and Submission to Client 13 days 20-09-17 02-10-17
74 Engineer's Comments on 1st submission 15 days 04-10-17 18-10-17
75 Resubmission for Code-B Approval 6 days 19-10-17 24-10-17
76 Engineers review and Code-B approval 16 days 25-10-17 09-11-17
77 Resubmission for Code-A approval 15 days 01-01-19 15-01-19
78 Engineers review and Code-A approval 26 days 16-01-19 10-02-19
79 P & ID 508 days 05-12-17 26-04-19 | [9 empty] | P & ID | 2017-05-12 | 26/04/2019
80 Preparation and Submission to Client 121 days 05-12-17 04-04-18
81 Engineer's Comments on 1st submission 141 days 06-12-17 25-04-18
82 Resubmission for Code-B Approval 122 days 30-12-17 30-04-18
83 Engineers review and Code-B approval 131 days 31-12-17 10-05-18
84 Resubmission for Code-A approval 30 days 01-03-19 30-03-19
85 Engineers review and Code-A approval 26 days 01-04-19 26-04-19
86 Piping and Valves Schedules 372 days 30-06-18 06-07-19 | [9 empty] | Piping and Valves Schedules | 30/06/2018 | 2018-12-07
87 Preparation and Submission to Client 13 days 30-06-18 12-07-18
88 Engineer's Comments on 1st submission 8 days 13-07-18 20-07-18
89 Resubmission for Code-B Approval 5 days 21-07-18 25-07-18
90 Engineers review and Code-B approval 15 days 26-07-18 09-08-18
91 Resubmission for Code-A approval 10 days 01-06-19 10-06-19
92 Engineers review and Code-A approval 26 days 11-06-19 06-07-19
93 E & I basic Package 286 days 15-07-18 26-04-19 | [8 empty] | E & I basic Package | 15/07/2018 | 26/04/2019
94 Electrical Load List 286 days 15-07-18 26-04-19 | [9 empty] | Electrical Load List | 15/07/2018 | 26/04/2019
95 Preparation and Submission to Client 13 days 15-07-18 27-07-18
96 Engineer's Comments on 1st submission 15 days 28-07-18 11-08-18
97 Resubmission for Code-B Approval 15 days 12-08-18 26-08-18
98 Engineers review and Code-B approval 15 days 27-08-18 10-09-18
99 Resubmission for Code-A approval 30 days 01-03-19 30-03-19
100 Engineers review and Code-A approval 26 days 01-04-19 26-04-19
101 Plant Operation and Control Philosophy 299 days 02-07-18 26-04-19 | [9 empty] | Plant Operation and Control Philosophy | 2018-02-07 | 26/04/2019
102 Preparation and Submission to Client 14 days 02-07-18 15-07-18
103 Engineer's Comments on 1st submission 20 days 16-07-18 04-08-18
104 Resubmission for Code-B Approval 5 days 05-08-18 09-08-18
105 Engineers review and Code-B approval 15 days 10-08-18 24-08-18
106 Resubmission for Code-A approval 30 days 01-03-19 30-03-19
107 Engineers review and Code-A approval 26 days 01-04-19 26-04-19
108 Vendor Credentials 242 days 01-11-17 30-06-18 | [9 empty] | Vendor Credentials | 2017-01-11 | 26/04/2019
109 Submission and Approval of Credentials -
Procurement of cement / steel / aggregates etc.
as applicable
61 days 01-11-17 31-12-17
110 Submission and Approval of Credentials -
Procurement of Mechanical / Electrical /
Instrumentation items as applicable
212 days 01-12-17 30-06-18
111 Detail Engineering 341 days 01-11-17 07-10-18 | [9 empty] | Detail Engineering | 2017-01-11 | 2018-07-10
112 Civil Drawings and Documents 341 days 01-11-17 07-10-18 | [10 empty] | Civil Drawings and Documents | 2017-01-11 | 2018-07-10
113 Civil Design Basis Report 341 days 01-11-17 07-10-18
114 Preparation and Submission to Client 8 days 01-11-17 08-11-17
115 Engineer's Comments on 1st submission 5 days 09-11-17 13-11-17
116 Resubmission for Code-B Approval 9 days 15-11-17 23-11-17
117 Engineers review and Code-B approval 11 days 24-11-17 04-12-17
118 Resubmission for Code-A approval 16 days 01-09-18 16-09-18
119 Engineers review and Code-A approval 21 days 17-09-18 07-10-18
120 Terminal Sewage Pumping station 692 days 24-12-17 15-11-19 | [9 empty] | Terminal Sewage Pumping station | 24/12/2017 | 15/11/2019
121 Mechanical GA Drawings 414 days 27-03-18 14-05-19 | [10 empty] | Mechanical GA Drawings | 27/03/2018 | 2018-05-04
122 Preparation and Submission to Client 10 days 27-03-18 05-04-18
123 Engineer's Comments on 1st submission 25 days 06-04-18 30-04-18
124 Resubmission for Code-B Approval 7 days 01-06-18 07-06-18
125 Engineers review and Code-B approval 11 days 08-06-18 18-06-18
126 Resubmission for Code-A approval 15 days 10-04-19 24-04-19
127 Engineers review and Code-A approval 20 days 25-04-19 14-05-19
128 Civil Design Drawings 383 days 01-07-18 18-07-19 | [10 empty] | Civil Design Drawings | 2018-01-07 | 18/07/2019
129 Preparation and Submission to Client 25 days 01-07-18 25-07-18
130 Engineer's Comments on 1st submission 12 days 26-07-18 06-08-18
131 Resubmission for Code-B Approval 12 days 07-08-18 18-08-18
132 Engineers review and Code-B approval 12 days 19-08-18 30-08-18
133 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
134 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
135 Procurement 584 days 24-12-17 30-07-19 | [10 empty] | Procurement | 24/12/2017 | 30/07/2019
136 Mechanical Medium Screen and Belt Conveyor 500 days 24-12-17 07-05-19 | [11 empty] | Mechanical Medium Screen and Belt Conveyo | 24/12/2017 | 2019-07-05
137 Placement of order 1 day 24-12-17 24-12-17
138 Submission of Datasheets / Drawings 10 days 01-02-18 10-02-18
139 Engineer's Comments on 1st submission 49 days 11-02-18 31-03-18
140 Resubmission 107 days 01-04-18 16-07-18
141 Engineers review and Code-A approval 28 days 17-07-18 13-08-18
142 Issue of manufacturing Clearance 3 days 14-08-18 16-08-18
143 Manufacturing 210 days 16-08-18 13-03-19
144 Inspection / Review of Test Certificates as
applicable
15 days 14-03-19 28-03-19
145 Painting and Packaging of Equipment 20 days 29-03-19 17-04-19
146 Despatch and receipt of Material at Site 20 days 18-04-19 07-05-19
150 Submersible Pumps 433 days 24-05-18 30-07-19 | [11 empty] | Submersible Pumps | 24/05/2018 | 30/07/2019
151 Placement of order 1 day 24-05-18 24-05-18
152 Submission of Datasheets / Drawings 12 days 06-07-18 17-07-18
153 Engineer's Comments on 1st submission 28 days 18-07-18 14-08-18
154 Resubmission 15 days 15-08-18 29-08-18
155 Engineers review and Code-A approval 28 days 30-08-18 26-09-18
156 Issue of manufacturing Clearance 3 days 27-09-18 29-09-18
157 Manufacturing 240 days 30-09-18 27-05-19
158 Inspection / Review of Test Certificates as
applicable
15 days 28-05-19 11-06-19
159 Painting and Packaging of Equipment 20 days 12-06-19 01-07-19
160 Despatch and receipt of Material at Site 30 days 01-07-19 30-07-19
161 Civil Works for TSPS 360 days 25-08-18 19-08-19 | [10 empty] | Civil Works for TSPS | 25/08/2018 | 19/08/2019
162 Completion of excavation 30 days 25-08-18 23-09-18
163 Completion of PCC 25 days 24-09-18 18-10-18
164 Completion of Raft 45 days 15-10-18 28-11-18
165 Completion of 50% side wall 80 days 20-11-18 07-02-19
166 Completion of 100% side wall 80 days 15-01-19 04-04-19
167 Completion of hydrotest 28 days 01-06-19 28-06-19
168 Completion of Plinth level slab 30 days 01-04-19 30-04-19
169 Completion of Col/Beam upto top slab 10 days 01-05-19 10-05-19
170 Completion of Top Slab 30 days 11-05-19 09-06-19
171 Completion of Block Masonary 25 days 10-06-19 04-07-19
172 Completion of Water proofing 25 days 20-06-19 14-07-19
173 Completion of Finishing works 50 days 01-07-19 19-08-19
174 Erection 107 days 01-08-19 15-11-19 | [10 empty] | Erection | 2019-01-08 | 15/11/2019
175 Erection of Mechanical and Piping
Equipments
60 days 01-08-19 29-09-19
176 Erection of Electrical & Instrumentation
Equipments
42 days 20-09-19 31-10-19
177 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
15 days 01-11-19 15-11-19
178 Inlet Chamber, Screen Channel, Grit Chamber and | [9 empty] | Inlet Chamber, Screen Channel, Grit Chamber and Parshall Flume | 24/12/2017 | 15/11/2019
Parshall Flume
692 days 24-12-17 15-11-19
179 Mechanical GA Drawings 368 days 24-05-18 26-05-19 | [10 empty] | Mechanical GA Drawings | 24/05/2018 | 2018-10-06
180 Preparation and Submission to Client 18 days 24-05-18 10-06-18
181 Engineer's Comments on 1st submission 28 days 11-06-18 08-07-18
182 Resubmission for Code-B Approval 10 days 09-07-18 18-07-18
183 Engineers review and Code-B approval 28 days 19-07-18 15-08-18
184 Resubmission for Code-A approval 28 days 01-04-19 28-04-19
185 Engineers review and Code-A approval 28 days 29-04-19 26-05-19
186 Civil Design Drawings 351 days 10-08-18 26-07-19 | [10 empty] | Civil Design Drawings | 2018-10-08 | 29/08/2018
187 Preparation and Submission to Client 20 days 10-08-18 29-08-18
188 Engineer's Comments on 1st submission 28 days 30-08-18 26-09-18
189 Resubmission for Code-B Approval 10 days 27-09-18 06-10-18
190 Engineers review and Code-B approval 28 days 07-10-18 03-11-18
191 Resubmission for Code-A approval 28 days 01-06-19 28-06-19
192 Engineers review and Code-A approval 28 days 29-06-19 26-07-19
197 Procurement 500 days 24-12-17 07-05-19 | [10 empty] | Procurement | 24/12/2017 | 2019-07-05
198 Mechanical Belt Conveyor 500 days 24-12-17 07-05-19 | [11 empty] | Mechanical Belt Conveyor | 24/12/2017 | 2019-07-05
199 Placement of order 1 day 24-12-17 24-12-17
200 Submission of Datasheets / Drawings 10 days 01-02-18 10-02-18
201 Engineer's Comments on 1st submission 49 days 11-02-18 31-03-18
202 Resubmission 147 days 01-04-18 25-08-18
203 Engineers review and Code-A approval 28 days 26-08-18 22-09-18
204 Issue of manufacturing Clearance 3 days 23-09-18 25-09-18
205 Manufacturing 169 days 26-09-18 13-03-19
206 Inspection / Review of Test Certificates as
applicable
15 days 14-03-19 28-03-19
207 Painting and Packaging of Equipment 20 days 29-03-19 17-04-19
208 Despatch and receipt of Material at Site 20 days 18-04-19 07-05-19
209 Mechanical Vortex type Grit Mechanism | [11 empty] | Mechanical Vortex type Grit Mechanism | 16/01/2018 | 23/03/2019
including Turbo Grit Pumps
432 days 16-01-18 23-03-19
210 Placement of order 1 day 16-01-18 16-01-18
211 Submission of Datasheets / Drawings 20 days 17-06-18 06-07-18
212 Engineer's Comments on 1st submission 12 days 07-07-18 18-07-18
213 Resubmission 12 days 19-07-18 30-07-18
214 Engineers review and Code-A approval 12 days 31-07-18 11-08-18
215 Issue of manufacturing Clearance 4 days 12-08-18 15-08-18
216 Manufacturing 220 days 16-08-18 23-03-19
217 Inspection / Review of Test Certificates as
applicable
20 days 24-03-18 12-04-18
218 Painting and Packaging of Equipment 30 days 13-04-18 12-05-18
219 Despatch and receipt of Material at Site 60 days 13-05-18 11-07-18
220 Civil Works for Mechanical Screen Inlet | [10 empty] | Civil Works for Mechanical Screen Inlet Channel and Distribution Chamber | 2018-01-11 | 15/11/2019
Channel and Distribution Chamber
380 days 01-11-18 15-11-19
221 Completion of excavation 18 days 01-11-18 18-11-18
222 Completion of PCC 15 days 19-11-18 03-12-18
223 Completion of Raft 80 days 04-12-18 21-02-19
224 Completion of 50% side wall 90 days 04-01-19 03-04-19
225 Completion of 100% side wall 90 days 04-02-19 04-05-19
226 Completion of hydrotest 30 days 05-05-19 03-06-19
227 Completion of Finishing works 40 days 04-06-19 13-07-19
228 Erection 107 days 01-08-19 15-11-19
229 Erection of Mechanical and Piping
Equipments
60 days 01-08-19 29-09-19
230 Erection of Electrical & Instrumentation
Equipments
42 days 20-09-19 31-10-19
231 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
15 days 01-11-19 15-11-19
232 Primary Clarifier 585 days 15-11-17 22-06-19 | [9 empty] | Primary Clarifier | 15/11/2017 | 22/06/2019
233 Mechanical GA Drawings 515 days 20-12-17 18-05-19 | [10 empty] | Mechanical GA Drawings | 20/12/2017 | 18/05/2019
234 Preparation and Submission to Client 10 days 20-12-17 29-12-17
235 Engineer's Comments on 1st submission 8 days 30-12-17 06-01-18
236 Resubmission for Code-B Approval 16 days 07-01-18 22-01-18
237 Engineers review and Code-B approval 8 days 23-01-18 30-01-18
238 Resubmission for Code-A approval 20 days 01-04-19 20-04-19
239 Engineers review and Code-A approval 28 days 21-04-19 18-05-19
242 Civil Design Drawings 529 days 10-01-18 22-06-19 | [10 empty] | Civil Design Drawings | 2018-10-01 | 21/01/2018
243 Preparation and Submission to Client 12 days 10-01-18 21-01-18
244 Engineer's Comments on 1st submission 10 days 22-01-18 31-01-18
245 Resubmission for Code-B Approval 130 days 01-02-18 10-06-18
246 Engineers review and Code-B approval 143 days 08-02-18 30-06-18
247 Resubmission for Code-A approval 25 days 01-05-19 25-05-19
248 Engineers review and Code-A approval 28 days 26-05-19 22-06-19
249 Procurement 493 days 15-11-17 22-03-19 | [10 empty] | Procuremen | 15/11/2017 | 22/03/2019
250 Clarifier Mechanism 493 days 15-11-17 22-03-19 | [11 empty] | Clarifier Mechanism | 15/11/2017 | 22/03/2019
251 Placement of order 1 day 15-11-17 15-11-17
252 Submission of Datasheets / Drawings 25 days 29-11-17 23-12-17
253 Engineer's Comments on 1st submission 19 days 24-12-17 11-01-18
254 Resubmission 160 days 12-01-18 20-06-18
255 Engineers review and Code-A approval 28 days 21-06-18 18-07-18
256 Issue of manufacturing Clearance 3 days 19-07-18 21-07-18
257 Manufacturing 180 days 22-07-18 17-01-19
258 Inspection / Review of Test Certificates as
applicable
15 days 18-01-19 01-02-19
259 Painting and Packaging of Equipment 20 days 01-02-19 20-02-19
260 Despatch and receipt of Material at Site 30 days 21-02-19 22-03-19
261 Civil Works for Primary Clarifiers 548 days 01-04-18 30-09-19 | [9 empty] | Civil Works for Primary Clarifiers | 2018-01-04 | 30/09/2019
262 Completion of excavation 32 days 01-04-18 02-05-18 | [10 empty] | Completion of excavation | 2018-01-04 | 2018-02-05
263 Completion of PCC 50 days 25-04-18 13-06-18 | [10 empty] | Completion of PCC | 25/04/2018 | 13/06/2018
264 Completion of Raft 131 days 01-05-18 08-09-18 | [10 empty] | Completion of Raft | 2018-01-05 | 2018-08-09
265 Completion of 50% side wall 120 days 15-07-18 11-11-18 | [10 empty] | Completion of 50% side wall | 15/07/2018 | 2018-11-11
266 Completion of 100% side wall 120 days 15-09-18 12-01-19 | [10 empty] | Completion of 100% side wall | 15/09/2018 | 2019-12-01
267 Completion of hydrotest 150 days 01-11-18 30-03-19 | [10 empty] | Completion of hydrotest | 2018-01-11 | 30/03/2019
268 Completion of Finishing works 90 days 01-01-19 31-03-19 | [10 empty] | Completion of Finishing works | 2019-01-01 | 31/03/2019
269 Erection 153 days 01-05-19 30-09-19 | [10 empty] | Erection | 2019-01-05 | 30/09/2019
270 Erection of Mechanical and Piping
Equipments
100 days 01-05-19 08-08-19
271 Erection of Electrical & Instrumentation
Equipments
30 days 01-08-19 30-08-19
272 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
30 days 01-09-19 30-09-19
273 Sequential Batch Reactor 733 days 28-11-17 30-11-19 | [9 empty] | Sequential Batch Reacto | 28/11/2017 | 30/11/2019
274 Mechanical GA Drawings 480 days 23-03-18 15-07-19 | [10 empty] | Mechanical GA Drawing | 23/03/2018 | 15/07/2019
275 Preparation and Submission to Client 15 days 23-03-18 06-04-18
276 Engineer's Comments on 1st submission 28 days 07-04-18 04-05-18
277 Resubmission for Code-B Approval 6 days 05-05-18 10-05-18
278 Engineers review and Code-B approval 12 days 11-05-18 22-05-18
279 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
280 Engineers review and Code-A approval 25 days 21-06-19 15-07-19
281 Civil Design Drawings 457 days 01-07-18 30-09-19 | [10 empty] | Civil Design Drawings | 2018-01-07 | 30/09/2019
282 Preparation and Submission to Client 22 days 01-07-18 22-07-18
283 Engineer's Comments on 1st submission 12 days 23-07-18 03-08-18
284 Resubmission for Code-B Approval 12 days 04-08-18 15-08-18
285 Engineers review and Code-B approval 12 days 16-08-18 27-08-18
286 Resubmission for Code-A approval 30 days 01-08-19 30-08-19
287 Engineers review and Code-A approval 30 days 01-09-19 30-09-19
291 Procurement 610 days 28-11-17 30-07-19 | [10 empty] | Procurement | 28/11/2017 | 30/07/2019
292 Diffuser System including Piping 556 days 28-11-17 06-06-19 | [11 empty] | Diffuser System including Piping | 29/11/2017 | 2019-06-06
293 Placement of order 1 day 28-11-17 28-11-17
294 Submission of Datasheets / Drawings 25 days 24-01-18 17-02-18
295 Engineer's Comments on 1st submission 122 days 18-02-18 19-06-18
296 Resubmission 20 days 20-06-18 09-07-18
297 Engineers review and Code-A approval 28 days 10-07-18 06-08-18
298 Issue of manufacturing Clearance 4 days 07-08-18 10-08-18
299 Manufacturing 180 days 11-08-18 06-02-19
300 Inspection / Review of Test Certificates as
applicable
30 days 09-03-19 07-04-19
301 Painting and Packaging of Equipment 30 days 08-04-19 07-05-19
302 Despatch and receipt of Material at Site 30 days 08-05-19 06-06-19
303 Decanter 457 days 28-11-17 27-02-19 | [11 empty] | Decanter | 28/11/2017 | 27/02/2019
304 Placement of order 1 day 28-11-17 28-11-17
305 Submission of Datasheets / Drawings 25 days 29-11-17 23-12-17
306 Engineer's Comments on 1st submission 53 days 24-12-17 14-02-18
307 Resubmission 19 days 15-02-18 05-03-18
308 Engineers review and Code-A approval 126 days 06-03-18 09-07-18
309 Issue of manufacturing Clearance 3 days 10-07-18 12-07-18
310 Manufacturing 130 days 13-07-18 19-11-18
311 Inspection / Review of Test Certificates as
applicable
20 days 20-11-18 09-12-18
312 Painting and Packaging of Equipment 20 days 10-12-18 29-12-18
313 Despatch and receipt of Material at Site 60 days 30-12-18 27-02-19
314 Pumps 433 days 24-05-18 30-07-19 | [11 empty] | Pumps | 24/05/2018 | 30/07/2019
315 Placement of order 1 day 24-05-18 24-05-18
316 Submission of Datasheets / Drawings 12 days 06-07-18 17-07-18
317 Engineer's Comments on 1st submission 28 days 18-07-18 14-08-18
318 Resubmission 15 days 15-08-18 29-08-18
319 Engineers review and Code-A approval 28 days 30-08-18 26-09-18
320 Issue of manufacturing Clearance 3 days 27-09-18 29-09-18
321 Manufacturing 240 days 30-09-18 27-05-19
322 Inspection / Review of Test Certificates as
applicable
15 days 28-05-19 11-06-19
323 Painting and Packaging of Equipment 20 days 12-06-19 01-07-19
324 Despatch and receipt of Material at Site 30 days 01-07-19 30-07-19
325 Alum Dispersion Mixer 503 days 15-12-17 01-05-19 | [11 empty] | Alum Dispersion Mixer | 15/12/2017 | 2019-01-05
326 Placement of order 1 day 15-12-17 15-12-17
327 Submission of Datasheets / Drawings 18 days 29-05-18 15-06-18
328 Engineer's Comments on 1st submission 28 days 16-06-18 13-07-18
329 Resubmission 25 days 14-07-18 07-08-18
330 Engineers review and Code-A approval 28 days 08-08-18 04-09-18
331 Issue of manufacturing Clearance 4 days 05-09-18 08-09-18
332 Manufacturing 180 days 09-09-18 07-03-19
333 Inspection / Review of Test Certificates as
applicable
15 days 08-03-19 22-03-19
334 Painting and Packaging of Equipment 10 days 23-03-19 01-04-19
335 Despatch and receipt of Material at Site 30 days 02-04-19 01-05-19
337 Civil Works for Sequential Batch Reactor 487 days 01-08-18 30-11-19 | [11 empty] | Civil Works for Sequential Batch Reacto | 2018-01-08 | 30/11/2019
338 Completion of excavation 30 days 01-08-18 30-08-18
339 Completion of PCC 30 days 01-09-18 30-09-18
340 Completion of Raft 90 days 20-09-18 18-12-18
341 Completion of 50% side wall 120 days 15-11-18 14-03-19
342 Completion of 100% side wall 120 days 15-01-19 14-05-19
343 Completion of hydrotest 90 days 15-04-19 13-07-19
344 Completion of Finishing works 120 days 15-05-19 11-09-19
345 Erection 121 days 02-08-19 30-11-19
346 Erection of Mechanical and Piping
Equipments
91 days 02-08-19 31-10-19
347 Erection of Electrical & Instrumentation
Equipments
60 days 17-09-19 15-11-19
348 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
15 days 16-11-19 30-11-19
349 Chlorine Contact Tank /Plant Water Sump 695 days 05-12-17 30-10-19 | [9 empty] | Chlorine Contact Tank /Plant Water Sump | 2017-05-12 | 30/10/2019
350 Mechanical GA Drawings 530 days 05-12-17 18-05-19 | [10 empty] | Mechanical GA Drawings | 2017-05-12 | 18/05/2019
351 Preparation and Submission to Client 17 days 05-12-17 21-12-17
352 Engineer's Comments on 1st submission 14 days 22-12-17 04-01-18
353 Resubmission for Code-B Approval 4 days 05-01-18 08-01-18
354 Engineers review and Code-B approval 11 days 09-01-18 19-01-18
355 Resubmission for Code-A approval 20 days 01-04-19 20-04-19
356 Engineers review and Code-A approval 28 days 21-04-19 18-05-19
357 Civil Design Drawings 538 days 10-01-18 01-07-19 | [10 empty] | Civil Design Drawings | 2018-10-01 | 2019-01-07
358 Preparation and Submission to Client 11 days 10-01-18 20-01-18
359 Engineer's Comments on 1st submission 14 days 21-01-18 03-02-18
360 Resubmission for Code-B Approval 10 days 04-02-18 13-02-18
361 Engineers review and Code-B approval 13 days 14-02-18 26-02-18
362 Resubmission for Code-A approval 20 days 15-05-19 03-06-19
363 Engineers review and Code-A approval 28 days 04-06-19 01-07-19
364 Procurement 433 days 24-05-18 30-07-19 | [10 empty] | Procurement | 24/05/2018 | 30/07/2019
365 Plant water pumps with motor 433 days 24-05-18 30-07-19 | [11 empty] | Plant water pumps with motor | 24/05/2018 | 30/07/2019
366 Placement of order 1 day 24-05-18 24-05-18
367 Submission of Datasheets / Drawings 12 days 06-07-18 17-07-18
368 Engineer's Comments on 1st submission 28 days 18-07-18 14-08-18
369 Resubmission 15 days 15-08-18 29-08-18
370 Engineers review and Code-A approval 28 days 30-08-18 26-09-18
371 Issue of manufacturing Clearance 3 days 27-09-18 29-09-18
372 Manufacturing 240 days 30-09-18 27-05-19
373 Inspection / Review of Test Certificates as
applicable
15 days 28-05-19 11-06-19
374 Painting and Packaging of Equipment 20 days 12-06-19 01-07-19
375 Despatch and receipt of Material at Site 30 days 01-07-19 30-07-19
376 Civil Works 637 days 01-02-18 30-10-19 | [10 empty] | Civil Works | 2018-01-02 | 30/10/2019
377 Completion of excavation 26 days 01-02-18 26-02-18
378 Completion of PCC 15 days 27-02-18 13-03-18
379 Completion of Raft 109 days 14-03-18 30-06-18
380 Completion of 50 % side wall 60 days 01-07-18 29-08-18
381 Completion of 100% side wall 70 days 30-08-18 07-11-18
382 Completion of hydrotest 40 days 08-11-18 17-12-18
383 Completion of Finishing works 60 days 18-12-18 15-02-19
386 Erection 91 days 01-08-19 30-10-19 | [10 empty] | Erection | 2019-01-08 | 30/10/2019
387 Erection of Mechanical and Piping
Equipments
30 days 01-08-19 30-08-19
388 Erection of Electrical & Instrumentation
Equipments
30 days 01-09-19 30-09-19
389 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
30 days 01-10-19 30-10-19
390 Disc Filter 669 days 16-01-18 15-11-19 | [9 empty] | Disc Filter | 16/01/2018 | 15/11/2019
391 Mechanical GA Drawings 463 days 12-05-18 17-08-19 | [10 empty] | Mechanical GA Drawings | 2018-12-05 | 26/05/2018
392 Preparation and Submission to Client 15 days 12-05-18 26-05-18
393 Engineer's Comments on 1st submission 5 days 27-05-18 31-05-18
394 Resubmission for Code-B Approval 5 days 01-06-18 05-06-18
395 Engineers review and Code-B approval 18 days 06-06-18 23-06-18
396 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
397 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
398 Civil Design Drawings 439 days 01-08-18 13-10-19 | [10 empty] | Civil Design Drawings | 2018-01-08 | 25/08/2018
399 Preparation and Submission to Client 25 days 01-08-18 25-08-18
400 Engineer's Comments on 1st submission 28 days 26-08-18 22-09-18
401 Resubmission for Code-B Approval 10 days 23-09-18 02-10-18
402 Engineers review and Code-B approval 28 days 03-10-18 30-10-18
403 Resubmission for Code-A approval 30 days 15-08-19 13-09-19
404 Engineers review and Code-A approval 30 days 14-09-19 13-10-19
405 Procurement 572 days 16-01-18 10-08-19 | [10 empty] | Procurement | 16/01/2018 | 2019-10-08
406 Disc Cloth Filter 572 days 16-01-18 10-08-19
407 Placement of order 1 day 16-01-18 16-01-18
408 Submission of Datasheets / Drawings 20 days 27-06-18 16-07-18
409 Engineer's Comments on 1st submission 12 days 17-07-18 28-07-18
410 Resubmission 12 days 29-07-18 09-08-18
411 Engineers review and Code-A approval 12 days 10-08-18 21-08-18
412 Issue of manufacturing Clearance 4 days 22-08-18 25-08-18
413 Manufacturing 240 days 26-08-18 22-04-19
414 Inspection / Review of Test Certificates as
applicable
20 days 23-04-19 12-05-19
415 Painting and Packaging of Equipment 30 days 13-05-19 11-06-19
416 Despatch and receipt of Material at Site 60 days 12-06-19 10-08-19
417 Civil Works 242 days 15-10-18 13-06-19 | [10 empty] | civil works | 15/10/2018 | 24/10/2018
418 Completion of excavation 10 days 15-10-18 24-10-18
419 Completion of PCC 5 days 25-10-18 29-10-18
420 Completion of Raft 30 days 30-10-18 28-11-18
421 Completion of 50 % side wall 60 days 29-11-18 27-01-19
422 Completion of 100% side wall 70 days 28-01-19 07-04-19
423 Completion of hydrotest 27 days 08-04-19 04-05-19
424 Completion of Finishing works 40 days 05-05-19 13-06-19
425
426 Erection 107 days 01-08-19 15-11-19 | [10 empty] | erection | 2019-01-08 | 15/11/2019
427 Erection of Mechanical and Piping Equipments 61 days 01-08-19 30-09-19
428 Erection of Electrical & Instrumentation
Equipments
31 days 01-10-19 31-10-19
429 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
15 days 01-11-19 15-11-19
435 COTDM UNIT 696 days 20-12-17 15-11-19 | [9 empty] | COTDM UNIT | 20/12/2017 | 15/11/2019
436 Mechanical GA Drawings 422 days 28-05-18 23-07-19 | [10 empty] | Mechanical GA Drawings | 28/05/2018 | 2018-11-06
437 Preparation and Submission to Client 15 days 28-05-18 11-06-18
438 Engineer's Comments on 1st submission 5 days 12-06-18 16-06-18
439 Resubmission for Code-B Approval 5 days 17-06-18 21-06-18
440 Engineers review and Code-B approval 14 days 22-06-18 05-07-18
441 Resubmission for Code-A approval 25 days 01-06-19 25-06-19
442 Engineers review and Code-A approval 28 days 26-06-19 23-07-19
443 Civil Design Drawings 399 days 15-08-18 17-09-19 | [10 empty] | Civil Design Drawings | 15/08/2018 | 17/09/2019
444 Preparation and Submission to Client 22 days 15-08-18 05-09-18
445 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
446 Resubmission for Code-B Approval 12 days 04-10-18 15-10-18
447 Engineers review and Code-B approval 28 days 16-10-18 12-11-18
448 Resubmission for Code-A approval 30 days 20-07-19 18-08-19
449 Engineers review and Code-A approval 30 days 19-08-19 17-09-19
450 Procurement 636 days 20-12-17 16-09-19 | [10 empty] | Procurement | 20/12/2017 | 16/09/2019
451 COTDM Unit 636 days 20-12-17 16-09-19 | [11 empty] | COTDM Unit | 20/12/2017 | 16/09/2019
452 Placement of order 1 day 20-12-17 20-12-17
453 Submission of Datasheets / Drawings 20 days 09-06-18 28-06-18
454 Engineer's Comments on 1st submission 28 days 29-06-18 26-07-18
455 Resubmission 20 days 27-07-18 15-08-18
456 Engineers review and Code-A approval 28 days 16-08-18 12-09-18
457 Issue of manufacturing Clearance 4 days 13-09-18 16-09-18
458 Manufacturing 210 days 17-09-18 14-04-19
459 Inspection / Review of Test Certificates as
applicable
35 days 15-04-19 19-05-19
460 Painting and Packaging of Equipment 30 days 20-05-19 18-06-19
461 Despatch and receipt of Material at Site 60 days 19-07-19 16-09-19
462 Poly Dosing Agitator 430 days 08-06-18 11-08-19 | [11 empty] | Poly Dosing Agitator | 2018-08-06 | 2019-11-08
463 Placement of order 1 day 08-06-18 08-06-18
464 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
465 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
466 Resubmission 20 days 04-10-18 23-10-18
467 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
468 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
469 Manufacturing 180 days 25-11-18 23-05-19
470 Inspection / Review of Test Certificates as
applicable
30 days 24-05-19 22-06-19
471 Painting and Packaging of Equipment 30 days 23-06-19 22-07-19
472 Despatch and receipt of Material at Site 20 days 23-07-19 11-08-19
473 Poly Dosing Pumps 461 days 08-06-18 11-09-19 | [11 empty] | Poly Dosing pump | 2018-08-06 | 2019-11-09
474 Placement of order 1 day 08-06-18 08-06-18
475 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
476 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
477 Resubmission 20 days 04-10-18 23-10-18
478 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
479 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
480 Manufacturing 210 days 25-11-18 22-06-19
481 Inspection / Review of Test Certificates as
applicable
30 days 24-06-19 23-07-19
482 Painting and Packaging of Equipment 30 days 24-07-19 22-08-19
483 Despatch and receipt of Material at Site 20 days 23-08-19 11-09-19
486 COTDM Feed Pumps 436 days 30-06-18 08-09-19 | [11 empty] | COTDM Feed Pumps | 30/06/2018 | 2019-08-09
487 Placement of order 1 day 30-06-18 30-06-18
488 Submission of Datasheets / Drawings 25 days 04-10-18 28-10-18
489 Engineer's Comments on 1st submission 28 days 29-10-18 25-11-18
490 Resubmission 20 days 26-11-18 15-12-18
491 Engineers review and Code-A approval 28 days 16-12-18 12-01-19
492 Issue of manufacturing Clearance 4 days 13-01-19 16-01-19
493 Manufacturing 180 days 17-01-19 15-07-19
494 Inspection / Review of Test Certificates as
applicable
20 days 16-07-19 04-08-19
495 Painting and Packaging of Equipment 15 days 05-08-19 19-08-19
496 Despatch and receipt of Material at Site 20 days 20-08-19 08-09-19
497 Sludge Conveyor 439 days 30-06-18 11-09-19 | [11 empty] | Sludge Conveyor | 30/06/2018 | 2019-11-09
498 Placement of order 1 day 30-06-18 30-06-18
499 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
500 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
501 Resubmission 20 days 04-10-18 23-10-18
502 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
503 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
504 Manufacturing 210 days 25-11-18 22-06-19
505 Inspection / Review of Test Certificates as
applicable
30 days 24-06-19 23-07-19
506 Painting and Packaging of Equipment 30 days 24-07-19 22-08-19
507 Despatch and receipt of Material at Site 20 days 23-08-19 11-09-19
508 Dewatered Sludge Cake Hopper System 439 days 30-06-18 11-09-19 | [11 empty] | Dewatered Sludge Cake Hopper System | 30/06/2018 | 2019-11-09
509 Placement of order 1 day 30-06-18 30-06-18
510 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
511 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
512 Resubmission 20 days 04-10-18 23-10-18
513 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
514 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
515 Manufacturing 210 days 25-11-18 22-06-19
516 Inspection / Review of Test Certificates as
applicable
30 days 24-06-19 23-07-19
517 Painting and Packaging of Equipment 30 days 24-07-19 22-08-19
518 Despatch and receipt of Material at Site 20 days 23-08-19 11-09-19
519 Civil Works 263 days 20-11-18 09-08-19 | [10 empty] | Civil Wroks | 20/11/2018 | 2019-09-08
520 Completion of excavation 10 days 20-11-18 29-11-18
521 Completion of PCC 10 days 30-11-18 09-12-18
522 Completion of Raft 25 days 10-12-18 03-01-19
523 Completion of 50% side wall 30 days 04-01-19 02-02-19
524 Completion of 100% side wall 30 days 03-02-19 04-03-19
525 Completion of RCC work upto Plinth for Pump
House
20 days 05-03-19 24-03-19
526 Grade Slab 10 days 25-03-19 03-04-19
527 Completion of RCC work Upto Top Slab 15 days 04-04-19 18-04-19
528 Completion of Top Slab 30 days 19-04-19 18-05-19
529 Completion of Block Masonary 40 days 19-05-19 27-06-19
530 Completion of Water proofing 20 days 30-05-19 18-06-19
531 Completion of Finishing works 40 days 01-07-19 09-08-19
536 Erection 107 days 01-08-19 15-11-19 | [10 empty] | Erection | 2019-01-08 | 15/11/2019
537 Erection of Mechanical and Piping Equipments 80 days 01-08-19 19-10-19
538 Erection of Electrical & Instrumentation
Equipments
31 days 01-10-19 31-10-19
539 Site Acceptance test for Mechanical / Piping /
Electrical / instrumentation Equipments (Dry /
Wet) as applicable
15 days 01-11-19 15-11-19
540 Process Air Blower Buildings/Store Room/MCC | [9 empty] | Process Air Blower Buildings/Store Room/MCC Room | 15/01/2018 | 31/10/2019
Room
655 days 15-01-18 31-10-19
541 Mechanical GA Drawings 409 days 12-06-18 25-07-19 | [10 empty] | Mechanical GA Drawings | 2018-12-06 | 30/06/2018
542 Preparation and Submission to Client 19 days 12-06-18 30-06-18
543 Engineer's Comments on 1st submission 28 days 01-07-18 28-07-18
544 Resubmission for Code-B Approval 6 days 29-07-18 03-08-18
545 Engineers review and Code-B approval 28 days 04-08-18 31-08-18
546 Resubmission for Code-A approval 25 days 01-06-19 25-06-19
547 Engineers review and Code-A approval 30 days 26-06-19 25-07-19
548 Civil Design Drawings 386 days 23-08-18 12-09-19 | [10 empty] | Civil Design drawings | 23/08/2018 | 2019-12-09
549 Preparation and Submission to Client 25 days 23-08-18 16-09-18
550 Engineer's Comments on 1st submission 28 days 17-09-18 14-10-18
551 Resubmission for Code-B Approval 15 days 15-10-18 29-10-18
552 Engineers review and Code-B approval 28 days 30-10-18 26-11-18
553 Resubmission for Code-A approval 30 days 15-07-19 13-08-19
554 Engineers review and Code-A approval 30 days 14-08-19 12-09-19
555 Procurement 517 days 15-01-18 15-06-19 | [10 empty] | Procuremenst | 15/01/2018 | 15/06/2019
556 Turbo Air Blowers 517 days 15-01-18 15-06-19 | [11 empty] | Turbo Air Blowers | 15/01/2018 | 15/06/2019
557 Placement of order 1 day 15-01-18 15-01-18
558 Submission of Datasheets / Drawings 20 days 11-06-18 30-06-18
559 Engineer's Comments on 1st submission 28 days 01-07-18 28-07-18
560 Resubmission 15 days 29-07-18 12-08-18
561 Engineers review and Code-A approval 28 days 13-08-18 09-09-18
562 Issue of manufacturing Clearance 4 days 10-09-18 13-09-18
563 Manufacturing 180 days 14-09-18 12-03-19
564 Inspection / Review of Test Certificates as
applicable
10 days 13-03-19 22-03-19
565 Painting and Packaging of Equipment 25 days 23-03-19 16-04-19
566 Despatch and receipt of Material at Site 60 days 17-04-19 15-06-19
567 Motors for Air Blowers 517 days 15-01-18 15-06-19 | [11 empty] | Motors for Air Blowers | 15/01/2018 | 15/06/2019
568 Placement of order 1 day 15-01-18 15-01-18
569 Submission of Datasheets / Drawings 20 days 11-06-18 30-06-18
570 Engineer's Comments on 1st submission 28 days 01-07-18 28-07-18
571 Resubmission 15 days 29-07-18 12-08-18
572 Engineers review and Code-A approval 28 days 13-08-18 09-09-18
573 Issue of manufacturing Clearance 4 days 10-09-18 13-09-18
574 Manufacturing 180 days 14-09-18 12-03-19
575 Inspection / Review of Test Certificates as
applicable
10 days 13-03-19 22-03-19
576 Painting and Packaging of Equipment 25 days 23-03-19 16-04-19
577 Despatch and receipt of Material at Site 60 days 17-04-19 15-06-19
578 Civil Works 232 days 15-11-18 04-07-19 | [10 empty] | Civil works | 15/11/2018 | 2019-04-07
579 Completion of excavation 12 days 15-11-18 26-11-18
580 Completion of RCC work upto Plinth for Blower
Room
25 days 27-11-18 21-12-18
581 Grade Slab 25 days 22-12-18 15-01-19
582 Completion of RCC work Upto Top Slab 25 days 16-01-19 09-02-19
583 Completion of Top Slab 40 days 10-02-19 21-03-19
584 Completion of Block Masonary 45 days 22-03-19 05-05-19
585 Completion of Water proofing 30 days 01-04-19 30-04-19
586 Completion of Finishing works 60 days 06-05-19 04-07-19
587 Erection 365 days 01-11-18 31-10-19 | [10 empty] | erection | 2018-01-11 | 31/10/2019
588 Erection of Mechanical and Piping Equipments 62 days 01-07-19 31-08-19
589 Erection of Electrical & Instrumentation
Equipments
78 days 15-08-19 31-10-19
590 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
15 days 01-11-18 15-11-18
591 Chemical Building/ Chlorination House / Scrubber Area 685 days 15-12-17 30-10-19 | [9 empty] | Chemical Building/ Chlorination House / Scrubber Area | 15/12/2017 | 30/10/2019
592 Mechanical GA Drawings 404 days 15-05-18 22-06-19 | [10 empty] | Mechanical GA Drawings | 15/05/2018 | 22/06/2018
593 Preparation and Submission to Client 15 days 15-05-18 29-05-18
594 Engineer's Comments on 1st submission 28 days 30-05-18 26-06-18
595 Resubmission for Code-B Approval 20 days 27-06-18 16-07-18
596 Engineers review and Code-B approval 28 days 17-07-18 13-08-18
597 Resubmission for Code-A approval 25 days 01-05-19 25-05-19
598 Engineers review and Code-A approval 28 days 26-05-19 22-06-19
599 Civil Design Drawings 352 days 01-09-18 18-08-19 | [10 empty] | Civil Design Drawings | 2018-01-09 | 18/08/2019
600 Preparation and Submission to Client 22 days 01-09-18 22-09-18
601 Engineer's Comments on 1st submission 12 days 23-09-18 04-10-18
602 Resubmission for Code-B Approval 28 days 05-10-18 01-11-18
603 Engineers review and Code-B approval 12 days 02-11-18 13-11-18
604 Resubmission for Code-A approval 30 days 20-06-19 19-07-19
605 Engineers review and Code-A approval 30 days 20-07-19 18-08-19
606 Procurement 636 days 15-12-17 11-09-19 | [10 empty] | Procurement | 15/12/2017 | 2019-11-09
607 Alum Dosing Pump with Motors 461 days 08-06-18 11-09-19 | [11 empty] | Alum Dosing Pump with Motors | 2018-08-06 | 2019-11-09
608 Placement of order 1 day 08-06-18 08-06-18
609 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
610 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
611 Resubmission 20 days 04-10-18 23-10-18
612 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
613 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
614 Manufacturing 210 days 25-11-18 22-06-19
615 Inspection 30 days 24-06-19 23-07-19
616 Painting and Packaging of Equipment 30 days 24-07-19 22-08-19
617 Despatch and receipt of Material at Site 20 days 23-08-19 11-09-19
618 Alum Dosing Tank Agitators with Motors 430 days 08-06-18 11-08-19 | [11 empty] | Alum Dosing Tank Agitators with Motors | 2018-08-06 | 2019-11-08
619 Placement of order 1 day 08-06-18 08-06-18
620 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
621 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
622 Resubmission 20 days 04-10-18 23-10-18
623 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
624 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
625 Manufacturing 180 days 25-11-18 23-05-19
626 Inspection 30 days 24-05-19 22-06-19
627 Painting and Packaging of Equipment 30 days 23-06-19 22-07-19
628 Despatch and receipt of Material at Site 20 days 23-07-19 11-08-19
633 Alum Dosing Tank 430 days 08-06-18 11-08-19 | [11 empty] | Alum Dosing Tank | 2018-08-06 | 2019-11-08
634 Placement of order 1 day 08-06-18 08-06-18
635 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
636 Engineer's Comments on 1st submission 28 days 06-09-18 03-10-18
637 Resubmission 20 days 04-10-18 23-10-18
638 Engineers review and Code-A approval 28 days 24-10-18 20-11-18
639 Issue of manufacturing Clearance 4 days 21-11-18 24-11-18
640 Manufacturing 180 days 25-11-18 23-05-19
641 Inspection 30 days 24-05-19 22-06-19
642 Painting and Packaging of Equipment 30 days 23-06-19 22-07-19
643 Despatch and receipt of Material at Site 20 days 23-07-19 11-08-19
644 Chlorination System including Scrubber, | [11 empty] | Chlorination System including Scrubber,Chlorinators, Booster Pumps etc. | 15/12/2017 | 2019-10-07
Chlorinators, Booster Pumps etc.
573 days 15-12-17 10-07-19
645 Placement of order 1 day 15-12-17 15-12-17
646 Submission of Datasheets / Drawings 25 days 08-05-18 01-06-18
647 Engineer's Comments on 1st submission 64 days 02-06-18 04-08-18
648 Resubmission 28 days 05-08-18 01-09-18
649 Engineers review and Code-A approval 28 days 02-09-18 29-09-18
650 Issue of manufacturing Clearance 4 days 30-09-18 03-10-18
651 Manufacturing 210 days 04-10-18 01-05-19
652 Inspection / Review of Test Certificates as applicable 25 days 02-05-19 26-05-19
653 Painting and Packaging of Equipment 20 days 27-05-19 15-06-19
654 Despatch and receipt of Material at Site 25 days 16-06-19 10-07-19
655 Civil Works 212 days 15-11-18 14-06-19 | [10 empty] | Civil Works | 15/11/2018 | 14/06/2019
656 Completion of excavation 10 days 15-11-18 24-11-18
657 Completion of RCC work upto Plinth for Chemical Building20 days 21-11-18 10-12-18
658 Grade Slab 20 days 10-12-18 29-12-18
659 Completion of RCC work Upto GF Slab 20 days 30-12-18 18-01-19
660 Completion of GF Slab 30 days 19-01-19 17-02-19
661 Completion of RCC work upto Top Slab 20 days 18-02-19 09-03-19
662 Completion of Top Slab 30 days 10-03-19 08-04-19
663 Completion of Block Masonary 40 days 09-04-19 18-05-19
664 Completion of Water proofing 20 days 20-04-19 09-05-19
665 Completion of Finishing works 45 days 01-05-19 14-06-19
666 Erection 122 days 01-07-19 30-10-19 | [10 empty] | Erection | 2019-01-07 | 30/10/2019
667 Erection of Mechanical and Piping Equipments 60 days 01-07-19 29-08-19
668 Erection of Electrical & Instrumentation
Equipments
61 days 01-08-19 30-09-19
669 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
30 days 01-10-19 30-10-19
670 Thickened Sludge Sludge Sump and Pump House 504 days 30-06-18 15-11-19 | [9 empty] | Thickened Sludge Sludge Sump and Pump House | 30/06/2018 | 15/11/2019
671 Mechanical GA Drawings 340 days 15-07-18 19-06-19 | [10 empty] | Mechanical GA Drawings | 15/07/2018 | 19/06/2019
672 Preparation and Submission to Client 15 days 15-07-18 29-07-18
673 Engineer's Comments on 1st submission 28 days 30-07-18 26-08-18
674 Resubmission for Code-B Approval 10 days 27-08-18 05-09-18
675 Engineers review and Code-B approval 28 days 06-09-18 03-10-18
676 Resubmission for Code-A approval 25 days 01-05-19 25-05-19
677 Engineers review and Code-A approval 25 days 26-05-19 19-06-19
682 Civil Design Drawings 334 days 01-10-18 30-08-19 | [10 empty] | Civil Design Drawings | 2018-01-10 | 30/08/2019
683 Preparation and Submission to Client 22 days 01-10-18 22-10-18
684 Engineer's Comments on 1st submission 28 days 23-10-18 19-11-18
685 Resubmission for Code-B Approval 12 days 20-11-18 01-12-18
686 Engineers review and Code-B approval 28 days 02-12-18 29-12-18
687 Resubmission for Code-A approval 30 days 01-07-19 30-07-19
688 Engineers review and Code-A approval 30 days 01-08-19 30-08-19
689 Procurement 436 days 30-06-18 08-09-19 | [10 empty] | Procurement | 30/06/2018 | 2019-08-09
690 Thickened Sludge Pumps 436 days 30-06-18 08-09-19
691 Placement of order 1 day 30-06-18 30-06-18
692 Submission of Datasheets / Drawings 25 days 04-10-18 28-10-18
693 Engineer's Comments on 1st submission 28 days 29-10-18 25-11-18
694 Resubmission 20 days 26-11-18 15-12-18
695 Engineers review and Code-A approval 28 days 16-12-18 12-01-19
696 Issue of manufacturing Clearance 4 days 13-01-19 16-01-19
697 Manufacturing 180 days 17-01-19 15-07-19
698 Inspection / Review of Test Certificates as
applicable
20 days 16-07-19 04-08-19
699 Painting and Packaging of Equipment 15 days 05-08-19 19-08-19
700 Despatch and receipt of Material at Site 20 days 20-08-19 08-09-19
701 Civil Works 200 days 01-01-19 19-07-19 | [10 empty] | civil works | 2019-01-01 | 19/07/2019
702 Completion of excavation 10 days 01-01-19 10-01-19
703 Completion of PCC 8 days 11-01-19 18-01-19
704 Completion of Raft 15 days 19-01-19 02-02-19
705 Completion of 50 % side wall 25 days 03-02-19 27-02-19
706 Completion of 100% side wall 25 days 28-02-19 24-03-19
707 Completion of RCC work upto Plinth for Pump
House
20 days 25-03-19 13-04-19
708 Grade Slab 12 days 14-04-19 25-04-19
709 Completion of RCC work Upto Top Slab 10 days 26-04-19 05-05-19
710 Completion of Top Slab 30 days 06-05-19 04-06-19
711 Completion of Block Masonary 15 days 05-06-19 19-06-19
712 Completion of Water proofing 15 days 15-05-19 29-05-19
713 Completion of Finishing works 30 days 20-06-19 19-07-19
714 Erection 76 days 01-09-19 15-11-19 | [10 empty] | Eretion | 2019-01-09 | 15/11/2019
715 Erection of Mechanical and Piping Equipments 45 days 01-09-19 15-10-19
716 Erection of Electrical & Instrumentation
Equipments
30 days 01-10-19 30-10-19
717 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as | [9 empty] | Piping / Electrical / instrumentation Equipments as applicable | 2019-01-11 | 15/11/2019
applicable
15 days 01-11-19 15-11-19
718 Thickener Feed Sump & Pump House/Screw
Thickener Shed
696 days 20-12-17 15-11-19
719 Mechanical GA Drawings 340 days 15-07-18 19-06-19 | [10 empty] | Mechanical GA Drawings | 15/07/2018 | 19/06/2019
720 Preparation and Submission to Client 15 days 15-07-18 29-07-18
721 Engineer's Comments on 1st submission 28 days 30-07-18 26-08-18
722 Resubmission for Code-B Approval 12 days 27-08-18 07-09-18
723 Engineers review and Code-B approval 12 days 10-09-18 21-09-18
724 Resubmission for Code-A approval 25 days 01-05-19 25-05-19
725 Engineers review and Code-A approval 25 days 26-05-19 19-06-19
726 Civil Design Drawings 334 days 01-10-18 30-08-19 | [10 empty] | Civil design drawings | 2018-01-10 | 30/08/2019
727 Preparation and Submission to Client 22 days 01-10-18 22-10-18
728 Engineer's Comments on 1st submission 28 days 23-10-18 19-11-18
729
Jun Jul Aug Sep Oct Nov Dec Jan Feb Mar Apr May Jun Jul Aug Sep Oct Nov Dec Jan Feb Mar Apr May Jun Jul Aug Sep Oct Nov Dec Jan Feb
7 Qtr 3, 2017 Qtr 4, 2017 Qtr 1, 2018 Qtr 2, 2018 Qtr 3, 2018 Qtr 4, 2018 Qtr 1, 2019 Qtr 2, 2019 Qtr 3, 2019 Qtr 4, 2019 Qtr 1, 20
Task
Split
Milestone
Summary
Project Summary
External Tasks
External Milestone
Deadline
100
732
733 Resubmission for Code-B Approval 12 days 20-11-18 01-12-18
734 Engineers review and Code-B approval 28 days 02-12-18 29-12-18
735 Resubmission for Code-A approval 30 days 01-07-19 30-07-19
736 Engineers review and Code-A approval 30 days 01-08-19 30-08-19
737 Procurement 619 days 20-12-17 30-08-19
738 Thickener Feed Pump 397 days 30-06-18 31-07-19
739 Placement of order 1 day 30-06-18 30-06-18
740 Submission of Datasheets / Drawings 25 days 04-10-18 28-10-18
741 Engineer's Comments on 1st submission 12 days 29-10-18 09-11-18
742 Resubmission 12 days 10-11-18 21-11-18
743 Engineers review and Code-A approval 12 days 22-11-18 03-12-18
744 Issue of manufacturing Clearance 4 days 04-12-18 07-12-18
745 Manufacturing 180 days 08-12-18 05-06-19
746 Inspection / Review of Test Certificates as
applicable
20 days 06-06-19 25-06-19
747 Painting and Packaging of Equipment 15 days 26-06-19 10-07-19
748 Despatch and receipt of Material at Site 21 days 11-07-19 31-07-19
749 Archimedian Screw Thickener 619 days 20-12-17 30-08-19
750 Placement of order 1 day 20-12-17 20-12-17
751 Submission of Datasheets / Drawings 25 days 04-10-18 28-10-18
752 Engineer's Comments on 1st submission 12 days 29-10-18 09-11-18
753 Resubmission 12 days 10-11-18 21-11-18
754 Engineers review and Code-A approval 12 days 22-11-18 03-12-18
755 Issue of manufacturing Clearance 4 days 04-12-18 07-12-18
756 Manufacturing 210 days 08-12-18 05-07-19
757 Inspection / Review of Test Certificates as
applicable
20 days 06-07-19 25-07-19
758 Painting and Packaging of Equipment 15 days 26-07-19 09-08-19
759 Despatch and receipt of Material at Site 21 days 10-08-19 30-08-19
760 Polyelectrolyte Dosing Pumps with Motors for
Existing STP
390 days 08-06-18 02-07-19
761 Placement of order 1 day 08-06-18 08-06-18
762 Submission of Datasheets / Drawings 20 days 17-08-18 05-09-18
763 Engineer's Comments on 1st submission 12 days 06-09-18 17-09-18
764 Resubmission 12 days 18-09-18 29-09-18
765 Engineers review and Code-A approval 12 days 30-09-18 11-10-18
766 Issue of manufacturing Clearance 4 days 12-10-18 15-10-18
767 Manufacturing 180 days 16-10-18 13-04-19
768 Inspection / Review of Test Certificates as
applicable
30 days 14-04-19 13-05-19
769 Painting and Packaging of Equipment 30 days 14-05-19 12-06-19
770 Despatch and receipt of Material at Site 20 days 13-06-19 02-07-19
771 Civil Works 200 days 01-01-19 19-07-19
772 Completion of excavation 10 days 01-01-19 10-01-19
773 Completion of PCC 8 days 11-01-19 18-01-19
774 Completion of Raft 15 days 19-01-19 02-02-19
775 Completion of 50 % side wall 25 days 03-02-19 27-02-19
776 Completion of 100% side wall 25 days 28-02-19 24-03-19
777 Completion of RCC work upto Plinth for Pump House 20 days 25-03-19 13-04-19
778 Grade Slab 12 days 14-04-19 25-04-19
779 Completion of RCC work Upto Top Slab 10 days 26-04-19 05-05-19
780 Completion of Top Slab 30 days 06-05-19 04-06-19
783 Completion of Block Masonary 15 days 05-06-19 19-06-19
784 Completion of Water proofing 15 days 15-05-19 29-05-19
785 Completion of Finishing works 30 days 20-06-19 19-07-19
786 Erection 106 days 02-08-19 15-11-19
787 Erection of Mechanical and Piping Equipments 60 days 02-08-19 30-09-19
788 Erection of Electrical & Instrumentation
Equipments
60 days 01-09-19 30-10-19
789 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
15 days 01-11-19 15-11-19
790 Anerobic Sludge Digester 599 days 01-02-18 22-09-19
791 Mechanical GA Drawings 533 days 01-02-18 18-07-19
792 Preparation and Submission to Client 9 days 01-02-18 09-02-18
793 Engineer's Comments on 1st submission 66 days 10-02-18 16-04-18
794 Resubmission for Code-B Approval 107 days 16-04-18 31-07-18
795 Engineers review and Code-B approval 28 days 01-08-18 28-08-18
796 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
797 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
798 Civil Design Drawings 483 days 28-05-18 22-09-19
799 Preparation and Submission to Client 15 days 28-05-18 11-06-18
800 Engineer's Comments on 1st submission 18 days 12-06-18 29-06-18
801 Resubmission for Code-B Approval 14 days 30-06-18 13-07-18
802 Engineers review and Code-B approval 12 days 14-07-18 25-07-18
803 Resubmission for Code-A approval 25 days 01-08-19 25-08-19
804 Engineers review and Code-A approval 28 days 26-08-19 22-09-19
805 Civil Works 304 days 01-08-18 31-05-19
806 Completion of excavation 60 days 01-08-18 29-09-18
807 Completion of PCC 45 days 25-08-18 08-10-18
808 Completion of Raft 120 days 10-09-18 07-01-19
809 Completion of 50 % side wall 120 days 15-10-18 11-02-19
810 Completion of 100% side wall 160 days 15-11-18 23-04-19
811 Completion of Hydro Test 120 days 01-01-19 30-04-19
812 Completion of Finishing works 120 days 01-02-19 31-05-19
813 Digester Sludge Mixing Pump House 663 days 06-02-18 30-11-19
814 Mechanical GA Drawings 472 days 06-02-18 23-05-19
815 Preparation and Submission to Client 16 days 06-02-18 21-02-18
816 Engineer's Comments on 1st submission 24 days 22-02-18 17-03-18
817 Resubmission for Code-B Approval 23 days 18-03-18 09-04-18
818 Engineers review and Code-B approval 11 days 10-04-18 20-04-18
819 Resubmission for Code-A approval 25 days 01-04-19 25-04-19
820 Engineers review and Code-A approval 28 days 26-04-19 23-05-19
821 Civil Design Drawings 453 days 20-04-18 16-07-19
822 Preparation and Submission to Client 11 days 20-04-18 30-04-18
823 Engineer's Comments on 1st submission 18 days 01-05-18 18-05-18
824 Resubmission for Code-B Approval 14 days 19-05-18 01-06-18
825 Engineers review and Code-B approval 28 days 02-06-18 29-06-18
826 Resubmission for Code-A approval 28 days 20-05-19 16-06-19
827 Engineers review and Code-A approval 30 days 17-06-19 16-07-19
832 Procurement 439 days 30-06-18 11-09-19
833 Digester Sludge Mixing System with Pumps 439 days 30-06-18 11-09-19
834 Placement of order 1 day 30-06-18 30-06-18
835 Submission of Datasheets / Drawings 20 days 01-07-18 20-07-18
836 Engineer's Comments on 1st submission 12 days 21-07-18 01-08-18
837 Resubmission 25 days 02-08-18 26-08-18
838 Engineers review and Code-A approval 12 days 27-08-18 07-09-18
839 Issue of manufacturing Clearance 4 days 08-09-18 11-09-18
840 Manufacturing 270 days 12-09-18 08-06-19
841 Inspection / Review of Test Certificates as
applicable
10 days 09-06-19 18-06-19
842 Painting and Packaging of Equipment 10 days 19-06-19 28-06-19
843 Despatch and receipt of Material at Site 75 days 29-06-19 11-09-19
844 Civil Works 309 days 01-06-18 05-04-19
845 Completion of excavation 20 days 01-06-18 20-06-18
846 Completion of PCC 10 days 21-06-18 30-06-18
847 Completion of RCC work upto Plinth for Pump House 60 days 01-07-18 29-08-18
848 Grade Slab 45 days 30-08-18 13-10-18
849 Completion of RCC work Upto Top Slab 60 days 14-10-18 12-12-18
850 Completion of Top Slab 45 days 13-12-18 26-01-19
851 Completion of Block Masonary 25 days 27-01-19 20-02-19
852 Completion of Water proofing 15 days 10-02-19 24-02-19
853 Completion of Finishing works 50 days 15-02-19 05-04-19
854 Erection 91 days 01-09-19 30-11-19
855 Erection of Mechanical and Piping Equipments 60 days 01-09-19 30-10-19
856 Erection of Electrical & Instrumentation
Equipments
46 days 01-10-19 15-11-19
857 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
15 days 16-11-19 30-11-19
858 Membrane Gas Dome 497 days 20-07-18 28-11-19
859 Mechanical GA Drawings 305 days 20-07-18 20-05-19
860 Preparation and Submission to Client 15 days 20-07-18 03-08-18
861 Engineer's Comments on 1st submission 28 days 04-08-18 31-08-18
862 Resubmission for Code-B Approval 10 days 01-09-18 10-09-18
863 Engineers review and Code-B approval 28 days 11-09-18 08-10-18
864 Resubmission for Code-A approval 25 days 01-04-19 25-04-19
865 Engineers review and Code-A approval 25 days 26-04-19 20-05-19
866 Civil Design Drawings 303 days 01-10-18 30-07-19
867 Preparation and Submission to Client 22 days 01-10-18 22-10-18
868 Engineer's Comments on 1st submission 28 days 23-10-18 19-11-18
869 Resubmission for Code-B Approval 12 days 20-11-18 01-12-18
870 Engineers review and Code-B approval 28 days 02-12-18 29-12-18
871 Resubmission for Code-A approval 30 days 01-06-19 30-06-19
872 Engineers review and Code-A approval 30 days 01-07-19 30-07-19
873 Procurement 413 days 30-07-18 15-09-19
874 Gas Membrane 413 days 30-07-18 15-09-19
875 Placement of order 1 day 30-07-18 30-07-18
876 Submission of Datasheets / Drawings 25 days 16-09-18 10-10-18
877 Engineer's Comments on 1st submission 12 days 11-10-18 22-10-18
878 Resubmission 12 days 23-10-18 03-11-18
879 Engineers review and Code-A approval 12 days 04-11-18 15-11-18
880 Issue of manufacturing Clearance 4 days 16-11-18 19-11-18
881 Manufacturing 210 days 20-11-18 17-06-19
882 Inspection / Review of Test Certificates as
applicable
10 days 18-06-19 27-06-19
883 Painting and Packaging of Equipment 20 days 28-06-19 17-07-19
884 Despatch and receipt of Material at Site 60 days 18-07-19 15-09-19
885 Civil Works 145 days 25-12-18 18-05-19
886 Completion of excavation 25 days 25-12-18 18-01-19
887 Completion of PCC 25 days 05-01-19 29-01-19
888 Completion of RCC work upto Plinth 30 days 15-01-19 13-02-19
889 Completion of 50 % work 30 days 01-02-19 02-03-19
890 Completion of 100% work 45 days 20-02-19 05-04-19
891 Completion of Finishing works 60 days 20-03-19 18-05-19
892 Erection 89 days 01-09-19 28-11-19
893 Erection of Mechanical and Piping Equipments 60 days 01-09-19 30-10-19
894 Erection of Electrical & Instrumentation
Equipments
30 days 15-10-19 13-11-19
895 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
15 days 14-11-19 28-11-19
896 H T Room / Transformer Yard / L T Room 323 days 01-10-18 19-08-19
897 Electrical Design Drawings 228 days 01-10-18 16-05-19
898 Preparation and Submission to Client 15 days 01-10-18 15-10-18
899 Engineer's Comments on 1st submission 28 days 16-10-18 12-11-18
900 Resubmission for Code-B Approval 10 days 13-11-18 22-11-18
901 Engineers review and Code-B approval 26 days 23-11-18 18-12-18
902 Resubmission for Code-A approval 20 days 01-04-19 20-04-19
903 Engineers review and Code-A approval 26 days 21-04-19 16-05-19
904 Civil Design Drawings 248 days 15-12-18 19-08-19
905 Preparation and Submission to Client 15 days 15-12-18 29-12-18
906 Engineer's Comments on 1st submission 28 days 30-12-18 26-01-19
907 Resubmission for Code-B Approval 10 days 27-01-19 05-02-19
908 Engineers review and Code-B approval 26 days 06-02-19 03-03-19
909 Resubmission for Code-A approval 25 days 01-07-19 25-07-19
910 Engineers review and Code-A approval 25 days 26-07-19 19-08-19
911 Civil Works 167 days 01-03-19 14-08-19
912 Completion of excavation 5 days 01-03-19 05-03-19
913 Completion of PCC 5 days 06-03-19 10-03-19
914 Completion of RCC work upto Plinth 20 days 11-03-19 30-03-19
915 Grade Slab 20 days 01-04-19 20-04-19
916 Completion of RCC work Upto Top Slab 10 days 21-04-19 30-04-19
917 Completion of Top Slab 30 days 01-05-19 30-05-19
918 Completion of Block Masonary 30 days 01-06-19 30-06-19
919 Completion of Water proofing 30 days 01-07-19 30-07-19
920 Completion of Finishing works 45 days 01-07-19 14-08-19
921 DG Shed for TSPS & STP 407 days 19-09-18 30-10-19
922 Electrical Design Drawings 228 days 01-10-18 16-05-19
923 Preparation and Submission to Client 15 days 01-10-18 15-10-18
924 Engineer's Comments on 1st submission 28 days 16-10-18 12-11-18
925 Resubmission for Code-B Approval 10 days 13-11-18 22-11-18
926 Engineers review and Code-B approval 26 days 23-11-18 18-12-18
927 Resubmission for Code-A approval 20 days 01-04-19 20-04-19
930 Engineers review and Code-A approval 26 days 21-04-19 16-05-19
931 Civil Design Drawings 248 days 15-12-18 19-08-19
932 Preparation and Submission to Client 15 days 15-12-18 29-12-18
933 Engineer's Comments on 1st submission 28 days 30-12-18 26-01-19
934 Resubmission for Code-B Approval 10 days 27-01-19 05-02-19
935 Engineers review and Code-B approval 26 days 06-02-19 03-03-19
936 Resubmission for Code-A approval 25 days 01-07-19 25-07-19
937 Engineers review and Code-A approval 25 days 26-07-19 19-08-19
938 Procurement 261 days 19-09-18 06-06-19
939 DG Sets 261 days 19-09-18 06-06-19
940 Placement of order 1 day 19-09-18 19-09-18
941 Submission of Datasheets / Drawings 10 days 20-09-18 29-09-18
942 Engineer's Comments on 1st submission 15 days 30-09-18 14-10-18
943 Resubmission 10 days 15-10-18 24-10-18
944 Engineers review and Code-A approval 28 days 25-10-18 21-11-18
945 Issue of manufacturing Clearance 4 days 22-11-18 25-11-18
946 Manufacturing 151 days 26-11-18 25-04-19
947 Inspection / Review of Test Certificates as
applicable
12 days 26-04-19 07-05-19
948 Painting and Packaging of Equipment 10 days 08-05-19 17-05-19
949 Despatch and receipt of Material at Site 20 days 18-05-19 06-06-19
950 Civil Works 122 days 01-03-19 30-06-19
951 Completion of excavation 5 days 01-03-19 05-03-19
952 Completion of PCC 5 days 06-03-19 10-03-19
953 Completion of RCC work upto Plinth 20 days 11-03-19 30-03-19
954 Grade Slab 20 days 01-04-19 20-04-19
955 Completion of work Upto Roof Shed 10 days 21-04-19 30-04-19
956 Completion of Top Roof 30 days 01-05-19 30-05-19
957 Completion of Finishing works 30 days 01-06-19 30-06-19
958 Erection 122 days 01-07-19 30-10-19
959 Erection of Electrical & Instrumentation
Equipments
90 days 01-07-19 28-09-19
960 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
30 days 01-10-19 30-10-19
961 Administrative cum Laboratory and SCADA Building 633 days 21-02-18 15-11-19
962 Civil Design Drawings 466 days 21-02-18 01-06-19
963 Preparation and Submission to Client 7 days 21-02-18 27-02-18
964 Engineer's Comments on 1st submission 41 days 28-02-18 09-04-18
965 Resubmission for Code-B Approval 36 days 10-04-18 15-05-18
966 Engineers review and Code-B approval 21 days 05-05-18 25-05-18
967 Resubmission for Code-A approval 25 days 10-04-19 04-05-19
968 Engineers review and Code-A approval 28 days 05-05-19 01-06-19
969 Procurement 252 days 15-01-19 23-09-19
970 UPS 212 days 15-01-19 14-08-19
971 Placement of order 1 day 15-01-19 15-01-19
972 Submission of Datasheets / Drawings 15 days 16-01-19 30-01-19
973 Engineer's Comments on 1st submission 28 days 31-01-19 27-02-19
974 Resubmission 20 days 28-02-19 19-03-19
975 Engineers review and Code-A approval 28 days 20-03-19 16-04-19
976 Issue of manufacturing Clearance 10 days 17-04-19 26-04-19
977 Manufacturing 90 days 27-04-19 25-07-19
981 Despatch and receipt of Material at Site 20 days 26-07-19 14-08-19
982 Lab Equipments 252 days 15-01-19 23-09-19
983 Placement of order 1 day 15-01-19 15-01-19
984 Submission of Datasheets / Drawings 15 days 16-01-19 30-01-19
985 Engineer's Comments on 1st submission 28 days 31-01-19 27-02-19
986 Resubmission 20 days 28-02-19 19-03-19
987 Engineers review and Code-A approval 28 days 20-03-19 16-04-19
988 Issue of manufacturing Clearance 10 days 17-04-19 26-04-19
989 Manufacturing 90 days 27-04-19 25-07-19
990 Despatch and receipt of Material at Site 60 days 26-07-19 23-09-19
991 Civil Works 379 days 17-04-18 30-04-19
992 Completion of excavation 10 days 17-04-18 26-04-18
993 Completion of PCC 10 days 27-04-18 06-05-18
994 Completion of RCC work upto Plinth 50 days 06-05-18 24-06-18
995 Grade Slab 20 days 25-06-18 14-07-18
996 Completion of RCC work Upto GF Slab 10 days 15-07-18 24-07-18
997 Completion of GF Slab 30 days 25-07-18 23-08-18
998 Completion of RCC work Upto FF Slab 10 days 24-08-18 02-09-18
999 Completion of FF Slab 30 days 03-09-18 02-10-18
1000 Completion of RCC work Upto SF Slab 10 days 03-10-18 12-10-18
1001 Completion of SF Slab 30 days 13-10-18 11-11-18
1002 Completion of RCC work Upto TF Slab 10 days 12-11-18 21-11-18
1003 Completion of TF Slab 30 days 22-11-18 21-12-18
1004 Completion of Block Masonary 139 days 25-09-18 10-02-19
1005 Completion of Water proofing 20 days 10-01-19 29-01-19
1006 Completion of Finishing works 181 days 01-11-18 30-04-19
1007 Erection 46 days 01-10-19 15-11-19
1008 Erection of Mechanical and Piping Equipments 30 days 01-10-19 30-10-19
1009 Erection of Electrical & Instrumentation
Equipments
30 days 01-10-19 30-10-19
1010 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
15 days 01-11-19 15-11-19
1011 Gas Engine Building/Gas Collecting & Engine Feed
Blower Shed
487 days 01-08-18 30-11-19
1012 Mechanical GA Drawings 293 days 01-08-18 20-05-19
1013 Preparation and Submission to Client 15 days 01-08-18 15-08-18
1014 Engineer's Comments on 1st submission 12 days 16-08-18 27-08-18
1015 Resubmission for Code-B Approval 10 days 28-08-18 06-09-18
1016 Engineers review and Code-B approval 12 days 07-09-18 18-09-18
1017 Resubmission for Code-A approval 25 days 01-04-19 25-04-19
1018 Engineers review and Code-A approval 25 days 26-04-19 20-05-19
1019 Civil Design Drawings 320 days 15-10-18 30-08-19
1020 Preparation and Submission to Client 22 days 15-10-18 05-11-18
1021 Engineer's Comments on 1st submission 28 days 06-11-18 03-12-18
1022 Resubmission for Code-B Approval 12 days 04-12-18 15-12-18
1023 Engineers review and Code-B approval 28 days 16-12-18 12-01-19
1024 Resubmission for Code-A approval 30 days 01-07-19 30-07-19
1025 Engineers review and Code-A approval 30 days 01-08-19 30-08-19
1030 Bio Gas Engine 405 days 01-08-18 09-09-19
1031 Placement of order 1 day 01-08-18 01-08-18
1032 Submission of Datasheets / Drawings 14 days 02-08-18 15-08-18
1033 Engineer's Comments on 1st submission 12 days 16-08-18 27-08-18
1034 Resubmission 12 days 28-08-18 08-09-18
1035 Engineers review and Code-A approval 12 days 09-09-18 20-09-18
1036 Issue of manufacturing Clearance 4 days 21-09-18 24-09-18
1037 Manufacturing 270 days 25-09-18 21-06-19
1038 Inspection / Review of Test Certificates as
applicable
10 days 22-06-19 01-07-19
1039 Painting and Packaging of Equipment 25 days 02-07-19 26-07-19
1040 Despatch and receipt of Material at Site 45 days 27-07-19 09-09-19
1041 Bio Gas Collecting Blowers 405 days 01-08-18 09-09-19
1042 Placement of order 1 day 01-08-18 01-08-18
1043 Submission of Datasheets / Drawings 14 days 02-08-18 15-08-18
1044 Engineer's Comments on 1st submission 12 days 16-08-18 27-08-18
1045 Resubmission 12 days 28-08-18 08-09-18
1046 Engineers review and Code-A approval 12 days 09-09-18 20-09-18
1047 Issue of manufacturing Clearance 4 days 21-09-18 24-09-18
1048 Manufacturing 270 days 25-09-18 21-06-19
1049 Inspection / Review of Test Certificates as
applicable
10 days 22-06-19 01-07-19
1050 Painting and Packaging of Equipment 25 days 02-07-19 26-07-19
1051 Despatch and receipt of Material at Site 45 days 27-07-19 09-09-19
1052 Bio Gas Feed Blower 405 days 01-08-18 09-09-19
1053 Placement of order 1 day 01-08-18 01-08-18
1054 Submission of Datasheets / Drawings 14 days 02-08-18 15-08-18
1055 Engineer's Comments on 1st submission 12 days 16-08-18 27-08-18
1056 Resubmission 12 days 28-08-18 08-09-18
1057 Engineers review and Code-A approval 12 days 09-09-18 20-09-18
1058 Issue of manufacturing Clearance 4 days 21-09-18 24-09-18
1059 Manufacturing 270 days 25-09-18 21-06-19
1060 Inspection / Review of Test Certificates as
applicable
10 days 22-06-19 01-07-19
1061 Painting and Packaging of Equipment 25 days 02-07-19 26-07-19
1062 Despatch and receipt of Material at Site 45 days 27-07-19 09-09-19
1063 Bio Gas Scrubbing System 405 days 01-08-18 09-09-19
1064 Placement of order 1 day 01-08-18 01-08-18
1065 Submission of Datasheets / Drawings 14 days 02-08-18 15-08-18
1066 Engineer's Comments on 1st submission 12 days 16-08-18 27-08-18
1067 Resubmission 12 days 28-08-18 08-09-18
1068 Engineers review and Code-A approval 12 days 09-09-18 20-09-18
1069 Issue of manufacturing Clearance 4 days 21-09-18 24-09-18
1070 Manufacturing 270 days 25-09-18 21-06-19
1071 Inspection / Review of Test Certificates as
applicable
10 days 22-06-19 01-07-19
1072 Painting and Packaging of Equipment 25 days 02-07-19 26-07-19
1073 Despatch and receipt of Material at Site 45 days 27-07-19 09-09-19
1074 Civil Works 170 days 01-01-19 19-06-19
1075 Completion of excavation 5 days 01-01-19 05-01-19
1076 Completion of PCC 10 days 06-01-19 15-01-19
1077 Completion of RCC work upto Plinth 25 days 16-01-19 09-02-19
1078 Grade Slab 30 days 10-02-19 11-03-19
1079 Completion of RCC work Upto Top Slab 10 days 12-03-19 21-03-19
1080 Completion of Top Slab 30 days 22-03-19 20-04-19
1081 Completion of Block Masonary 30 days 21-04-19 20-05-19
1082 Completion of Water proofing 20 days 01-05-19 20-05-19
1083 Completion of Finishing works 30 days 21-05-19 19-06-19
1084 Erection 91 days 01-09-19 30-11-19
1085 Erection of Mechanical and Piping
Equipments
60 days 01-09-19 30-10-19
1086 Erection of Electrical & Instrumentation
Equipments
30 days 16-10-19 14-11-19
1087 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
16 days 15-11-19 30-11-19
1088 Plant Drain Pump Station 525 days 24-05-18 30-10-19
1089 Mechanical GA Drawings 347 days 11-06-18 23-05-19
1090 Preparation and Submission to Client 20 days 11-06-18 30-06-18
1091 Engineer's Comments on 1st submission 28 days 01-07-18 28-07-18
1092 Resubmission for Code-B Approval 12 days 29-07-18 09-08-18
1093 Engineers review and Code-B approval 28 days 10-08-18 06-09-18
1094 Resubmission for Code-A approval 25 days 01-04-19 25-04-19
1095 Engineers review and Code-A approval 28 days 26-04-19 23-05-19
1096 Civil Design Drawings 326 days 01-09-18 23-07-19
1097 Preparation and Submission to Client 22 days 01-09-18 22-09-18
1098 Engineer's Comments on 1st submission 28 days 23-09-18 20-10-18
1099 Resubmission for Code-B Approval 15 days 21-10-18 04-11-18
1100 Engineers review and Code-B approval 28 days 05-11-18 02-12-18
1101 Resubmission for Code-A approval 25 days 01-06-19 25-06-19
1102 Engineers review and Code-A approval 28 days 26-06-19 23-07-19
1103 Procurement 433 days 24-05-18 30-07-19
1104 Plant Drain pump with motor 433 days 24-05-18 30-07-19
1105 Placement of order 1 day 24-05-18 24-05-18
1106 Submission of Datasheets / Drawings 12 days 06-07-18 17-07-18
1107 Engineer's Comments on 1st submission 28 days 18-07-18 14-08-18
1108 Resubmission 15 days 15-08-18 29-08-18
1109 Engineers review and Code-A approval 28 days 30-08-18 26-09-18
1110 Issue of manufacturing Clearance 3 days 27-09-18 29-09-18
1111 Manufacturing 240 days 30-09-18 27-05-19
1112 Inspection / Review of Test Certificates as
applicable
15 days 28-05-19 11-06-19
1113 Painting and Packaging of Equipment 20 days 12-06-19 01-07-19
1114 Despatch and receipt of Material at Site 30 days 01-07-19 30-07-19
1115 Civil Works 200 days 01-12-18 18-06-19
1116 Completion of excavation 5 days 01-12-18 05-12-18
1117 Completion of PCC 4 days 06-12-18 09-12-18
1118 Completion of Raft 15 days 10-12-18 24-12-18
1119 Completion of 50 % side wall 60 days 25-12-18 22-02-19
1120 Completion of 100% side wall 60 days 23-02-19 23-04-19
1121 Completion of Hydrotest 30 days 24-04-19 23-05-19
1122 Completion of finishing works 30 days 20-05-19 18-06-19
1123 Erection 91 days 01-08-19 30-10-19
1124 Erection of Mechanical and Piping Equipments 30 days 01-08-19 30-08-19
1125 Erection of Electrical & Instrumentation
Equipments
30 days 01-09-19 30-09-19
1126 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
30 days 01-10-19 30-10-19
1127 Filtrate Sump 525 days 24-05-18 30-10-19
1128 Mechanical GA Drawings 347 days 11-06-18 23-05-19
1129 Preparation and Submission to Client 20 days 11-06-18 30-06-18
1130 Engineer's Comments on 1st submission 28 days 01-07-18 28-07-18
1131 Resubmission for Code-B Approval 12 days 29-07-18 09-08-18
1132 Engineers review and Code-B approval 28 days 10-08-18 06-09-18
1133 Resubmission for Code-A approval 25 days 01-04-19 25-04-19
1134 Engineers review and Code-A approval 28 days 26-04-19 23-05-19
1135 Civil Design Drawings 326 days 01-09-18 23-07-19
1136 Preparation and Submission to Client 22 days 01-09-18 22-09-18
1137 Engineer's Comments on 1st submission 28 days 23-09-18 20-10-18
1138 Resubmission for Code-B Approval 15 days 21-10-18 04-11-18
1139 Engineers review and Code-B approval 28 days 05-11-18 02-12-18
1140 Resubmission for Code-A approval 25 days 01-06-19 25-06-19
1141 Engineers review and Code-A approval 28 days 26-06-19 23-07-19
1142 Procurement 433 days 24-05-18 30-07-19
1143 Filtrate pump with motor 433 days 24-05-18 30-07-19
1144 Placement of order 1 day 24-05-18 24-05-18
1145 Submission of Datasheets / Drawings 12 days 06-07-18 17-07-18
1146 Engineer's Comments on 1st submission 28 days 18-07-18 14-08-18
1147 Resubmission 15 days 15-08-18 29-08-18
1148 Engineers review and Code-A approval 28 days 30-08-18 26-09-18
1149 Issue of manufacturing Clearance 3 days 27-09-18 29-09-18
1150 Manufacturing 240 days 30-09-18 27-05-19
1151 Inspection / Review of Test Certificates as
applicable
15 days 28-05-19 11-06-19
1152 Painting and Packaging of Equipment 20 days 12-06-19 01-07-19
1153 Despatch and receipt of Material at Site 30 days 01-07-19 30-07-19
1154 Civil Works 200 days 01-12-18 18-06-19
1155 Completion of excavation 5 days 01-12-18 05-12-18
1156 Completion of PCC 4 days 06-12-18 09-12-18
1157 Completion of Raft 15 days 10-12-18 24-12-18
1158 Completion of 50 % side wall 60 days 25-12-18 22-02-19
1159 Completion of 100% side wall 60 days 23-02-19 23-04-19
1160 Completion of Hydrotest 30 days 24-04-19 23-05-19
1161 Completion of finishing works 30 days 20-05-19 18-06-19
1162 Erection 91 days 01-08-19 30-10-19
1163 Erection of Mechanical and Piping Equipments 30 days 01-08-19 30-08-19
1164 Erection of Electrical & Instrumentation
Equipments
30 days 01-09-19 30-09-19
1165 Site Acceptance test (Dry / Wet) for Mechanical /
Piping / Electrical / instrumentation Equipments as
applicable
30 days 01-10-19 30-10-19
1166 Security Cabin 328 days 20-01-18 13-12-18
1167 Civil Design Drawings 328 days 20-01-18 13-12-18
1168 Preparation and Submission to Client 25 days 20-01-18 13-02-18
1169 Engineer's Comments on 1st submission 28 days 14-02-18 13-03-18
1170 Resubmission for Code-B Approval 10 days 14-03-18 23-03-18
1171 Engineers review and Code-B approval 26 days 24-03-18 18-04-18
1172 Resubmission for Code-A approval 28 days 19-10-18 15-11-18
1173 Engineers review and Code-A approval 28 days 16-11-18 13-12-18
1174 Civil Works 220 days 01-05-18 06-12-18
1175 Completion of excavation 10 days 01-05-18 10-05-18
1176 Completion of PCC 10 days 11-05-18 20-05-18
1177 Completion of RCC work upto Plinth 25 days 21-05-18 14-06-18
1178 Grade Slab 35 days 15-06-18 19-07-18
1179 Completion of RCC work Upto Top Slab 30 days 20-07-18 18-08-18
1180 Completion of Top Slab 30 days 19-08-18 17-09-18
1181 Completion of Block Masonary 30 days 18-09-18 17-10-18
1182 Completion of Water proofing 20 days 18-10-18 06-11-18
1183 Completion of Finishing works 30 days 07-11-18 06-12-18
1184 Road & Drain/Landscapping works 274 days 01-05-19 29-01-20
1185 Civil Design Drawings - Roads & Drains and
Landscapping
203 days 01-05-19 19-11-19
1186 Preparation and Submission to Client 25 days 01-05-19 25-05-19
1187 Engineer's Comments on 1st submission 28 days 26-05-19 22-06-19
1188 Resubmission for Code-B Approval 15 days 23-06-19 07-07-19
1189 Engineers review and Code-B approval 15 days 08-07-19 22-07-19
1190 Resubmission for Code-A approval 22 days 01-10-19 22-10-19
1191 Engineers review and Code-A approval 28 days 23-10-19 19-11-19
1192 Roads 90 days 01-11-19 29-01-20
1193 Civil works 90 days 01-11-19 29-01-20
1194 Completion of 100% Work 90 days 01-11-19 29-01-20
1195 Drains 120 days 01-08-19 28-11-19
1196 Civil works 120 days 01-08-19 28-11-19
1197 Completion of 100% Work 120 days 01-08-19 28-11-19
1198 Landscapping 90 days 01-11-19 29-01-20
1199 Plantation Work including Red soil filling and
dressing
90 days 01-11-19 29-01-20
1200 Completion of 100% Work 90 days 01-11-19 29-01-20
1201 Mechanical Procurement 447 days 10-08-18 30-10-19
1202 Pipes and Valves Procurement 447 days 10-08-18 30-10-19
1203 Gate Valves 218 days 10-08-18 15-03-19
1204 Placement of order 10 days 10-08-18 19-08-18
1205 Submission of Datasheets / Drawings 10 days 20-08-18 29-08-18
1206 Engineer's Comments on 1st submission 15 days 30-08-18 13-09-18
1207 Resubmission 5 days 14-09-18 18-09-18
1208 Engineers review and Code-A approval 15 days 19-09-18 03-10-18
1209 Issue of manufacturing Clearance 3 days 04-10-18 06-10-18
1210 Manufacturing 120 days 07-10-18 03-02-19
1211 Inspection / Review of Test Certificates as
applicable
10 days 04-02-19 13-02-19
1212 Painting and Packaging of Equipment 10 days 14-02-19 23-02-19
1213 Despatch and receipt of Material at Site 20 days 24-02-19 15-03-19
1214 Non Return Valves 345 days 10-08-18 20-07-19
1215 Placement of order 10 days 10-08-18 19-08-18
1216 Submission of Datasheets / Drawings 15 days 20-08-18 03-09-18
1217 Engineer's Comments on 1st submission 15 days 04-09-18 18-09-18
1218 Resubmission 10 days 19-09-18 28-09-18
1219 Engineers review and Code-A approval 22 days 29-09-18 20-10-18
1220 Issue of manufacturing Clearance 3 days 21-10-18 23-10-18
1223 Manufacturing 210 days 24-10-18 21-05-19
1224 Inspection / Review of Test Certificates as
applicable
20 days 22-05-19 10-06-19
1225 Painting and Packaging of Equipment 20 days 11-06-19 30-06-19
1226 Despatch and receipt of Material at Site 20 days 01-07-19 20-07-19
1227 Knife gate Valves 248 days 10-08-18 14-04-19
1228 Placement of order 10 days 10-08-18 19-08-18
1229 Submission of Datasheets / Drawings 10 days 20-08-18 29-08-18
1230 Engineer's Comments on 1st submission 15 days 30-08-18 13-09-18
1231 Resubmission 5 days 14-09-18 18-09-18
1232 Engineers review and Code-A approval 15 days 19-09-18 03-10-18
1233 Issue of manufacturing Clearance 3 days 04-10-18 06-10-18
1234 Manufacturing 150 days 07-10-18 05-03-19
1235 Inspection / Review of Test Certificates as
applicable
10 days 06-03-19 15-03-19
1236 Painting and Packaging of Equipment 10 days 16-03-19 25-03-19
1237 Despatch and receipt of Material at Site 20 days 26-03-19 14-04-19
1238 Ball Valves 305 days 10-08-18 10-06-19
1239 Placement of order 10 days 10-08-18 19-08-18
1240 Submission of Datasheets / Drawings 15 days 20-08-18 03-09-18
1241 Engineer's Comments on 1st submission 15 days 04-09-18 18-09-18
1242 Resubmission 10 days 19-09-18 28-09-18
1243 Engineers review and Code-A approval 22 days 29-09-18 20-10-18
1244 Issue of manufacturing Clearance 3 days 21-10-18 23-10-18
1245 Manufacturing 180 days 24-10-18 21-04-19
1246 Inspection / Review of Test Certificates as
applicable
20 days 22-04-19 11-05-19
1247 Painting and Packaging of Equipment 10 days 12-05-19 21-05-19
1248 Despatch and receipt of Material at Site 20 days 22-05-19 10-06-19
1249 Butterfly Valves 345 days 10-08-18 20-07-19
1250 Placement of order 10 days 10-08-18 19-08-18
1251 Submission of Datasheets / Drawings 15 days 20-08-18 03-09-18
1252 Engineer's Comments on 1st submission 15 days 04-09-18 18-09-18
1253 Resubmission 10 days 19-09-18 28-09-18
1254 Engineers review and Code-A approval 22 days 29-09-18 20-10-18
1255 Issue of manufacturing Clearance 3 days 21-10-18 23-10-18
1256 Manufacturing 210 days 24-10-18 21-05-19
1257 Inspection / Review of Test Certificates as
applicable
20 days 22-05-19 10-06-19
1258 Painting and Packaging of Equipment 20 days 11-06-19 30-06-19
1259 Despatch and receipt of Material at Site 20 days 01-07-19 20-07-19
1260 D I Pipes 218 days 10-08-18 15-03-19
1261 Placement of order 10 days 10-08-18 19-08-18
1262 Submission of Datasheets / Drawings 10 days 20-08-18 29-08-18
1263 Engineer's Comments on 1st submission 15 days 30-08-18 13-09-18
1264 Resubmission 5 days 14-09-18 18-09-18
1265 Engineers review and Code-A approval 15 days 19-09-18 03-10-18
1266 Issue of manufacturing Clearance 3 days 04-10-18 06-10-18
1267 Manufacturing 120 days 07-10-18 03-02-19
1268 Inspection / Review of Test Certificates as
applicable
10 days 04-02-19 13-02-19
1269 Painting and Packaging of Equipment 10 days 14-02-19 23-02-19
1270 Despatch and receipt of Material at Site 20 days 24-02-19 15-03-19
1273 D I Fittings 305 days 10-08-18 10-06-19
1274 Placement of order 10 days 10-08-18 19-08-18
1275 Submission of Datasheets / Drawings 15 days 20-08-18 03-09-18
1276 Engineer's Comments on 1st submission 15 days 04-09-18 18-09-18
1277 Resubmission 10 days 19-09-18 28-09-18
1278 Engineers review and Code-A approval 22 days 29-09-18 20-10-18
1279 Issue of manufacturing Clearance 3 days 21-10-18 23-10-18
1280 Manufacturing 180 days 24-10-18 21-04-19
1281 Inspection / Review of Test Certificates as
applicable
20 days 22-04-19 11-05-19
1282 Painting and Packaging of Equipment 10 days 12-05-19 21-05-19
1283 Despatch and receipt of Material at Site 20 days 22-05-19 10-06-19
1284 SS Pipes and Fittings 305 days 10-08-18 10-06-19
1285 Placement of order 10 days 10-08-18 19-08-18
1286 Submission of Datasheets / Drawings 15 days 20-08-18 03-09-18
1287 Engineer's Comments on 1st submission 15 days 04-09-18 18-09-18
1288 Resubmission 10 days 19-09-18 28-09-18
1289 Engineers review and Code-A approval 22 days 29-09-18 20-10-18
1290 Issue of manufacturing Clearance 3 days 21-10-18 23-10-18
1291 Manufacturing 180 days 24-10-18 21-04-19
1292 Inspection / Review of Test Certificates as
applicable
20 days 22-04-19 11-05-19
1293 Painting and Packaging of Equipment 10 days 12-05-19 21-05-19
1294 Despatch and receipt of Material at Site 20 days 22-05-19 10-06-19
1295 EOT / HOT Hoist 183 days 10-12-18 10-06-19
1296 Placement of order 10 days 10-12-18 19-12-18
1297 Submission of Datasheets / Drawings 15 days 20-12-18 03-01-19
1298 Engineer's Comments on 1st submission 15 days 04-01-19 18-01-19
1299 Resubmission 10 days 19-01-19 28-01-19
1300 Engineers review and Code-A approval 22 days 29-01-19 19-02-19
1301 Issue of manufacturing Clearance 3 days 20-02-19 22-02-19
1302 Manufacturing 58 days 23-02-19 21-04-19
1303 Inspection / Review of Test Certificates as
applicable
20 days 22-04-19 11-05-19
1304 Painting and Packaging of Equipment 10 days 12-05-19 21-05-19
1305 Despatch and receipt of Material at Site 20 days 22-05-19 10-06-19
1306 Erection of Common Mechanical and Piping Equipme1n5t2s days 01-06-19 30-10-19
1307 Erection of Mechanical and Piping
Equipments
92 days 01-06-19 31-08-19
1308 Erection of Electrical & Instrumentation
Equipments
60 days 01-08-19 29-09-19
1309 Site Acceptance test (Dry / Wet) for
Mechanical / Piping / Electrical /
instrumentation Equipments as applicable
30 days 01-10-19 30-10-19
1310 E & I Documents and Engineering 368 days 15-08-18 17-08-19
1311 Electrical 368 days 15-08-18 17-08-19
1312 Transformer Sizing Calculation 246 days 15-08-18 17-04-19
1313 Preparation and Submission to Client 5 days 15-08-18 19-08-18
1314 Engineer's Comments on 1st submission 12 days 20-08-18 31-08-18
1315 Resubmission for Code-B Approval 3 days 01-09-18 03-09-18
1316 Engineers review and Code-B approval 15 days 04-09-18 18-09-18
1317 Resubmission for Code-A approval 20 days 01-03-19 20-03-19
1318 Engineers review and Code-A approval 28 days 21-03-19 17-04-19
1319 D G Sizing Calculation 246 days 15-08-18 17-04-19
1320 Preparation and Submission to Client 5 days 15-08-18 19-08-18
1321 Engineer's Comments on 1st submission 12 days 20-08-18 31-08-18
1322 Resubmission for Code-B Approval 3 days 01-09-18 03-09-18
1323 Engineers review and Code-B approval 15 days 04-09-18 18-09-18
1324 Resubmission for Code-A approval 20 days 01-03-19 20-03-19
1325 Engineers review and Code-A approval 28 days 21-03-19 17-04-19
1326 L T Capacitor Sizing Calculation 318 days 04-09-18 18-07-19
1327 Preparation and Submission to Client 25 days 04-09-18 28-09-18
1328 Engineer's Comments on 1st submission 15 days 29-09-18 13-10-18
1329 Resubmission for Code-B Approval 8 days 14-10-18 21-10-18
1330 Engineers review and Code-B approval 15 days 21-10-18 04-11-18
1331 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
1332 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
1333 Single Line Diagram 318 days 04-09-18 18-07-19
1334 Preparation and Submission to Client 25 days 04-09-18 28-09-18
1335 Engineer's Comments on 1st submission 15 days 29-09-18 13-10-18
1336 Resubmission for Code-B Approval 8 days 14-10-18 21-10-18
1337 Engineers review and Code-B approval 15 days 21-10-18 04-11-18
1338 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
1339 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
1340 Sizing Calculation for Bus Bar and 11 KV and LT Swi3tc1h8 Gdaeyasr 04-09-18 18-07-19
1341 Preparation and Submission to Client 25 days 04-09-18 28-09-18
1342 Engineer's Comments on 1st submission 15 days 29-09-18 13-10-18
1343 Resubmission for Code-B Approval 8 days 14-10-18 21-10-18
1344 Engineers review and Code-B approval 15 days 21-10-18 04-11-18
1345 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
1346 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
1347 Sizing calculation for UPS 318 days 04-09-18 18-07-19
1348 Preparation and Submission to Client 25 days 04-09-18 28-09-18
1349 Engineer's Comments on 1st submission 15 days 29-09-18 13-10-18
1350 Resubmission for Code-B Approval 8 days 14-10-18 21-10-18
1351 Engineers review and Code-B approval 15 days 21-10-18 04-11-18
1352 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
1353 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
1354 LT Bus duct sizing calculation 318 days 04-09-18 18-07-19
1355 Preparation and Submission to Client 25 days 04-09-18 28-09-18
1356 Engineer's Comments on 1st submission 15 days 29-09-18 13-10-18
1357 Resubmission for Code-B Approval 8 days 14-10-18 21-10-18
1358 Engineers review and Code-B approval 15 days 21-10-18 04-11-18
1359 Resubmission for Code-A approval 20 days 01-06-19 20-06-19
1360 Engineers review and Code-A approval 28 days 21-06-19 18-07-19
1361 Earthing Grid design Calculation and Earthing
layout
301 days 21-10-18 17-08-19
1362 Preparation and Submission to Client 20 days 21-10-18 09-11-18
1363 Engineer's Comments on 1st submission 12 days 10-11-18 21-11-18
1364 Resubmission for Code-B Approval 10 days 22-11-18 01-12-18
1365 Engineers review and Code-B approval 15 days 02-12-18 16-12-18
1366 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
1367 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
1371 Lighting Design Calculation 321 days 01-10-18 17-08-19
1372 Preparation and Submission to Client 20 days 01-10-18 20-10-18
1373 Engineer's Comments on 1st submission 12 days 21-10-18 01-11-18
1374 Resubmission for Code-B Approval 10 days 02-11-18 11-11-18
1375 Engineers review and Code-B approval 15 days 12-11-18 26-11-18
1376 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
1377 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
1378 Power and Control Cable Schedule 301 days 21-10-18 17-08-19
1379 Preparation and Submission to Client 20 days 21-10-18 09-11-18
1380 Engineer's Comments on 1st submission 12 days 10-11-18 21-11-18
1381 Resubmission for Code-B Approval 10 days 22-11-18 01-12-18
1382 Engineers review and Code-B approval 15 days 02-12-18 16-12-18
1383 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
1384 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
1385 Outdoor Lighting Layout 321 days 01-10-18 17-08-19
1386 Preparation and Submission to Client 20 days 01-10-18 20-10-18
1387 Engineer's Comments on 1st submission 12 days 21-10-18 01-11-18
1388 Resubmission for Code-B Approval 10 days 02-11-18 11-11-18
1389 Engineers review and Code-B approval 15 days 12-11-18 26-11-18
1390 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
1391 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
1392 Dts for Battery and Battery Charger 321 days 01-10-18 17-08-19
1393 Preparation and Submission to Client 20 days 01-10-18 20-10-18
1394 Engineer's Comments on 1st submission 12 days 21-10-18 01-11-18
1395 Resubmission for Code-B Approval 10 days 02-11-18 11-11-18
1396 Engineers review and Code-B approval 24 days 12-11-18 05-12-18
1397 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
1398 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
1399 Overall Cable Routing Diagram 301 days 21-10-18 17-08-19
1400 Preparation and Submission to Client 20 days 21-10-18 09-11-18
1401 Engineer's Comments on 1st submission 12 days 10-11-18 21-11-18
1402 Resubmission for Code-B Approval 10 days 22-11-18 01-12-18
1403 Engineers review and Code-B approval 15 days 02-12-18 16-12-18
1404 Resubmission for Code-A approval 20 days 01-07-19 20-07-19
1405 Engineers review and Code-A approval 28 days 21-07-19 17-08-19
1406 Instrumentation 271 days 15-07-18 11-04-19
1407 Functional Design Specification 159 days 15-07-18 20-12-18
1408 Preparation and Submission to Client 45 days 15-07-18 28-08-18
1409 Engineer's Comments on 1st submission 12 days 29-08-18 09-09-18
1410 Resubmission for Code-B Approval 30 days 10-09-18 09-10-18
1411 Engineers review and Code-B approval 24 days 10-10-18 02-11-18
1412 Resubmission for Code-A approval 20 days 03-11-18 22-11-18
1413 Engineers review and Code-A approval 28 days 23-11-18 20-12-18
1414 Instrument Schedule 109 days 01-08-18 17-11-18
1415 Preparation and Submission to Client 10 days 01-08-18 10-08-18
1416 Engineer's Comments on 1st submission 12 days 11-08-18 22-08-18
1417 Resubmission for Code-B Approval 15 days 23-08-18 06-09-18
1418 Engineers review and Code-B approval 24 days 07-09-18 30-09-18
1419 Resubmission for Code-A approval 20 days 01-10-18 20-10-18
1420 Engineers review and Code-A approval 28 days 21-10-18 17-11-18
1423 Data Sheets of Instruments 95 days 07-08-18 09-11-18
1424 Preparation and Submission to Client 10 days 07-08-18 16-08-18
1425 Engineer's Comments on 1st submission 12 days 17-08-18 28-08-18
1426 Resubmission for Code-B Approval 15 days 29-08-18 12-09-18
1427 Engineers review and Code-B approval 10 days 13-09-18 22-09-18
1428 Resubmission for Code-A approval 20 days 23-09-18 12-10-18
1429 Engineers review and Code-A approval 28 days 13-10-18 09-11-18
1430 I/O Schedule 109 days 15-07-18 31-10-18
1431 Preparation and Submission to Client 15 days 15-07-18 29-07-18
1432 Engineer's Comments on 1st submission 12 days 30-07-18 10-08-18
1433 Resubmission for Code-B Approval 10 days 11-08-18 20-08-18
1434 Engineers review and Code-B approval 24 days 21-08-18 13-09-18
1435 Resubmission for Code-A approval 20 days 14-09-18 03-10-18
1436 Engineers review and Code-A approval 28 days 04-10-18 31-10-18
1437 Cable Schedule 152 days 01-08-18 30-12-18
1438 Preparation and Submission to Client 30 days 01-08-18 30-08-18
1439 Engineer's Comments on 1st submission 20 days 31-08-18 19-09-18
1440 Resubmission for Code-B Approval 25 days 20-09-18 14-10-18
1441 Engineers review and Code-B approval 25 days 15-10-18 08-11-18
1442 Resubmission for Code-A approval 24 days 09-11-18 02-12-18
1443 Engineers review and Code-A approval 28 days 03-12-18 30-12-18
1444 Cable Routing and Instruments Location Layout 152 days 01-08-18 30-12-18
1445 Preparation and Submission to Client 30 days 01-08-18 30-08-18
1446 Engineer's Comments on 1st submission 20 days 31-08-18 19-09-18
1447 Resubmission for Code-B Approval 25 days 20-09-18 14-10-18
1448 Engineers review and Code-B approval 25 days 15-10-18 08-11-18
1449 Resubmission for Code-A approval 24 days 09-11-18 02-12-18
1450 Engineers review and Code-A approval 28 days 03-12-18 30-12-18
1451 FAT and SAT Procedure 118 days 15-12-18 11-04-19
1452 Preparation and Submission to Client 22 days 15-12-18 05-01-19
1453 Engineer's Comments on 1st submission 12 days 06-01-19 17-01-19
1454 Resubmission for Code-B Approval 10 days 18-01-19 27-01-19
1455 Engineers review and Code-B approval 20 days 28-01-19 16-02-19
1456 Resubmission for Code-A approval 25 days 18-02-19 14-03-19
1457 Engineers review and Code-A approval 28 days 15-03-19 11-04-19
1458 Electrical Procurement 432 days 10-09-18 15-11-19
1459 Battery and Battery Charger 191 days 25-11-18 03-06-19
1460 Placement of order 1 day 25-11-18 25-11-18
1461 Submission of Datasheets / Drawings 10 days 26-11-18 05-12-18
1462 Engineer's Comments on 1st submission 15 days 06-12-18 20-12-18
1463 Resubmission 10 days 21-12-18 30-12-18
1464 Engineers review and Code-A approval 15 days 01-01-19 15-01-19
1465 Issue of manufacturing Clearance 5 days 16-01-19 20-01-19
1466 Manufacturing 61 days 21-01-19 22-03-19
1467 Inspection / Review of Test Certificates as
applicable
30 days 23-03-19 21-04-19
1468 Despatch and receipt of Material at Site 40 days 25-04-19 03-06-19
1469 Distribution Box 184 days 25-10-18 26-04-19
1470 Placement of order 1 day 25-10-18 25-10-18
1471 Submission of Datasheets / Drawings 20 days 26-10-18 14-11-18
1472 Engineer's Comments on 1st submission 15 days 15-11-18 29-11-18
1473 Resubmission 5 days 30-11-18 04-12-18
1474 Engineers review and Code-A approval 15 days 05-12-18 19-12-18
1475 Issue of manufacturing Clearance 3 days 20-12-18 22-12-18
1476 Manufacturing 90 days 20-12-18 19-03-19
1477 Inspection / Review of Test Certificates as
applicable
15 days 20-03-19 03-04-19
1478 Despatch and receipt of Material at Site 23 days 04-04-19 26-04-19
1479 Lighting System 191 days 25-11-18 03-06-19
1480 Placement of order 1 day 25-11-18 25-11-18
1481 Submission of Datasheets / Drawings 10 days 26-11-18 05-12-18
1482 Engineer's Comments on 1st submission 15 days 06-12-18 20-12-18
1483 Resubmission 10 days 21-12-18 30-12-18
1484 Engineers review and Code-A approval 15 days 01-01-19 15-01-19
1485 Issue of manufacturing Clearance 5 days 16-01-19 20-01-19
1486 Manufacturing 61 days 21-01-19 22-03-19
1487 Inspection / Review of Test Certificates as
applicable
30 days 23-03-19 21-04-19
1488 Despatch and receipt of Material at Site 40 days 25-04-19 03-06-19
1489 Earthing 159 days 15-12-18 22-05-19
1490 Placement of order 1 day 15-12-18 15-12-18
1491 Submission of Datasheets / Drawings 15 days 16-12-18 30-12-18
1492 Engineer's Comments on 1st submission 20 days 31-12-18 19-01-19
1493 Resubmission 10 days 20-01-19 29-01-19
1494 Engineers review and Code-A approval 20 days 30-01-19 18-02-19
1495 Issue of manufacturing Clearance 3 days 19-02-19 21-02-19
1496 Manufacturing 60 days 22-02-19 22-04-19
1497 Inspection / Review of Test Certificates as
applicable
10 days 23-04-19 02-05-19
1498 Despatch and receipt of Material at Site 20 days 03-05-19 22-05-19
1499 Cable Tray & Cables 181 days 01-01-19 30-06-19
1500 Placement of order 1 day 01-01-19 01-01-19
1501 Submission of Datasheets / Drawings 15 days 02-01-19 16-01-19
1502 Engineer's Comments on 1st submission 20 days 17-01-19 05-02-19
1503 Resubmission 10 days 06-02-19 15-02-19
1504 Engineers review and Code-A approval 15 days 16-02-19 02-03-19
1505 Issue of manufacturing Clearance 3 days 03-03-19 05-03-19
1506 Manufacturing 90 days 06-03-19 03-06-19
1507 Inspection / Review of Test Certificates as
applicable
10 days 04-06-19 13-06-19
1508 Despatch and receipt of Material at Site 17 days 14-06-19 30-06-19
1509 H T panel 309 days 25-10-18 29-08-19
1510 Placement of order 1 day 25-10-18 25-10-18
1511 Submission of Datasheets / Drawings 20 days 26-10-18 14-11-18
1512 Engineer's Comments on 1st submission 15 days 15-11-18 29-11-18
1513 Resubmission 5 days 30-11-18 04-12-18
1514 Engineers review and Code-A approval 15 days 05-12-18 19-12-18
1515 Issue of manufacturing Clearance 3 days 20-12-18 22-12-18
1516 Manufacturing 180 days 20-12-18 17-06-19
1517 Inspection / Review of Test Certificates as
applicable
25 days 18-06-19 12-07-19
1518 Painting and Packaging of Equipment 23 days 13-07-19 04-08-19
1519 Despatch and receipt of Material at Site 25 days 05-08-19 29-08-19
1520 Transformer 301 days 10-09-18 07-07-19
1521 Placement of order 1 day 10-09-18 10-09-18
1522 Submission of Datasheets / Drawings 20 days 11-09-18 30-09-18
1523 Engineer's Comments on 1st submission 15 days 01-10-18 15-10-18
1524 Resubmission 5 days 16-10-18 20-10-18
1525 Engineers review and Code-A approval 15 days 21-10-18 04-11-18
1526 Issue of manufacturing Clearance 3 days 05-11-18 07-11-18
1527 Manufacturing 180 days 05-11-18 03-05-19
1528 Inspection / Review of Test Certificates as
applicable
25 days 04-05-19 28-05-19
1529 Painting and Packaging of Equipment 20 days 29-05-19 17-06-19
1530 Despatch and receipt of Material at Site 20 days 18-06-19 07-07-19
1531 L T panel 309 days 25-10-18 29-08-19
1532 Placement of order 1 day 25-10-18 25-10-18
1533 Submission of Datasheets / Drawings 20 days 26-10-18 14-11-18
1534 Engineer's Comments on 1st submission 15 days 15-11-18 29-11-18
1535 Resubmission 5 days 30-11-18 04-12-18
1536 Engineers review and Code-A approval 15 days 05-12-18 19-12-18
1537 Issue of manufacturing Clearance 3 days 20-12-18 22-12-18
1538 Manufacturing 180 days 20-12-18 17-06-19
1539 Inspection / Review of Test Certificates as
applicable
25 days 18-06-19 12-07-19
1540 Painting and Packaging of Equipment 23 days 13-07-19 04-08-19
1541 Despatch and receipt of Material at Site 25 days 05-08-19 29-08-19
1542 Erection 107 days 01-08-19 15-11-19
1543 Erection of Electrical Equipment 90 days 01-08-19 29-10-19
1544 Site Acceptance test (Dry / Wet) for Electrical
Equipments as applicable
15 days 01-11-19 15-11-19
1545 Instrumentation Procurement 419 days 23-09-18 15-11-19
1546 Placement of order 9 days 23-09-18 01-10-18
1547 Submission of Datasheets / Drawings 25 days 02-10-18 26-10-18
1548 Engineer's Comments on 1st submission 20 days 27-10-18 15-11-18
1549 Resubmission 20 days 16-11-18 05-12-18
1550 Engineers review and Code-A approval 28 days 06-12-18 02-01-19
1551 Issue of manufacturing Clearance 20 days 03-01-19 22-01-19
1552 Manufacturing 80 days 23-01-19 12-04-19
1553 Inspection / Review of Test Certificates as applicable 20 days 13-04-19 02-05-19
1554 Painting and Packaging of Equipment 20 days 03-05-19 22-05-19
1555 Despatch and receipt of Material at Site 30 days 23-05-19 21-06-19
1556 Instrumentation Cable - Control & Power Cable 212 days 09-11-18 08-06-19
1557 Placement of order 10 days 09-11-18 18-11-18
1558 Submission of Datasheets / Drawings 25 days 19-11-18 13-12-18
1559 Engineer's Comments on 1st submission 15 days 14-12-18 28-12-18
1560 Resubmission 10 days 29-12-18 07-01-19
1561 Engineers review and Code-A approval 21 days 08-01-19 28-01-19
1562 Issue of manufacturing Clearance 10 days 29-01-19 07-02-19
1563 Manufacturing 70 days 08-02-19 18-04-19
1564 Inspection / Review of Test Certificates as
applicable
21 days 19-04-19 09-05-19
1565 Despatch and receipt of Material at Site 30 days 10-05-19 08-06-19
1566 Cable tray and Support 212 days 09-11-18 08-06-19
1567 Placement of order 10 days 09-11-18 18-11-18
1568 Submission of Datasheets / Drawings 25 days 19-11-18 13-12-18
1569 Engineer's Comments on 1st submission 15 days 14-12-18 28-12-18
1572 Resubmission 10 days 29-12-18 07-01-19
1573 Engineers review and Code-A approval 21 days 08-01-19 28-01-19
1574 Issue of manufacturing Clearance 10 days 29-01-19 07-02-19
1575 Manufacturing 70 days 08-02-19 18-04-19
1576 Inspection / Review of Test Certificates as
applicable
21 days 19-04-19 09-05-19
1577 Despatch and receipt of Material at Site 30 days 10-05-19 08-06-19
1578 EPABX System 124 days 01-04-19 02-08-19
1579 Placement of order 1 day 01-04-19 01-04-19
1580 Submission of Datasheets / Drawings 10 days 02-04-19 11-04-19
1581 Engineer's Comments on 1st submission 10 days 12-04-19 21-04-19
1582 Resubmission 10 days 22-04-19 01-05-19
1583 Engineers review and Code-A approval 28 days 02-05-19 29-05-19
1584 Issue of manufacturing Clearance 20 days 30-05-19 18-06-19
1585 Manufacturing 20 days 19-06-19 08-07-19
1586 Inspection / Review of Test Certificates as
applicable
10 days 09-07-19 18-07-19
1587 Despatch and receipt of Material at Site 15 days 19-07-19 02-08-19
1588 Online Analysers 272 days 23-09-18 21-06-19
1589 Placement of order 9 days 23-09-18 01-10-18
1590 Submission of Datasheets / Drawings 25 days 02-10-18 26-10-18
1591 Engineer's Comments on 1st submission 20 days 27-10-18 15-11-18
1592 Resubmission 20 days 16-11-18 05-12-18
1593 Engineers review and Code-A approval 28 days 06-12-18 02-01-19
1594 Issue of manufacturing Clearance 20 days 03-01-19 22-01-19
1595 Manufacturing 80 days 23-01-19 12-04-19
1596 Inspection / Review of Test Certificates as
applicable
20 days 13-04-19 02-05-19
1597 Painting and Packaging of Equipment 20 days 03-05-19 22-05-19
1598 Despatch and receipt of Material at Site 30 days 23-05-19 21-06-19
1599
1600
1601 PLC Panels alongwith necessary hardware &
Software (PLC Processor/IO
Parts/Communication Modules/Power
Supply/Alarm Annunciators/Selector
Switches/Work Station PC/Ethernet Switches/RIO
Modules/Wireless GSM/GPRS / Gateways / 62"
LCD Screen etc)
345 days 05-11-18 15-10-19
1602 Placement of order 1 day 05-11-18 05-11-18
1603 Submission of Datasheets / Drawings 30 days 06-11-18 05-12-18
1604 Engineer's Comments on 1st submission 28 days 06-12-18 02-01-19
1605 Resubmission 20 days 03-01-19 22-01-19
1606 Engineers review and Code-A approval 15 days 23-01-19 06-02-19
1607 Issue of manufacturing Clearance 15 days 07-02-19 21-02-19
1608 Manufacturing 180 days 22-02-19 20-08-19
1609 Inspection / Review of Test Certificates as
applicable
21 days 21-08-19 10-09-19
1610 Painting and Packaging of Equipment 10 days 11-09-19 20-09-19
1611 Despatch and receipt of Material at Site 25 days 21-09-19 15-10-19
1612 Erection 107 days 01-08-19 15-11-19
1613 Erection of Electrical Equipment 91 days 01-08-19 30-10-19
1614 Site Acceptance test (Dry / Wet) for
Instrumentationl Equipments as applicable
15 days 01-11-19 15-11-19
1617 Commissioning 92 days 01-11-19 31-01-20
1618 Preparation and Submission of Training Manual 50 days 10-12-19 28-01-20
1619 Preparation and Submission of O & M Manual 50 days 10-12-19 28-01-20
1620 Preparation and Submission of As Built Drawings 50 days 10-12-19 28-01-20
1621 Test on Completion 30 days 01-11-19 30-11-19
1622 Trial Run and Commissioning 60 days 03-12-19 31-01-20
1623 Trainning of BWSSB Staff 10 days 21-01-20 30-01-20
1624 Handing over of Plant and Taking over Certificate 1 day 31-01-20 31-01-20